## Slide 1: RunCo Report for IOTA/FAST Meeting 05/07
Important Dates:
  FAST Shutdown: ~end of June(ish)
  Main Complex Summer Shutdown
    June 28–~09/19 (HEP ~10/04)(AD/Ops/Schedule)
  FESS:
    Adams Strainer continuous cycling is fixed™ again again
    FESS completed™ switching NML to cooling May 6
    NML 13.8 kV switch/transformer HV-PM August 3
    Lab B HV-PM (Cryo): July 23 (FAST @ RT by then)
    KRS & MSS Outages (30 min): 08/30 & 09/07 & 09/13
Linac:
  Camera servers being worked on (ongoing)
  Kinney MPS upgrade last Monday 4/19
    Recovery till 5/5 morning (Downtime)
    CC1 and CM not stable –contamination (CMTF)
    Thermal cycled the JT circuit to >80K. CM <40K.
    Fridge still has low excess capacity. Needs warm-up.
IOTA: Working on lifetime & aperture & lattice & orbit
  We were up to 0.2 mA and 15 minutes (not at the same time)
  M3R Trim coils still need checking
  150 MeV studies when Cryo is up
    IBEND needs slow ramp-down (in sequencer)
  OSC studies when Cryo is up
    (e-/PU/KU alignments, tuning, interference)
    Instrumentation work in IOTA
  Cables pulled for OSC & IOTA being terminated
    Work to occur during all week access
    SCam electrical hook-ups
    SCam optically aligned
Notes: Why are you looking down here? Look back at the slide.

## Slide 2: Run Plan for Next Week (May 10)
Monday – Friday
  Monday Morning CA (notify RunCo)
    IOTA OSC work
  CA possible in the mornings (w/ RunCo approval)
    OSC diagnostics installation
    IOTA Cable termination
    URSSE tweaking and calibration
  Run beam in IOTA after noon (maybe all day):
    OSC running
    lattice tunning for OSC
    150 commissioning