## Slide 1: Project X Strategy
Steve Holmes
Accelerator Sector Planning and Strategy Workshop
October 27, 2011

## Slide 2: Outline
Introduction: Background information, recent accomplishments, history
Strategy
  Ultimate goal: where should this activity be in 10 years? What is the central overarching goal of this activity?
  Goals in the near-term, mid-term and long-term: What are some clear goals for this activity over the next 10 years? What are the targeted outcomes (i.e. specific goals with a milestone)
  Overall plan: Describe the full plan for this activity as it develops over the full life of the activity, or over the next 10 years.
  Barriers: are there systematic barriers (structural, intellectual, financial, organizational,…) that need to be solved in order to reach the ultimate goal?
Near-term plan
  FY12 Plan: what do we plan on doing this year? What are the actual tasks that have to be carried out and what are all the subactivities?
  FY12 Deliverables: what will be accomplished by the end of FY12?
  FY12 Metrics: how should we measure the success of this activity this year? Identify quantifiable metrics, milestones and goals.
  FY13 and 14 Plans and goals: what are the goals for this activity in FY13 and FY14?
Resources
  What resources are needed to meet this year’s goals? Are the planned resources consistent with the established goals and milestones?
  What resources are needed to meet the 10 year goal?
Risks
  What are the risks to this year’s plan?
  What are the risks to reaching the 10-year goals?

## Slide 3: Strategic Context
Fermilab is the sole remaining U.S. laboratory providing facilities in support of accelerator-based Elementary Particle Physics.
The Fermilab strategy is to
mount a world-leading program
at the intensity frontier, while
using this program as a bridge
to an energy frontier facility
beyond LHC in the longer term.
Project X is the key element of
this strategy

## Slide 4: Mission Elements
A neutrino beam for long baseline neutrino oscillation experiments
  2 MW proton source at 60-120 GeV
High intensity, low energy protons
for kaon, muon, and neutrino based
precision experiments
  Operations simultaneous with the
  neutrino program
A path toward a muon source for
possible future Neutrino Factory
and/or a Muon Collider
  Requires ~4 MW at ~5-15 GeV
Possible missions beyond EPP
  Standard Model Tests with nuclei and energy applications

## Slide 5: Reference Design
Reference Design supports all mission elements
Stable for more than a year
3 MW @ 3 GeV
200 kW @ 8 GeV
2 MW @ 120 GeV

## Slide 6: Reference Design Site

## Slide 7: Organization
Project Office
  Project Manager S. Holmes
  Deputy Project Manager TBD
  Project Scientist/Accelerators S. Nagaitsev
  Project Scientist/Experiments R. Tschirhart
  Project Engineer J. Kerby
  International Coordinator S. Mishra
  Budgeting/Scheduling E. Peoples
  Financials M. Smith
Level 2 Managers
  CW Linac R. Kephart, B. Lebedev
  Pulsed Linac N. Solyak
  MI/Recycler I. Kourbanis
  Conventional Facilities TBD (R. Alber, acting)
  Experimental Facilities R. Tschirhart
Level 3 Managers
  We have assigned a complete complement of L3Ms

## Slide 8: Collaboration
Two MOUs covering the RD&D Phase
  National IIFC
  ANL ORNL/SNS BARC/Mumbai
  BNL MSU IUAC/Delhi
  Cornell TJNAF RRCAT/Indore
  Fermilab SLAC VECC/Kolkata
  LBNL ILC/ART
Informal collaboration/contacts with CERN/SPL, ESS, China, Korea
Responsibilities of collaborators in the R&D (and construction) phase are becoming relatively well established

## Slide 9: Strategy
2021 Goal: Project X construction is nearing completion
Working Timeline (not approved by DOE)
  CD-0 FY 2012
  CD-1 FY 2013
  CD-2 FY 2014
  CD-3 FY 2016
  CD-4 FY 2021

## Slide 10: Strategy RD&D Program
Goal: Mitigate risk associated with technical, cost, and schedule uncertainties
  Facility performance
    Integrated facility goals defined by Functional Requirements Specification (FRS)
    Facility configuration including upgrade paths; systems integration
  CW linac
    The first 15 MeV is key to the Reference Design concept.
    Front-end, chopper, low-b acceleration, beam loss mitigation
  Pulsed linac
    Pulsed linac has diverged from ILC requirements due to low current
    Long-pulse beam operation, b=1 accelerating structures/modules
  MI/Recycler
    H- injection; factor of three increase in beam intensity (relative to NOvA)
    Injection, instabilities, rf systems

## Slide 11: Strategy R&D Program
The primary elements of the R&D program include:
  Development of a wide-band chopper
    Capable of removing bunches in arbitrary patterns at a 162.5 MHz bunch rate
  Development of an H- injection system
    Require between 4.4 – 26 msec injection period, depending on pulsed linac operating scenario
  Superconducting rf development
    Six different cavity types at four different frequencies
    Appropriate rf sources
    Development of partners and vendors
  Design development
    Beam and e-m modeling
    reliability analysis
    Upgrade paths: MC and Muons@PX Task Forces
  Test Facilities
    Next slide
Goal is to complete R&D phase by 2016

## Slide 12: Strategy R&D Test Facilities
New Muon Lab (NML) facility under construction for ILC RF unit test
  Eventually will house PX style CM (but pulsed)
Meson Detector Building (MDB) Test Facility
  2.5 MeV beam (p, H-): 1% duty factor, 3 msec pulse
    Initial chopper tests
    H- beam instrumentation development
  Test stands for dressed cavities at 1.3 GHz, 650 MHz, and 325 MHz
Project X Injector Experiment PXIE)
  Prototype of first 10-30 MeV of Project X.
    Validate Project X front end concept  mitigate primary technical risk element within the Reference Design.
    Operate at full design parameters
  Integrated systems test goals:
    1 mA average current with 80% chopping of beam delivered from RFQ
    Efficient acceleration with minimal emittance dilution through ~15 MeV
  Potential utilization in Project X facility following successful demonstration
  Collaboration between Fermilab, ANL, LBNL, (SLAC); India & China?
Oct 2016: Beam through b=0.1 , 0.2 CM at ~10 MeV with nearly final parameters (1 mA cw, 5 mA peak, arbitrary bunch chopping)

## Slide 13: Strategy PXIE Scope
CW H- source delivering 5 mA at 30 keV
LEBT with beam pre-chopping
CW RFQ operating at 162.5 MHz and delivering 5 mA at 2.1 MeV
MEBT with integrated wide band chopper and beam absorbers capable of generating arbitrary bunch patterns at 162.5 MHz, and disposing of 4 mA average beam current
Low beta superconducting cryomodules capable of accelerating 1 mA to 15 MeV
Beam dump capable of accommodating 1 mA at 15 MeV (15 kW) for extended periods.
Associated beam diagnostics, utilities and shielding
Beam Dump
Ion Source
LEBT
RFQ
MEBT
HWR
SSR1
Diagnostics
~40 m

## Slide 14: Strategy Barriers
Intellectual
  Wideband Chopper
  Multi-MW target stations
  Halo formation/loss control and mitigation
  H- injection
  Cavity/cryomodule design and fabrication plan
Financial
  PXIE will probably cost $40-50M
  Another ~$50M to complete srf R&D and get to CD-3
Organizational
  Matrix organization – achieving appropriate priority within the divisions
  Staff fragmentation
  Integration of collaborators
  Coordination of Project X, SRF, and GAD activities

## Slide 15: Near Term Plan Goals for FY2012
Project Management
  Update the RDR to current configuration
  Receive CD-0!
    Assure all required documentation is up to date
    Support laboratory preparations for the DOE Intensity Frontier Workshop
  Initiate work on Conceptual Design Report and other documentation for CD-1
  Continue reliability modeling with OSU
  Receive/evaluate reports from MC and mu2e Task Forces
  Coordinate all collaboration activities

## Slide 16: Near Term Plan Goals for FY2012
CW Linac/PXIE
  Conventional facilities @ CMTF
    Complete shielded enclosure – ready for equipment installation.
  LEBT
    Complete design and all parts ordered*
    Ion source commissioning (at LBNL)
  RFQ
    Complete design, ready for procurement (LBNL/FNAL)
    Specifications complete, ready for procurement: rf & water systems*
  MEBT
    Vacuum prototype chopper kicker tested (bandwidth and average power)*
    12 kW prototype beam absorber designed, fabricated and tested (e-beam) *
    MEBT design 50% complete
  * Need a mechanical engineer assigned to each of these activities: ~2.5 FTE total

## Slide 17: Near Term Plan Goals for FY2012
CW Linac/design & development
  Complete lattice design for CW linac (including front end)
    Preliminary specifications on all linac components: cavities, CM, magnets, correctors, diagnostics
  Beam dynamics studies
    Preliminary tolerances: alignment, stability, optical mismatch
    Failure analysis: effect of failed components on performance and correction schemes
  RF sources (w/ SLAC, India)
    325 MHz test stand operational at MDB (couplers)
    Complete coupler designs; prototype
    Solid state development at 650 MHz (w/SLAC)
  Cryogenics
    Heat load estimates, pre-conceptual design, segmentation
  Design SSR1 (test) cryomodule

## Slide 18: Near Term Plan Goals for FY2012
Pulsed Linac
  Complete lattice design
    Specifications for alignment and RF tolerances
    Failure analysis
  Design of the transport lines to/from pulsed linac
  Conceptual design of the HLRF system
    Systems specifications
    Survey of alternatives (klystron, IOT, magnetron)
  LLRF performance study for long pulse operation.
  Complete conceptual and EM design of splittable SC (focusing) magnet
  Conceptual design of the cryogenic systems and specifications
  Specifications for beam diagnostics in Linac and transport lines

## Slide 19: Near Term Plan Goals for FY2012
Main Injector/Recycler
  RF systems
    Complete design of the second harmonic (106 MHz) cavity (w/SLAC)
    Fabricate 53 MHz cavity mockup for low level measurements
  Instabilities
    e-cloud
      In-situ measurements of different material samples.
      Evaluate beam conditioning effect on SEY (in MI).
      Set-up coating facility (sputtering) in E4R.
    Space Charge
      Continue simulations with SYNERGIA and IMPACT/MLI
  H- Stripping injection
    Simulate rotating foil with tracking.
      Rotating foil prototype (w/ANL)
    Order parts for Laser stripping R&D (w/SNS)

## Slide 20: Near Term Plan Goals for FY2012
Experimental Facilities
  Prepare for DOE workshop
  Preliminary identification of day one experiments and facilities
Conventional Facilities
  Master planning as relate to PX siting and utility needs
    Consolidation of new project (LBNE, MU2E, PX, g-2) infrastructure
  Preliminary design of critical infrastructure needs:
    Electrical single lines and load tables
    Cooling schematics with input from pond studies; cost analysis of various cooling options (cooling towers, new pond(s), ICW, etc.)
    Update siting scenarios against latest wetland studies,
    Discipline reviews of CD-0 cost estimate Review and revise RLS to support a CD-0 review
  General support of alternate configurations, value engineering and phasing options

## Slide 21: Near Term Plan Goals for FY2013-14
Primary goal is to get to CD-2 by the end of FY2014
  Complete a Conceptual Design Report
  Establish Project X configuration
    Backed up by beam simulations and technology development
  Identify baseline technologies for all major systems
    Feasible solutions for: wideband chopper, H- injection, long pulse operations,
  Complete baseline cost estimate and resource loaded schedule
  Semi-infinite list of documentation
    CDR, RMP, RA, AS, PMP, PEP, HA, EA, SVAR
  Agreed upon responsibilities among collaborators for the construction phase
Major SRF Goals
  Protoype of every cavity type, meeting performance requirements in horizontal test
  Cryomodule design for all cavity types.
  Prototype cryomodule for each frequency

## Slide 22: Resources FY2012 Budget
Note: Dollar amounts are direct
$600K of collaborator funding in 1.2 forward funded in FY11
New WBS consistent with what we will use as a project
FY12 budget has been developed within this WBS
A new set of task codes, aligned with this WBS, will become operational on October 1, 2011
1.0 Project X
1.1
Project Management
FTE 6.0
M&S $300
Collab $0
MR $200
1.2
CW Linac
FTE 17.5
M&S $2310
Collab $450
1.4
MI/ Recycler
FTE 3.6
M&S $200
Collab $250
1.3
Pulsed Linac
FTE 4.35
M&S $50
Collab $0
1.6 Conventional Facilities
FTE 0
M&S $170
Collab $0
1.5 Experimental Facilities
FTE 2.2
M&S $130
Collab $0

## Slide 23: Resources Labor Plan/Accelerator Sector

## Slide 24: Resources Labor Plan Commentary
Accelerator Division
  Primary shortfall is in mechanical engineering
    Impact is on PXIE preparation
  Primary concern is fragmentation
    13 FTE spread over 71 people(!)
  Goal is to eliminate half the shortfall and decrease fragmentation
Technical Division
  Fragmentation, not as severe as in AD
APC, PPD, CD, DIR
  OK as is

## Slide 25: Resources FY2013 and Beyond
FTE Requirements
  R&D phase (to CD-3) requires ~350 person-years
    (This does not include srf development)
    (This does not include experimental facilities)
    ~90 FTE × 4 years
    ~60 FTE at Fermilab if 1/3 could come from collaborators
  Construction phase requires ~854 person-years
    This does not include experimental facilities)
    ~170 FTE × 5 years
    ~100 FTE at Fermilab if 40% could come from collaborators

## Slide 26: Risks
FY2012
  Lack of adequate (staff) resources
  Lack of community support for the physics program
    No CD-0
FY2013-FY2021
  Lack of adequate resources
  Failure to meet technical specification
    Wideband chopper
    Recycler injection
    High power targets
  Failure to meet cost goals
  Failure to develop qualified vendors
  Unable to establish the required CM production rate
  Starting construction before confirmed technical solution
    Consequence: Higher contingency requirement
  No financing plan for PX within DOE or significantly drawn out schedule
    No significant in-kind contribution from overseas

## Slide 27: Backup Slides

## Slide 28: Budget Commentary
FY2011
  Budgeted 27.4 FTE
  Averaged ~21 FTE over the year
  There will be ~$100K of requisitions in process at the end of FY2011
    Under-run will be $70K (M&S) + $672K (SWF) + $632K (OHD) = $1,374K
FY2012
  FTE (request) is 35.05
    67% increase from FY2011 actual
    29.55 allocated
  M&S (request, direct) is $4,187K
    54% increase from FY2011 budgeted/actual
    Includes $1,637K earmarked for collaborators
    $347K underfunded relative to identified activities
  ~$200K is budgeted retained in reserve. Primary candidates for the reserve :
    Enhanced support for PXIE
    Increased collaborator support
  Rebalance
    32.0 FTE (engineers, drafters)
    $4,570 M&S (direct)

## Slide 29: Requests
Carryover of M&S to cover the requisition in process at the end of FY2011 + OHD associated with all uncosted obligations
  Projecting $70K direct + $196K OHD
Request carryover of $200K + OHD of SWF
  Retain in reserve for the purpose of supporting expansion of the Project Office following CD-0
With this we should be able to maintain sufficient progress toward a construction start in 2016-2017 timeframe.

## Slide 30: FY2011 Budget Actual/Projected
FY11 Budget Actual to date* %Spent RIPs
SWF $3,974 $3,077 77%
M&S $2,718 $2,030 75% $714
Overhead $3,837 $2,975 78%
TOTAL $10,529 $8,082 77% $714
*Through 8/31/11
FY11 Budget Projected %Spent RIPs
SWF $3,974 $3,302 83%
M&S $2,718 $2,648 97% $100
Overhead $3,837 $3,205 83%
TOTAL $10,529 $9,155 87% $100

## Slide 31: FY2012 Budget
Note: Significant SRF & GAD activities are not included in this budget
  GAD supports cavity/CM development at all frequencies
  GAD supports MDB beam facility
  SRF supports infrastructure, including test stands at MDB and CMTF
Note: The budget presented is for accelerator design/development only
  Project Scientist for Experimental Programs is supported on Physics Research/Intensity Frontier
FY2012 Budget Guidance $13,000
Plan DSC Upload
FTE 35.05 29.54
SWF $4,516 $3,924
M&S/FNAL $2,550 $3,473
M&S/Collaborators $1,637 $1,637
Overhead $4,297 $3,966
TOTAL $13,000 $13,000

## Slide 32: Labor Plan Laboratory Total

## Slide 33: Labor Plan Computing, PPD, Directorate