## Test infrastructure
Task Name | Deliverable | Resource | Start | Finish | Duration | Comment
Installation
| Room temperature auxiliary piping | Cryo techs, welders | 2024-06-01 | 2024-09-29 | 120 | cold box vendor delivery date
| vacuum jacket transfer line installation | Cryo techs, welders | 2024-06-01 | 2024-09-29 | 120 | parallel with room temperature piping installation
| Controls programming, eletrical wiring and HMI programming | Controls engineer, eletrical engineer, computing specialist | 2024-06-01 | 2024-09-29 | 120 | starts after vendor delivery of valve box and transfer line
ORC and Safety Approval
| In-kind contribution safety documentation | Engineer | 2022-01-01 | 2024-01-01 | 730 | cryostat and endcap documents from INFN
Testing
| Initial cooldown/commissioing | Engineer, cryo techs | 2024-10-18 | 2024-11-17 | 30 | start date tied to comissioinig of the cold box. 1 month for initial commissioning and cooldown
| steady state testing | Engineer, cryo techs | 2024-11-18 | 2025-01-02 | 45 | acceptance tests, steady state operation
| warmup and ready for removal | Engineer, cryo techs | 2025-01-03 | 2025-02-02 | 30
Formulas:
Finish = [Start]+[Duration]
Start = [Start, row above]
Start = [Finish, row above]+1