## Slide 1: Inventory
Cable at FNAL | Qualified
P43OL1139 | Q
P43OL1147 | Q
P43OL1151 | Q
P43OL1257 | Q
P43OL1259 | Q
P43OL1163 | QXFA 138
P43OL1164 | Y
P43OL1165 | Y
P43OL1167 | Y
Cable at BNL | Qualified
P43OL1158 | QXFA228
P43OL1161 | Y
P43OL1166 | Y
Coil Parts | Qt.
Pole | 23 sets
End Parts | 27 sets
Wedges | 68 sets
QH Trace | 44 sets
NbTi cable | 40 sets
DR related with IL impregnation cloth:
  Currently all the S2 glass components are laser cut upon the email request. The autoCAD models used to cut the components were made by the tech based on the drawings. These components are visual inspected and put in the drawers on the coil production floor.
  Prevention plan (proposed):
    Fabricate all the components at once, route them in QC, stock in IB2 instead of coil production floor, and issue these soft components together with coil pole, wedge, end parts.
    Issue travelers to control the fabrication process if fabricate the components every year based on coil production rate
Start work on part kit for QXFA 231 later this week.

## Slide 2: Procurement Status
Coil Parts and Materials Status on Jul 26, 2021
Coil Part in FY 21 | PO | Qt. | Delivery Date | In Process /Received
Modified IC3 | ˅ | 1 | 09/30/2021 | 
HH2619 VT wire | ˅ | 3000 ft | 07/26/2021 | Received
Pole | ˅ | 12 sets | 12/31/2021 | 
 | July 2021 | 4 sets |  | 
End Parts | ˅ | 12 sets | 12/31/2021 | 
 | July 2021 | 4 sets |  | 
Plasma Coating on AUP parts | July 2021 | 12 sets |  | 
 | Aug. 2021 | 4 sets |  | 
Plasma Coating on CERN parts | Oct. 2021 | 16 + sets |  |