## Slide 1: Risk Analysis and Covid-19
Lucas Taylor
HL-LHC CMS Upgrades Associate PM
Fermilab Risk Manager
PIP-II Risk Manager
NSF MREFC Annual Review, 25th August 2021
Draft updated
25th Aug 2021
Version 2

## Slide 2: Outline
Non-Covid-19 Risk Analysis
  Charge 2c: Risk management process, […] adequacy of the contingency budget and schedule to mitigate future non-COVID risks. […] completeness of the risk register […] non-COVID related threats and opportunities with appropriate probabilities and estimated cost and schedule.
Covid-19 Risk Scenario Analysis
  Charge 3a: […] COVID impact modelling […] of forecast COVID-related cost and schedule impacts. […] realism of assumptions and the credibility of the models used, and […] additional schedule and budget needs. […]
Towards a re-baseline
  Charge 3d: Do the materials […] provide adequate substantiation for re-baselining within the next 6-12 months? If not, what criteria must be satisfied as a precondition for conducting a re-baselining review that would confidently bound estimates for additional schedule and budget […]?

## Slide 3: Outline
Non-Covid-19 Risk Analysis
  Charge 2c: Risk management process, […] adequacy of the contingency budget and schedule to mitigate future non-COVID risks. […] completeness of the risk register […] non-COVID related threats and opportunities with appropriate probabilities and estimated cost and schedule.
Covid-19 Risk Scenario Analysis
  Charge 3a: […] COVID impact modelling […] of forecast COVID-related cost and schedule impacts. […] realism of assumptions and the credibility of the models used, and […] additional schedule and budget needs. […]
Towards a re-baseline
  Charge 3d: Do the materials […] provide adequate substantiation for re-baselining within the next 6-12 months? If not, what criteria must be satisfied as a precondition for conducting a re-baselining review that would confidently bound estimates for additional schedule and budget […]?

## Slide 4: Risk Management Process
We follow the Fermilab-standard risk management procedures which are based on PMI’s PMBOK, NSF MFG, DOE O 413.3b
  Threats: negative risks – minimize probability and impacts
  Opportunities: positive risks – maximize probability and impacts
  Uncertainties: positive or negative – need to manage them
Risk identification is carried out by SMEs, CAMs, L2s, PM
  Risk workshops, brainstorming, reviews of WBS and RBS
  Estimate risk probability, cost and schedule impacts  Risk Register
Risk mitigations are pre-emptive actions in our base plans
  R&D, pre-production, QA/QC, multiple vendors, redundant facilities…
Risk response plans cope with residual risk that cannot be mitigated
  Risk responses use cost and schedule contingency
  In extremis: exercise downscope options  CMS-doc-13357
MC analysis aggregates all risks to determine contingency needs

## Slide 5: Risk Management Process
Risks documented in the Fermilab-standard Risk Register tool
Risk Ranking Matrix grades risks according to management level
  High rank  PM
  Medium  L2
  Low  CAM
Risk Management Board reviews all risks every ~2 months
Risk Register  CMS-doc-12897
Risk Mngt. Plan  CMS-doc-13408

## Slide 6: Cost estimate uncertainty (EU)
Each P6 activity has cost EU to help mitigate cost risk from uncertainties in labor needs, vendor costs, etc.
  EU is percentage of base cost, depending estimate maturity
  ~$1.4M of EU “released” so far as activities were completed
EU is parametrized by min/likely/max
  In the risk analysis, EU is modeled with
  triangle probability distribution functions
Correlations are taken into account by grouping related activities into categories of “Cost drivers”
  E.g. multiple batches of the same item have correlated costs
Probability
Impact
Min
Likely
(point estimate)
Max
Mean

## Slide 7: Risks
1 risk
3 risks
10 risks
12 risks
7 risks
4 risks
3 risks
3 risks
5 risks
1 risk
2 risks
3 risks
54 risks in total

## Slide 8: Risk changes since MREFC / pandemic start
Reviewed and updated all risks: 9 decreased, 2 increased
  Main cost savings from project wide risks
    RU-402-1-01-N PM - Foreign exchange rates $777k → $463k
    RU-402-1-02-N PM - Future escalation rates $433k → $327k
Merged L2 lpGBT risks into single common correlated risk
Retired three risks
  RT-402-1-15-N PM - Change of overhead rates
  RT-402-5-06-N EM – lpGBT or VL+ components delays GE2/1
  RT-402-7-21-N FP – Module production delayed
Added 6 new Trigger risks for improved performance
  More physics capability … but at a potential mean cost of ~ $444k
    Muon Trigger: RT-402-9-[11,12,13,14]
    Track Trigger: RT-402-9-[15,16]

## Slide 9: High Rank Risks
Risk Register  CMS-doc-12897
Risk Mngt. Plan  CMS-doc-13408
*
*
*
*
*
Common risks

## Slide 10: Contingency Analysis
We aggregate the cost and schedule impacts of all risks using Oracle’s Primavera Risk Analysis Monte Carlo framework
PRA Risk Monte Carlo
Risks do or do not happen according to their probabilities
Sample the ranges of impacts
Results in a new project scenario
Repeat 1. – 3.  many scenarios
Primavera P6
Resource
Loaded Schedule
Risk
Register
Probability
Impact
Min
Likely
Max
Mean
Cost and schedule probability distributions
MC produces probability distributions for total cost and schedule impacts
 cost and schedule contingency needs at given confidence levels
Risk Register  CMS-doc-12897
Risk Mngt. Plan  CMS-doc-13408

## Slide 11: Cost contingency (non-Covid risks)
Contingency available = $ 17,857 k
  Data Date = 1 June 2021 (Monthly report #14, CMS-doc-14298)
Contingency need = $17,036 k (EU + risk MC at 90% CL)
We can complete the project within cost at 95% CL
  Not including future Covid risks

## Slide 12: Schedule delays since MREFC start
Barrel Calo.
EM - CSC
EM - GE2/1
EM – ME0
Forward Pixels
Muon Trigger
Track Trigger
LHC and CMS need by dates ( ) remain fixed, despite Covid
L2 / L3 finish dates ( ) are all sliding due to Covid, eating float

## Slide 13: Schedule delays since MREFC start
L2/L3 finish dates are delayed up to 8 months since start of MREFC / pandemic (→ plot)
  Delays are mostly due to Covid lockdowns, Covid safe-working inefficiencies, and Covid delays of partners / vendors
LHC schedule and hence the CMS need-by dates have not yet been updated for Covid
Hence, Covid delays have eaten into our schedule contingency

## Slide 14: Non-Covid risk MC analysis – TFPX example
402.7 Forward Pixels
Early
finish
30 Jun 2026
CMS
need by
5 Feb 2027
Finish including
risk at 90% CL
6 May 2027
TFPX can be delivered before the CMS need by date at only 75% CL
including all delays so far, and future risks, but not yet including future Covid delays

## Slide 15: Non-Covid-19 schedule risk
Early finish dates (baseline plan, without risk) precede CMS need by dates by 7 – 24 months
Non-Covid risks delay L2/L3 finish dates by 6 – 18 months (at 90% CL)
Not all deliverables have enough float at 90% CL
Including all risks

## Slide 16: Non-Covid-19 schedule risk
Barrel Calorimeter and Endcap Muons have adequate schedule contingency allowing for all non-Covid-19 risks.
  7.9–17.7 months of contingency (at 90% CL) before need by dates
Forward Pixels: 90% CL is 3 months after CMS need by
  The project can only finish on time at 75% confidence level (which is uncomfortable) … not including any additional Covid delays
Muon Trigger and Track Trigger: much of the risk delay is due to potential CMS decisions to pursue higher performance options
  We assume CMS would not “self-inflict” such risk delays if they could jeopardize on-time delivery of the Trigger
  Re-run risk MC without these risks, i.e. RT-402-9-[11,12,13,14,15,16]
  Muon Trigger has 8.3 months of float at 90% CL (was –0.3 months)
  Track Trigger has 2.4 months of float at 90% CL (was –8.5 months)
  Also, the need by date for the Track Trigger is being re-evaluated

## Slide 17: Non-Covid-19 schedule risk
Re-run MC analysis excluding Trigger risks related to enhanced Trigger performance
  RT-402-9-[11,12,13,14,15,16]
All deliverables now have enough float at 90% CL, except TFPX (only 75% CL)
Not including future Covid delays
Without risks related to enhancing the Trigger performance

## Slide 18: Outline
Non-Covid-19 Risk Analysis
  Charge 2c: Risk management process, […] adequacy of the contingency budget and schedule to mitigate future non-COVID risks. […] completeness of the risk register […] non-COVID related threats and opportunities with appropriate probabilities and estimated cost and schedule.
Covid-19 Risk Scenario Analysis
  Charge 3a: […] COVID impact modelling […] of forecast COVID-related cost and schedule impacts. […] realism of assumptions and the credibility of the models used, and […] additional schedule and budget needs. […]
Towards a re-baseline
  Charge 3d: Do the materials […] provide adequate substantiation for re-baselining within the next 6-12 months? If not, what criteria must be satisfied as a precondition for conducting a re-baselining review that would confidently bound estimates for additional schedule and budget […]?

## Slide 19: Covid-19 impacts
Lockdowns in Spring 2020 restricted access to labs; then labs re-opened with enhanced safety (PPE, distancing)
Many people have been teleworking from home
Project work has continued but with diminished efficiencies
  Computer-based work continues by teleworking with > ~80% efficiency for Project Office, design work, firmware, software, etc.
  Lab-based work has ~50 - 100% efficiency due to Covid safe-working. We endeavor to measure and increase these efficiencies
  Deliverables from vendors may be delayed or more expensive. Ongoing concerns (e.g. Si chip foundries).
  International partners also delayed by Covid. LHC and CMS have not yet revised schedules to account for Covid
Increased activity and project durations
Increased labor, M&S, marching army and escalation costs

## Slide 20: Covid-19 costs incurred so far
Covid actual costs (April 2020 – June 2021) | Covid actual costs (April 2020 – June 2021) | Cost
Covid working inefficiencies | Covid working inefficiencies increase the labor costs. These are tracked as EVMS variances (NSF guidance). CAMs/PIs estimate the Covid contributions to these cost variances in the monthly reports. | $636k
Escalation | Covid BCRs that reschedule future work result in increased escalation costs. | $279k
Management/ LoE labor | Covid has increased the project duration by 8.2 months due to non-Covid and Covid effects, which are hard to disentangle. We estimate 5.8 months is due to Covid and 2.5 months is not (based on Phase 1 FPIX delays of 2.1 months / year). The Covid cost impact is given by (Covid delay) × (management / LoE labor burn rate). | $850k
Total |  | $1,765k

## Slide 21: Covid-19 scenario analysis model
To bracket potential future Covid impacts, we use a novel Covid scenario analysis methodology developed at Fermilab
We model lower working efficiencies due to Covid by reducing the effective no. of working hours per day in the P6 calendars
  This stretches activity durations, causing knock-on delays
today
ppp-DocDB-2104

## Slide 22: Covid-19 scenarios – Working efficiencies
Working efficiency factors…
  …are different during lockdowns and afterwards
  …depend on the nature of the work and location-specific restrictions
  …are estimated by CAMs based on actual experience
  …are applied at the lowest level (P6 activities)
Methodology widely discussed with experts, Lab mgmt, agencies.
Used by many projects and well received in external reviews

## Slide 23: Covid-19 potential future cost impacts
Category | Impact modeling
Management / LoE | Labor stays the same but teleworking inefficiency degrades quality of work. Covid delays overall project finish, increasing total Management / LoE labor. ► Cost = (Delay to project finish) × (management/LoE labor burn rate)
Computer-based work | Teleworking inefficiency increases durations and costs by a factor (1/eff. – 1). ► Cost = (Cost of labor that is teleworking) × (1/eff. – 1)
Lab-based work | Safe-working inefficiency increases activity durations by a factor (1/eff. – 1). ► Cost = (Cost of Lab-based labor) × (1/eff. – 1) Plus additional labor to safely close/re-open Labs before/after lockdowns. ► Cost = (No. of days to safely stop/restart Labs) × (labor cost in Labs per day)
Vendor work | Task durations increase by (1/eff. – 1). Cost impact from mgmt. judgment: ► Cost = (Vendor costs in scenario timeframe) × (5%/15% for M/H scenarios)
Escalation | ► Cost = (P6 cost of scenario delayed by Covid) – (P6 cost for working file)
Contingency (=EU + risk) | Assume Covid costs have same % contingency need as the rest of the project. ► Cost = (Covid costs, excl. Mgmt/LoE) × (baseline contingency of 34% on CTG)

## Slide 24: Covid-19: Cost impacts
Cost increase due to Covid is up to $5.3M (High scenario)
 Erratum 25 Aug 2021: this increased by $125k due to a bug fix in the contingency calculation

## Slide 25: Non-Covid-19 + Covid-19: Schedule impacts
Allowing for risks (at 90% CL) and Covid (High scenario): the project (TFPX) will finish late by up to 5.7 months
Non-Covid risks (90% CL)
Non Covid risk delays of up to 11 months
Future Covid delays of up to 5 months
Covid scenarios
Not all deliverables have enough schedule contingency at 90% CL
Non-Covid plus Covid impacts

## Slide 26: Outline
Non-Covid-19 Risk Analysis
  Charge 2c: Risk management process, […] adequacy of the contingency budget and schedule to mitigate future non-COVID risks. […] completeness of the risk register […] non-COVID related threats and opportunities with appropriate probabilities and estimated cost and schedule.
Covid-19 Risk Scenario Analysis
  Charge 3a: […] COVID impact modelling […] of forecast COVID-related cost and schedule impacts. […] realism of assumptions and the credibility of the models used, and […] additional schedule and budget needs. […]
Towards a re-baseline
  Charge 3d: Do the materials […] provide adequate substantiation for re-baselining within the next 6-12 months? If not, what criteria must be satisfied as a precondition for conducting a re-baselining review that would confidently bound estimates for additional schedule and budget […]?

## Slide 27: Towards a re-baseline
The project expects to be ready to re-baseline in Spring 2022, subject to the following two pre-requisites
CERN and CMS schedules have been revisited considering the impacts of Covid, meaning either:
  CERN delays the LHC master schedule, in which case CMS and the US project need to revise their schedules accordingly
  CERN does not delay the LHC master schedule, in which case CMS and the US project need to either accelerate the current scope (at additional cost) or defer (stage) some scope
Covid cost and schedule uncertainties are reduced to an acceptable level, meaning all risks plus the residual risk of the Covid High scenario are covered by the project cost and schedule contingency at ~90% confidence level

## Slide 28: Summary – numbers
Total cost estimate = $ 81,254k
  Estimate at complete = $ 58,908k
    Based on working file (DD = 1 Jun 2021). Includes contributions of Covid to past actual costs
    ($636k) and escalation costs from Covid-induced delays in processed BCRs ($279k)
  Non-Covid-19 contingency (EU + risk at 90% CL) = $ 17,036k
  Liens list items L3 (pending BCRs) + L4 (PM watch list) = $ 880k
    PM watch list includes provision for the current poor exchange rates – to revisit early FY22
  Covid future costs = $ 4,430k
  = Future LoE costs of past Covid delays ($850k) + Covid High scenario ($3,580k)
Total current funding = $ 77,225k
Additional funds needed to deliver within cost at 90% CL = $ 4,029k
Schedule summary (driven by TFPX)
  Non-Covid risk: TFPX has –3.0 months float at 90% CL (0m at 75% CL)
  Covid High scenario: TFPX loses 2.8 more months of float due to Covid
  Non-Covid risks + Covid: TFPX is on time at ~50% CL (will be late half the time)
Additional float needed to deliver on time at 90% CL = 5.7 months

## Slide 29: Summary
Non-Covid-19 Risk Analysis (Charge 2c)
  The project has a mature risk management process, risk register, and risk MC
  Cost contingency adequately covers the non-Covid risks
  Schedule contingency is no longer comfortably sufficient, due to Covid
Covid-19 Risk Scenario Analysis (Charge 3a)
  The project uses the Fermilab-standard Covid analysis methodology
  A range of Covid impacts is bracketed using three scenarios
    Including activity-level inefficiencies, impacts of lockdowns, teleworking, lab safe-working, vendor Covid impacts, escalation and marching army costs
  Covid may potentially increase the project cost by $5.2M (High scenario)
The project expects to be ready to re-baseline in Spring 2022 (Charge 3d), subject to the following two pre-requisites
  CERN and CMS schedules have been revisited, allowing for Covid
  Covid cost and schedule uncertainties are at an acceptable level
The project currently would need an additional ~$4.0M and 5.7 months of float to finish on time and under budget at 90% CL

## Slide 30: Thank you

## Slide 31: Covid-19 scenarios – Schedule impacts
Working efficiencies  longer durations and hence delays
Lockdown #1
Lockdown #2
Lockdown #3
Ex 1: No Covid impacts in scenario analysis
(activity is in the past)
P6 Activities: Legend
Baseline (incl. Low)
Medium scenario
High scenario
Ex.2: No Covid impacts in scenario analysis
(Covid efficiencies covered in baseline)
Ex 3: Medium / High scenarios both delayed by lockdown #2
Ex 4: Medium / High scenario durations increase due to efficiencies
Ex 5: High scenario delayed by lockdown #3 (but not the Medium scenario)
Ex 6: Activities not directly impacted, but are they delayed by predecessors
Examples
Note: the assumed timing of lockdowns has evolved since this graphic was created, but the concepts of the model remain the same