## Slide 1: Beamline Storage and Assembly Needs
Jonathan Lewis
Rich Andrews
4 August 2021

## Slide 2: Primary Beam
Magnets
  Correctors on site – stored in Village Lab 8
  Main dipoles and quads
    Require 30 ton crane
    Agreement with PPD to store at Wideband (PB7)
      Included in MOA
      Lab supposed to upgrade crane controls
Magnet Installation
  Magnet Stands
    ~1100 sq ft indoor storage needed
  Magnet mover
    25’x8’ space needed when not in use
  Probably use D0 MVA

## Slide 3: Primary Beam
Power Supplies
  500 sq ft indoor staging space
  Store cables in AD shipping containers
LCW and Bus
  1200 sq ft close packed
    Clearly larger
  Pipe bundles, components on pallets, stack of copper bus
    Probably store components and bus in shipping containers
    SS pipe bundles might be on hardstand
  All field assembled
Vacuum
  Guess 200 sq ft indoor storage for pipe and pumps
  Field assembled

## Slide 4: Neutrino Beamline: Horns and Target
MI8 and TSIB
  Detailed planning underway
  Excludes target cooling
    Guess that cooling will need few 100 sq ft for major components and shipping container for small parts

## Slide 5: Neutrino Beamline: Target Shield Pile
Bulk Shielding
  Assembly at MAB
  Storage required for raw material and finished blocks
  Try to minimize handling and travel times
  Storage can be outside
    Covered with tarps
    Suggest storing along a road to minimize space
      1.4 acres in a yard or 1700 ft along a road
T-blocks and Hatch Covers need to be out of weather
  Expect to use Shieldblock Storage Building (SBSB)
  Need ~20k sq ft with 30T forklift
  T-block fab either in industry or at MAB
Carriage beams
  OK for outdoor storage
Cooling panels
  1000 sq ft out of weather (SBSB?)

## Slide 6: Target Shield Pile: Fabrication and storage possibilities
MAB
Existing hard stand:
25000 sq ft
SBSB
Extend hard stand?
30000 sq ft
Additional roadsides

## Slide 7
Install here
Fabricate here
Direct route ~2.5 miles
Target Shield Pile: Route to Target Complex

## Slide 8: Neutrino Beamline
Horn Power Supply
  2000 sq ft needed for assembly
    Indoors, crane, forklift access
Stripline
  No info yet. Guess ~2000 sq ft indoors for assembly
Windows
  Probably fits at MI8
Absorber
  500 sq ft storage out of weather
  Use SBSB
Instrumentation
  No info yet. Relatively small need. Probably accommodated within regular departmental space

## Slide 9: Neutrino Beamline
RAW
  Store the tanks, valves, fittings, skid frame hardware, and heat exchangers at A0 south.
  Store the piping indoors -- at SBSB?
  Fittings in Shipping containers at TC?
  Some skids assembled in situ, smaller ones at vendor
Remote Handling
  Work cell, shield doors, morgue
  Steel for doors etc. out of weather
    ~1500 sq ft
    SBSB?
  Sensitive components need climate control
    ~500 sq ft

## Slide 10: System Integration
Controls and Interlocks
  Accommodate within departmental spaces