## Slide 1
Vendor Management
Claire SIMON

## Slide 2: Outline
Procurement plan strategy
Procurement process
Identification of CEA Parts
Contract standard architectures
Follow-up

## Slide 3: Procurement plan strategy
Calls for tenders are placed for the whole components of the series in one batch
(1+ 9 sets of components for pre-production and production)
CEA procurement department standards are used for the calls for tenders and selection of companies.
For each contract, a team is identified for the contracts follow up:
  • Business manager
  • Product manager (technical and performance aspects)
  • Product assurance officer (quality assurance)
  • Experts team
  • Procurement Buyer from CEA procurement department

## Slide 4: Procurement process
Main steps of the procurement process:
Identification of a needed item
Establishment of technical, quality requirements and procurement documents
Evaluation and selection of a Supplier
Monitoring of Supplier performance
Handling of deviations from requirements
Acceptance of items and services

## Slide 5: Identification of the CEA parts
Corresponds to a code for identifying the supplier
Corresponds to the last 7 numbers of CEA drawings
Corresponds to the chronological number of manufacturing (the first digit indicates if it is pre-serie or serie part)
Rules for the identification of the manufactured parts from CEA drawings
Supplier
Drawing reference
Serial number
The identification may be a label or engraving, the method which shall be submitted by the supplier to the CEA and shall be approved by the CEA before application.
The marking place shall be clearly visible and readable
The identification of each component shall be indicated on the manufacturing traveler of the corresponding component.
The components in stock will have an identification code defined by the manufacturer.

## Slide 6: Contract standard architectures
Each contract is supported by two documents:
  The commercial contract, backed by the CEA general purchase clauses,
  The technical specifications of the product, which specify the technical and Quality Assurance requirements. This document also includes the management specifications, which express the monitoring and reporting requirements of the contract.
The Technical specifications are attached to the call for tenders.
The quality requirements are included in the technical specifications
  Manufacturing quality plan including quality control
  Application of ISO 9001;
  Application of manufacturing and materials standards
  Identification and labelling of each component under the CEA responsibility;

## Slide 7: Contract standard architecture
Kickoff Meeting
Holdpoint n°1 : Acceptance of the manufacturing studies (drawings, …) -> MRR
FAT: Factory Acceptance Test on subcontractor site
SAT: Site Acceptance Test on CEA site
MRR: Manufacturing Readiness Review
Manufacturing studies
Holdpoint n°2 : Test of pre-production (SAT)
+ updated manufacturing studies if needed and MRR
Pre-production unit fabrication + FAT
End of the contract after the test of production (SAT)
Production units fabrication + FAT
Contract Signature
between the company and CEA …

## Slide 8: Factory Acceptance Test, Site Acceptance Test
Each component or set of components must be declared Ready For Assembly (RFA) before being sent to the assembly team. The RFA status is reached when the component has successfully passed the Factory Acceptance Test (FAT) and the Site Acceptance test (SAT).
Manufacturing operation
Responsibility
Quality control
Traceability of controls and acceptance
Controls
& Tests
Factory acceptance test
Site acceptance test
Visual inspection
Leak test
Dimensional control
Documentation check
Etc.
Factory acceptance test report
Site acceptance test report
Manufacturer
Manufacturer & CEA
CEA
Ready for assembly
Visual inspection
Leak test
Dimensional control
Etc.
Manufacturer folder (tests & controls reports, etc.)
According to the CEA technical specifications and the validation of the quality plan of the manufacturer
CEA
Manufacturer
CEA
Manufacturer
Manufacturer

## Slide 9: Incoming inspection -SAT
After the delivery of the components at CEA, an incoming inspection is performed and a report is filled.
The incoming inspection report is used as an input data for the Site Acceptance Report

## Slide 10: Follow-up
  For the follow-up of the component production, several tables are filled in by the Business manager / Product manager.
Follow-up table of the part deliveries, with references to acceptance reports, non conformities and changes
Follow-up table for the traceability of the drawings revision, following change requests from suppliers or CEA

## Slide 11: Examples of documents from a vendor
Welding procedure qualification record (WPQR)
Non conformance report from a supplier
Quality control plan

## Slide 12: Thank you for your attention Question ?