## Slide 1
J. Holzbauer on behalf of the PIP-II Transport Team
Monday, August 30, 2021
PIP-II LB650 Transport

## Slide 2: Transport Scope
CEA and STFC-UKRI are transporting production CMs to FNAL, goal is to align these efforts as much as possible
FNAL/STFC-UKRI own first transport demonstration
  pHB650 CM/Transport Frame Design
  Transport System Design (dummy load, procedures, travelers, instrumentation, etc.)
  Execution of escalating validation testing ending in shipment from FNAL to UK and back
CEA is strongly involved, and it is critical that the CEA transport scope will follow the same process including lessons learned
  CEA owns the LB650 CM design, the LB Transport frame design, production, local testing, transport system design.
  FNAL owns actual shipment to US

## Slide 3: Transport Communication
Collaboration and communication is critical for transport success and efficiency
  FNAL SPM: Jeremiah Holzbauer
  STFC-UKRI SPC: Mitchell Kane
  CEA SPC: Robin Cubizolles
All teams are invited to all transport meetings, notes documented and transmitted to all, and lessons learned communicated widely
  It is expected that CEA will be fully informed and involved with pHB650 validation testing to inform the LB650 transport work

## Slide 4: Transportation Planning
LB CM Design
Standard requirements
Transport System Design
Frame Design
Transport Validation
Local Testing validates frame performance
Transport design report
Instrumentation
Dummy Load
pHB650 shipping test validates logistics
Validation testing during production
Procedures and travelers
Lifting Fixture Certification
Transport configuration

## Slide 5: HB/LB650 Transport Documentation Status
For reference:
Doc Name | HB650 | LB650
Transport Spec | ED0012328 | ED0013421
Transport Plan | ED0012594 | ED0013424
Transport ISD | ED0012741 | ED0013425
Transport FMEA | ED0012325 | ED0013422
Transport PtD | ED0012559 | ED0013423
Frame Design Report | ED0012560 | TBD
pCM Transport Analysis | ED0012420 | TBD

## Slide 6: Transport Documentation Plans
Procedures will be developed for significant activities:
  CM reconfiguration from testing to transport (and back)
  Mating of the CM and Frame
  Configuration of the Transport System (CM+Frame) for transport (short range and long range) including mounting to trailer
Acceptance Criteria for Transport System will be developed for start and end of ALL transports (supplementary to CM Acceptance Criteria)
  Visual inspection of frame, paneling, etc.
  Instrumentation configuration/operation
All transports will have detailed travelers referencing updated procedures, include planning and results documents, and specifically note changes since prior transport (design changes, lessons learned)

## Slide 7: Outgoing Transportation Stages
End of Module Production/Validation
Reconfiguration for Transport (Gross Mechanical Rearrangement)
Detailed Preparation for Transportation (checkouts, transport sensors, etc.)
Assembly of the transport system (Module in Frame)
Sensors triggered and Handoff to Transport Vendor

## Slide 8: Warm Outgoing Inspections/Shipping Assembly
Standard acceptance testing after major configuration changes are made:
  Electrical Checkouts of sensors/heaters/etc.
  RF measurement of cavity with adaptor caps in place
  Record beamline vacuum pressure
Installation of any CM-interior sensors
Installation of any dedicated shipping supports
  Spiders to hold piping
  Foam inserts to damp shield motion
  Bumper supports for cold-end couplers
  Blank flanges to ‘close’ insulating vacuum space
  Protective cage around beamline vacuum manifolds
  Will be during validation process

## Slide 9
Backup Slides

## Slide 10: HB650 Configurations
End of production, fully assembled, ready for cold testing
Transport Configuration: Cryogenic top-hat removed, HX removed, piping capped, RF warm-end couplers removed
Beamline Vacuum Manifold

## Slide 11: Transportation Instrumentation
Vibration, GPS, Vacuum, Temperature sensors for each CM transport
On board instrumentation system must be self-contained, including electrical power for the duration
Data captures are specified
Reserved space on transport frame

## Slide 12: Cryomodule Transport Experience
LCLS-II
  1.3GHz & 3.9GHz
  Shipping CM’s to SLAC
    Partnership with JLab
  Onsite transport
PIP-II
  SSR1
    Onsite Transport
  HWR
    Transport from Argonne
    Onsite transport

## Slide 13: PIP-II HB650 Transportation Specification – Section 9
The transportation system shall include instrumentation to actively monitor critical values during the entirety of transport to the extent allowed by external regulations (e.g. GPS devices are often restricted during air transport). These critical values include:
  Beamline vacuum pressure at least 1x/minute
  Temperature of the vacuum vessel at least 1x/minute
  GPS location at least 1x/minute
  Acceleration on the outer transport frame captured at >300 Hz with a range sufficient to capture all shocks experienced (>10g) at a minimum of two wide-spread locations on the outer frame
  Acceleration experienced on the cryomodule vacuum vessel captured at >300 Hz with a range sufficient to capture all shocks experienced (>10g) at a minimum of two wide-spread locations on the vacuum vessel
  Acceleration experienced on critical cryomodule components captured at >300 Hz with a range sufficient to capture all shocks experienced (>10g) at the set of locations defined in the FNAL Cryomodule Shipping Configuration.

## Slide 14: Slam Sticks
All in one device
  Accelerometers
  Data logging
  Configuration
DC MEMS sensor
  Digital Capacitance Micro Electro Mechanical System
  16g range of acceleration measurement
  Frequency response <500Hz
Other sensors built in
  Temperature, pressure, humidity, light
Recently rebranded as enDAQ sensors

## Slide 15: USB Hub Network
Slam Sticks mounted inside CM
  Interface/configure
  Remote start
  External battery power
Data hubs
  Interfacing
  Distribute 5V to sensors
Power hub
  24V to 5V
Modified Tuner Access Port Covers
LCLS-II Modified TAP Port Cover
D-Link USB Data Hub

## Slide 16: Real-time Beamline Vacuum Pressure Monitoring
LCLS-II Beamline Vacuum Pressure Monitoring System

## Slide 17: Successful Transport Vacuum Data
Chart: F1.3-03 Beamline Vacuum Pressure (Torr)
Truck Departs | 5.222e-06
Cryomodule Unloaded | 1.5558e-06

## Slide 18: Unsuccessful Transport Vacuum Data
Chart: F1.3-05 Beamline Vacuum Pressure (Torr)

## Slide 19: Temperature Monitoring
DIGI
  External ambient temperature
  Monitor in real time
Slam Sticks
  External and internal surface temperature
  Cannot monitor in real time

## Slide 20: GPS Tracking
Amcrest GPS Tracker
  Used on all previous LCLS-II and PIP-II transports
  Logs location at minimum 1 minute intervals
  Transmits data over cellular network

## Slide 21: Transport Monitoring Website

## Slide 22: Battery Power
LCLS-II
  Transport lasts 4 days
  24V, 55Ah SLA assembly for vacuum monitoring system
  12V, 55Ah SLA assembly for Slam Stick system
  5V USB Li-Polymer battery packs for external Slam Sticks and GPS
LCLS-II 24V Battery Assembly
5V USB Li-Polymer Battery