## Slide 1: UEC Meeting: Users Meeting Sub-committee Report
By Sophie Middleton
17th Sept 2021

## Slide 2: UM2021: Summary
UM2021 took place 2-6 August 2021
~400 registrants
Talks from all experiments and several additional talks – many early careers speakers
Release forms collected - videos live
Poster prize winners contacted - $ 600 total money  a one off!:
1st : Ben Zhang (Astro)
2nd : Miranda Elkins (neutrino)
3rd: Emrys Peets (LDMX/Dark Matter)
Survey in progress

## Slide 3: UM2021: Publicity
Particles article from Ashley (thanks for this) now live:
  https://news.fnal.gov/fermilab-at-work/from-lab-leadership/
I am writing a Fermilab news article summarizing the meeting
Lesson for next year: We should have a news article before the meeting to further advertise the meeting

## Slide 4: Towards UM2022
It is now time to begin planning for next years meeting
A few things I noted from informal feedback:
  People would prefer a move back to a June time slot
  A in-person component next year would be welcome
We should aim to start planning early with this in mind

## Slide 5: Milestone Plan for UM2022
Oct. 2021
Kick-off sub-committee meeting with all parties invited
Roundtable theme and keynote speakers
Nov. 2021
Second meeting should allow some convergence on names and themes
FNAL would like names by January
Make list of dates
Dec. 2021
Assign deputy to URA forms and start proposal (usually due by Feb)
Decide dates – inform FNAL
Finalize keynote choices and theme

## Slide 6: Milestone Plan for UM2022
Jan. 2022
Finalize the URA proposal
Contact FNAL about keynotes suggestions
Feb. 2022
Submit URA proposa;
EDI talk/SciCom/LRGs – begin to discuss with FNAL team for names
Mar.–Apr. 2022
Things will start to be busy here if we plan in-person June meeting
Book rooms (conference office)
Finalize Timetable
Setup Indico site (communicate with FNAL)

## Slide 7: Milestone Plan for UM2022
April – May 2022
Reach out to spokespeople for speaker nominees (give them at least a month)
June 2022
This will depend on nature of meeting….
Reach out to public for poster nominees (if virtual we need to think about platform)
Open registration (if in person people will need to make travel arrangements)
Publicity – FNAL news, Users Mailing Lists, Posters – communicate with communications office
Festa Italia (amount of work depends if virtual)

## Slide 8: Summary
UM2021 was a great success – thank you Reddy and Ashley for making it so!
I am happy to inherit the chair role and am looking forward to an equally successful UM2022
If you want to assist the planning please reach-out or come to the first meeting when advertised