## Slide 1: AF4 Timeline to Final Snowmass Report
11/11/2021
Mark Palmer

## Slide 2: A Couple Key Points...
AF4 is on focus is on the Machine Concept Whitepapers
  We request that Machine Concept POCs coordinate with the technology whitepaper submitters
    Cross-referencing with “supporting” whitepapers will help us coordinate across the full range of AF submissions
    Will help us identify critical R&D connections to highlight and cross-reference in the AF4 portion of the report
    For reference, the full list of the topical groups is on the next slide
  The timeline for generation of the report envisions significant back and forth with the Machine Concept POCs in order to deliver a robust set of inputs to the HEP community

## Slide 4
 | 2021 |  |  | 2022 |  |  |  |  |  |  |  | 
 | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | Jul | Aug | Sep
Snowmass Timeline |  |  |  |  |  | Whitepaper Due Date: March 15th |  |  |  | Snowmass at Seattle: July 17-26 |  | 
AF4 Timeline |  |  |  |  |  |  |  |  |  |  |  | 
AF4 Restart
Snowmass Restart: Snowmass Day – September 24, 2021
Complete AF4 Report Draft
WP Initial Review
Whitepaper Preparation
Snowmass
Prepare Snowmass Discussion Materials
April 15: Requests for Clarification (if needed)
May 30:
Preliminary Draft Circulated to POCs for Comment
Executive Summary Sent to AF Conveners to Incorporate into Snowmass Meeting Documents
Final AF4 and AF Report Editing
Final Reports Due September 30, 2022
August 31: Request POC Comments
Today’s AF4 Whitepaper Meeting

## Slide 5: Discussion Period