## Slide 1: Neutrino Beamline Horns B and C Preliminary Design Review
Meredith Lee
3 December 2021
Horns B & C Fabrication Plans

## Slide 2: Agenda
Weld Progress and Plans
Welding Machine Expansion
Inner Conductor Nickel Plating Fixture
Outer Conductor Anodizing Fixture
Horn Flipping Fixture Configurations
TSIB Layout and Lift Plan
Fabrication Procedures
Summary

## Slide 3: Weld Progress and Plans – Overview
Jetline CNC circumferential welding machine
Used to weld NuMI horn inner conductors
Welding inner conductor sample parts since August 2021
  Refine weld routines prior to welding LBNF horn inner conductors
  Achieve clean welds with 100% penetration
  X-ray and certify to NAS 1514 Class 1
NuMI horn 2 inner conductor on welding machine
Welding Team: Meredith Lee, Kris Anderson, Austin Fletcher, Jaime Sanchez, and Cory Crowley

## Slide 4: Weld Progress and Plans – Results
Finalized routine parameters for Horn A welds
Clean, 100% penetration welds with crown
Final samples X-rayed and certified to NAS 1514 Class 1
Horn A 3.780” Diameter Sample
Horn A 3.780” Diameter Sample X-ray
Horn A 3.380” Diameter Sample

## Slide 5: Weld Progress and Plans – QA Documentation
Xiris monochrome weld camera installed to capture videos
Positioned to allow monitoring of weld puddle, tungsten, and wire
Videos conducive to troubleshooting and routine modifications

## Slide 6: Weld Progress and Plans – QA Documentation
Dedicated SharePoint page contains information for each sample run:
  Routine used
  Run date
  Comments
  Plots
  Image(s)
  Video

## Slide 7: Weld Progress and Plans – Other Capabilities
Routines for missed underbead
Cosmetic overpass routines using mag arc oscillator
Straightening routines to correct runout
DC Cosmetic Overpass Routine – NuMI sample
DC Cosmetic Overpass – NuMI sample

## Slide 8: Weld Progress and Plans
Horn B and Horn C inner conductors both consist of 2 welds
Requires weld samples for 3 different diameters
Horn B Weld Diameters and Locations
Horn C Weld Diameters and Locations

## Slide 9: Weld Progress and Plans
Program testing and troubleshooting will use a multi-ring sample
  Either forged or machined from Al round stock
Multi-ring sample for each weld diameter
  Rings spaced closely together: initial routine tests and modifications
  Rings spaced moderately apart: near final-stage routine version
  Rings spaced far apart: final routine version
Initial routine version test welds
Routine troubleshooting
Near final version test welds
Final version welds

## Slide 10: Weld Progress and Plans
Sample sets will be used for final welds prior to horn welds
Two sets of samples for each diameter
  Each sample half contains step in and step out
  Allows each sample set to be used for two welds
  Four total sample welds
1. Complete first weld
2. Cut out weld
3. Weld ends together

## Slide 11: Welding Machine Expansion
Floor rails need to be extended to allow tailstock to accommodate Horn B length
New section will be fabricated and attached to existing rail
Upper rail will not need extension
Welding machine rail extension

## Slide 12: Inner Conductor Nickel Plating Fixture
Nickel plating fixture for Horns B & C constrained by process tank size
  Cannot exceed length of Horn B
  Cannot exceed 58” width
Structure will use 6061-T6 Al
  316 SS hardware
Fixture design to occur following Horns B&C Final Design Review
Horn B Nickel Plating Fixture Concept
Swivel shackle

## Slide 13: Outer Conductor Anodizing Fixture
Anodizing fixture nearly identical to NuMI design
  Design for Horns B & C will be scaled version of Horn A design
Clamps and support channels to hold and lift conductor
Cathode tube assembly inside conductor
Processed in chemical baths at 5 angle
Process tank size is 5’ x 5’ x 16’
  Vendor will fabricate tank
Horn A Anodizing Fixture

## Slide 14: Horn B Assembly in Flipping Fixture
Assemble collars, flanges and shafts on the outer conductor
Bolt counterweight to upstream end of outer conductor
  Use plastic washers
Set stand height to Horn C position for Horn B initially
Counterweight
Collars
Shaft
Flange

## Slide 15: Horn B Assembly in Flipping Fixture
Lift outer conductor and position in stands
  Attach shafts to pillow block bearings
Rotate horn to vertical position with counterweight end closest to floor
7.3 in
15.3 ft

## Slide 16: Horn B Assembly in Flipping Fixture
Lower inner conductor and fasten to the outer conductor
30.9 ft
16.2 ft

## Slide 17: Horn B Assembly in Flipping Fixture
Raise stands to Horn B pin position
Support the counterweight using a hydraulic cart and remove
Place connecting flange and ceramic ring together on hydraulic cart and bolt to the horn
2.4 ft

## Slide 18: Horn B Assembly in Flipping Fixture
Rotate horn to horizontal position and remove from fixture

## Slide 19: Horn C Assembly
Assemble collar, flange and shafts on the outer conductor
Bolt counterweight to upstream end outer conductor
Use plastic washers
Set stand height to Horn C position

## Slide 20: Horn C Assembly
Lift outer conductor and position in stands
  Attach shafts to pillow block bearings
Rotate horn to vertical position with counterweight end closest to floor
3.6 ft

## Slide 21: Horn C Assembly
Lower inner conductor and fasten to the outer conductor
22.1 ft

## Slide 22: Horn C Assembly
Remove counterweight, using hydraulic cart to support
Place connecting flange and ceramic ring together on hydraulic cart and bolt to the horn
Rotate horn to horizontal position and remove from fixture

## Slide 23: TSIB Layout and Lift Plan
Lowering of inner conductor into outer conductor confirmed to fit within hook height

## Slide 24: Fabrication Procedures
All procedures and specifications shown at Horn A reviews apply to Horns B and C
Aluminum Welding Specification
Electrical Isolator Assembly
Electroless Nickel Plating Specification
Friction Stir Welding Requirements for Conductor Buswork
HI-POT Voltage Testing Procedure for LBNF Focusing Horns
Instrumentation Line Assembly Procedure
Horn A Spider Supports Installation Procedure
LBNF Horn Assembly in Flipping Fixture
LBNF Horn Inner Conductor Welding
LBNF Horns Traveler
Silver Brush-Plating Procedure for Focusing Horns
Vendor Specification for LBNF Silver Plating
All procedures available at DUNE-doc-21618

## Slide 25: Fabrication Procedures - Traveler
Document containing all QA checks and signoffs for every assembly and fabrication step
Categorized by specific parts, assemblies and processes
References in-depth procedures
One traveler assigned and populated for each horn built

## Slide 26: Summary
Fabrication planning occurred at same time as horn design to ensure feasibility
Welding plan will follow proven process to date
  Greater dependence on multi-ring sample due to high cost of individual sample parts
Anodizing and nickel plating fixtures heavily influenced by NuMI design
  Nickel plating fixture design requires slight differences in order to not exceed tank size
All stages of flipping fixture assembly confirmed to fit in TSIB
Fabrication procedures available for all critical assemblies and processes

## Slide 27: Additional Slides

## Slide 28: Anodizing Fixture in Tank

## Slide 29: Horn B Assembly in Flipping Fixture
Four ground steel plates form 178”x115”x0.75” (14.8’x9.6’) base plate
  Holes to anchor plate to the floor
  Holes to anchor stands to plate
Left stand is fixed
Right stand has 1 position for Horn A and 1 position for B and C
A
A
B,C
B,C