## DEBUNCHER
Because of the low intensity expected after the target, the DCCT is not a useful diagnostic tool for g-2 experimetns. Consequently, this costing estimates reflect ONLY beam requirements for Mu2E experiments. In Mu2E experiments, each 4E12 Booster batch is divided into four 1E12 bunches in the Recycler and sent one at a time to the Debuncher. Each 1e12 bunch is slow extracted out of the Debuncher before the next one is injected. About 3-5% of the 1E12 will be leftover after each slow spill and will be sent to the abort. |  | MNIMUM | MS Cost | Electrical Engineer | Electrical Technician | EE Suport (Drafter & PCB Layout) | FrontEnd Programmer | Mechanical Engineer | ME Support (Drafter / Technician / Machine Shop /Vacuum /Alignment) | Contacted Work / Delivery Times | MOST LIKELY | MS Cost | Electrical Engineer | Electrical Technician | EE Suport (Drafter & PCB Layout) | FrontEnd Programmer | Mechanical Engineer | ME Support (Drafter / Technician / Machine Shop /Vacuum /Alignment) | Contacted Work / Delivery Times | MAXIMUM | MS Cost | Electrical Engineer | Electrical Technician | EE Suport (Drafter & PCB Layout) | FrontEnd Programmer | Mechanical Engineer | ME Support (Drafter / Technician / Machine Shop /Vacuum /Alignment) | Contacted Work / Delivery Times
|  |  | 250 | 56 | 36 | 0 | 10 | 6 | 0 | 0 |  | 1750 | 176 | 162 | 0 | 50 | 12 | 60 | 80 |  | 31050 | 242 | 214 | 80 | 86 | 62 | 240 | 1332
|  |  | Existing system is sufficient; Detector/cables need repair/maintnenace | [8 empty] | Apply firmware and board-level kludges to current DCCT system (Webber design + front end supported by T.Meyers); Detector/cables need repair/maintnenace | [8 empty] | Install entirely new DCCT system (1st installation expected for RR 2012/2013 ANU tasks)
Construct DCCT Detector (ANU-Units) | 0
Review ceramic break and core configuration | 1 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
Review and update detector design | 2 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
Procure ceramic break | 3 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 7000 | 0 | 2 | 0 | 0 | 0 | 0 | 480
Procure transformer cores | 4 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 600 | 0 | 2 | 0 | 0 | 0 | 0 | 240
Procure detector materials, including Mu metal shielding layers | 5 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 2000 | 0 | 2 | 0 | 0 | 0 | 0 | 240
Test ceramic break | 6 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0
Test and wind transformer cores | 7 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0
Assemble detector | 8 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 20 | 60 | 0
Review and update mounting supports | 9 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 0
Procure materials for mounting supports and assembly | 10 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 1000 | 0 | 0 | 0 | 0 | 10 | 60 | 0
Removal of DCCT Detector (Webber-Units) | 0
Remove Detector(need to break vacuum etc.) | 11 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0
Modifications to existing pickup per beam requirements | 12 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Signal and Calibration Cables | 0
Review cable location, types, count, and length | 13 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Procure signal and calibration cables and connectors | 14 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pull cables from tunnel location via penetrations to designated service buildings | 15 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DCCT Electronics (Webber -Units) | 0
Review and update dcct electronics circuit | 16 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Order pcb components for electronics | 17 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 750 | 0 | 4 | 0 | 0 | 0 | 0 | 40 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Order components for chassis, powers supply, etc.. | 18 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Assembly and test electronic/chassis | 19 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Intensity Output Conditioning NIM Board (Webber-Units) | 0
Review and update conditioning board | 20 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 8 | 8 | 0 | 8 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Draw schematic of conditioning module/chassis | 21 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Layout of conditioning module/chassis | 22 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Procure conditioning board | 23 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Order components for conditioning circuit | 24 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 250 | 0 | 4 | 0 | 0 | 0 | 0 | 40 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Order components for chassis, powers supply, etc.. | 25 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Assembly and test conditioning circuit | 26 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DCCT Power Amplifier Chassis (ANU-Units) | 0
Review and update power amplifier circuit | 27 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 2 | 2 | 0 | 2 | 0 | 0 | 0
Draw schematic of power amplifier module/chassis | 28 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 12 | 0 | 20 | 0 | 0 | 0 | 0
Layout of power amplifier module/chassis | 29 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 12 | 0 | 20 | 0 | 0 | 0 | 0
Procure power amplifier board | 30 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 500 | 0 | 2 | 0 | 0 | 0 | 0 | 40
Order components for power amplifier circuit | 31 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 3000 | 0 | 4 | 0 | 0 | 0 | 0 | 40
Order components for chassis, powers supply, etc.. | 32 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 4200 | 0 | 4 | 0 | 0 | 0 | 0 | 72
Assembly and test power amplifier circuit | 33 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0
VME Digitzer and Transition Boards (ANU-Units) | 0
Review and update VME digitizer board and transition board | 34 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 2 | 2 | 0 | 2 | 0 | 0 | 0
Draw schematic of conditioning module/chassis | 35 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 12 | 0 | 20 | 0 | 0 | 0 | 0
Layout of conditioning module/chassis | 36 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 12 | 0 | 20 | 0 | 0 | 0 | 0
Procure transition board and digitizer board (alexei) | 37 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 2000 | 0 | 2 | 0 | 0 | 0 | 0 | 60
Order components for transition and digitizer board | 38 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 1000 | 0 | 4 | 0 | 0 | 0 | 0 | 40
Order components for chassis, powers supply, etc.. | 39 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 500 | 0 | 4 | 0 | 0 | 0 | 0 | 40
Assembly and test digitzer board and transition board | 40 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 20 | 20 | 0 | 20 | 0 | 0 | 0
VME Infrastructure Hardware | 0
Review and update VME digitizer system/software | 41 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | Y | 0 | 2 | 2 | 0 | 2 | 0 | 0 | 0
Order specIfied standard VME hardware (VME64X crates, TCK decoder, crate controllers, etc.) | 42 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 8000 | 0 | 4 | 0 | 0 | 0 | 0 | 40
Order VME commerical digitzer board (ICS-Bl24) | 43 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Order acessories/connectors/etc. for VME digitizer board | 44 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 500 | 0 | 4 | 0 | 0 | 0 | 0 | 40
Test basic operability/resolution/etc.. of VME digitizer | 45 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 20 | 20 | 0 | 20 | 0 | 0 | 0
Layout rack space in service building | 46 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
Install VME crate and electronics in designated service building | 47 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 4 | 12 | 0 | 0 | 0 | 0 | 0
Front End Software Programming | 0
Review and update digital signal processing for intensity measurements, baseline/droop corrections, etc.. | 48 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | Y | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0
Review and update VME Interface code to Control System | 49 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0
Review and update control system devices/GUI/Page | 50 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0
Test digital signal processing with digitized, conditioned CT signals | 51 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 20 | 20 | 0 | 20 | 0 | 0 | 0 | Y | 0 | 20 | 20 | 0 | 20 | 0 | 0 | 0
Installation & Commissioning | 0
Vacuum/Electrical/Alignment testing of tunnel installation | 52 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 500 | 0 | 0 | 0 | 0 | 6 | 60 | 0 | Y | 500 | 0 | 0 | 0 | 0 | 6 | 60 | 0
Review tunnel installation: terminate cables/connections/electrical isolation/pipe conductiviity etc… | 53 | Y | 0 | 6 | 6 | 0 | 0 | 6 | 0 | 0 | Y | 0 | 6 | 6 | 0 | 0 | 6 | 0 | 0 | Y | 0 | 6 | 6 | 0 | 0 | 6 | 0 | 0
System repair/maintenance (detector, connector, adapter, filters, ceramic break, mounting stands, electronics) | 54 | Y | 250 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | Y | 250 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | Y | 250 | 20 | 20 | 0 | 0 | 0 | 0 | 0
Calibrate/test intensity monitor system to verIfy operability and control system readiness | 55 | Y | 0 | 10 | 10 | 0 | 10 | 0 | 0 | 0 | Y | 0 | 10 | 10 | 0 | 10 | 0 | 0 | 0 | Y | 0 | 10 | 10 | 0 | 10 | 0 | 0 | 0
Finalize Intensity Monitoring System Documentation | 56 | Y | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0

## ACCUMULATOR
No work is needed to be done for either g-2 or Mu2E, because beam path does not include Accumulator. If decommissioned, pickup/electronics can be removed and used as spares. |  | MNIMUM | MS Cost | Electrical Engineer | Electrical Technician | EE Suport (Drafter & PCB Layout) | FrontEnd Programmer | Mechanical Engineer | ME Support (Drafter / Technician / Machine Shop /Vacuum /Alignment) | Contacted Work / Delivery Times | MOST LIKELY | MS Cost | Electrical Engineer | Electrical Technician | EE Suport (Drafter & PCB Layout) | FrontEnd Programmer | Mechanical Engineer | ME Support (Drafter / Technician / Machine Shop /Vacuum /Alignment) | Contacted Work / Delivery Times |  | MS Cost | Electrical Engineer | Electrical Technician | EE Suport (Drafter & PCB Layout) | FrontEnd Programmer | Mechanical Engineer | ME Support (Drafter / Technician / Machine Shop /Vacuum /Alignment) | Contacted Work / Delivery Times
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construct DCCT Detector (ANU-Units) | 0
Review ceramic break and core configuration | 1 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Review and update detector design | 2 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Procure ceramic break | 3 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Procure transformer cores | 4 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Procure detector materials, including Mu metal shielding layers | 5 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Test ceramic break | 6 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Test and wind transformer cores | 7 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Assemble detector | 8 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Review and update mounting supports | 9 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Procure materials for mounting supports and assembly | 10 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Removal of DCCT Detector (Webber-Units) | 0
Remove Detector(need to break vacuum etc.) | 11 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Modifications to existing pickup per beam requirements | 12 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Signal and Calibration Cables | 0
Review cable location, types, count, and length | 13 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Procure signal and calibration cables and connectors | 14 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pull cables from tunnel location via penetrations to designated service buildings | 15 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DCCT Electronics (Webber -Units) | 0
Review and update dcct electronics circuit | 16 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Order pcb components for electronics | 17 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Order components for chassis, powers supply, etc.. | 18 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Assembly and test electronic/chassis | 19 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Intensity Output Conditioning NIM Board (Webber-Units) | 0
Review and update conditioning board | 20 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Draw schematic of conditioning module/chassis | 21 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Layout of conditioning module/chassis | 22 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Procure conditioning board | 23 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Order components for conditioning circuit | 24 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Order components for chassis, powers supply, etc.. | 25 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Assembly and test conditioning circuit | 26 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DCCT Power Amplifier Chassis (ANU-Units) | 0
Review and update power amplifier circuit | 27 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Draw schematic of power amplifier module/chassis | 28 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Layout of power amplifier module/chassis | 29 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Procure power amplifier board | 30 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Order components for power amplifier circuit | 31 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Order components for chassis, powers supply, etc.. | 32 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Assembly and test power amplifier circuit | 33 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
VME Digitzer and Transition Boards (ANU-Units) | 0
Review and update VME digitizer board and transition board | 34 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Draw schematic of conditioning module/chassis | 35 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Layout of conditioning module/chassis | 36 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Procure transition board and digitizer board (alexei) | 37 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Order components for transition and digitizer board | 38 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Order components for chassis, powers supply, etc.. | 39 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Assembly and test digitzer board and transition board | 40 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
VME Infrastructure Hardware | 0
Review and update VME digitizer system/software | 41 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Order specIfied standard VME hardware (VME64X crates, TCK decoder, crate controllers, etc.) | 42 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Order VME commerical digitzer board (ICS-Bl24) | 43 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Order acessories/connectors/etc. for VME digitizer board | 44 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Test basic operability/resolution/etc.. of VME digitizer | 45 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Layout rack space in service building | 46 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Install VME crate and electronics in designated service building | 47 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Front End Software Programming | 0
Review and update digital signal processing for intensity measurements, baseline/droop corrections, etc.. | 48 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Review and update VME Interface code to Control System | 49 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Review and update control system devices/GUI/Page | 50 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Test digital signal processing with digitized, conditioned CT signals | 51 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Installation & Commissioning | 0
Vacuum/Electrical/Alignment testing of tunnel installation | 52 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Review tunnel installation: terminate cables/connections/electrical isolation/pipe conductiviity etc… | 53 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
System repair/maintenance (detector, connector, adapter, filters, ceramic break, mounting stands, electronics) | 54 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Calibrate/test intensity monitor system to verIfy operability and control system readiness | 55 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Finalize Intensity Monitoring System Documentation | 56 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF!

## COSTING REFERENCE
Task# | Task Name / Description | Comments | Duration (Days) | Total ManHours | MS Cost | Electrical Engineer | Electrical Technician | EE Suport (Drafter & PCB Layout) | FrontEnd Programmer | Mechanical Engineer | ME Support (Drafter / Technician / Machine Shop /Vacuum /Alignment) | Contacted Work / Delivery Times
0 | Construct DCCT Detector (ANU-Units) |  |  | 0
1 | Review ceramic break and core configuration | Using existing design | 1 | 4 |  | 2 | 2
2 | Review and update detector design | Using existing design | 1 | 4 |  | 2 | 2
3 | Procure ceramic break | Using existing design | 84 | 482 | 7000 |  | 2 |  |  |  |  | 480
4 | Procure transformer cores |  | 72 | 242 | 600 |  | 2 |  |  |  |  | 240
5 | Procure detector materials, including Mu metal shielding layers |  | 72 | 242 | 2000 |  | 2 |  |  |  |  | 240
6 | Test ceramic break |  | 5 | 40 |  | 20 | 20
7 | Test and wind transformer cores |  | 5 | 40 |  | 20 | 20
8 | Assemble detector |  | 15 | 80 | [5 empty] | 20 | 60
9 | Review and update mounting supports |  | 5 | 40 | [5 empty] | 20 | 20
10 | Procure materials for mounting supports and assembly |  | 10 | 70 | 1000 |  |  |  |  | 10 | 60
0 | Removal of DCCT Detector (Webber-Units) |  |  | 0
11 | Remove Detector(need to break vacuum etc.) |  | 3.5 | 40 | [6 empty] | 40
12 | Modifications to existing pickup per beam requirements |  | 7 | 80 | 500 | 40 | 40
| Signal and Calibration Cables |  |  | 0
13 | Review cable location, types, count, and length | Not expecting any change to location/cables | 1 | 4 |  | 2 | 2
14 | Procure signal and calibration cables and connectors |  | 14 | 82 | 2000 |  | 2 |  |  |  |  | 80
15 | Pull cables from tunnel location via penetrations to designated service buildings | Estimated $100/hr | 3 | 16 | 1600 | [6 empty] | 16
| DCCT Electronics (Webber -Units) |  |  | 0
16 | Review and update dcct electronics circuit | Using existing design | 1 | 16 |  | 8 | 8
17 | Order pcb components for electronics |  | 7 | 44 | 750 |  | 4 |  |  |  |  | 40
18 | Order components for chassis, powers supply, etc.. |  | 7 | 44 | 750 |  | 4 |  |  |  |  | 40
19 | Assembly and test electronic/chassis |  | 7 | 80 |  | 40 | 40
| Intensity Output Conditioning NIM Board (Webber-Units) |  |  | 0
20 | Review and update conditioning board | Using existing design | 1 | 24 |  | 8 | 8 |  | 8
21 | Draw schematic of conditioning module/chassis |  | 5 | 32 |  | 12 |  | 20
22 | Layout of conditioning module/chassis |  | 5 | 32 |  | 12 |  | 20
23 | Procure conditioning board |  | 7 | 40 | 500 | [6 empty] | 40
24 | Order components for conditioning circuit |  | 7 | 44 | 250 |  | 4 |  |  |  |  | 40
25 | Order components for chassis, powers supply, etc.. |  | 7 | 44 | 500 |  | 4 |  |  |  |  | 40
26 | Assembly and test conditioning circuit |  | 7 | 80 |  | 40 | 40
| DCCT Power Amplifier Chassis (ANU-Units) |  |  | 0
27 | Review and update power amplifier circuit | Using existing design | 1 | 6 |  | 2 | 2 |  | 2
28 | Draw schematic of power amplifier module/chassis |  | 5 | 32 |  | 12 |  | 20
29 | Layout of power amplifier module/chassis |  | 5 | 32 |  | 12 |  | 20
30 | Procure power amplifier board |  | 7 | 42 | 500 |  | 2 |  |  |  |  | 40
31 | Order components for power amplifier circuit |  | 7 | 44 | 3000 |  | 4 |  |  |  |  | 40
32 | Order components for chassis, powers supply, etc.. |  | 9 | 76 | 4200 |  | 4 |  |  |  |  | 72
33 | Assembly and test power amplifier circuit |  | 7 | 40 |  | 20 | 20
| VME Digitzer and Transition Boards (ANU-Units) |  |  | 0
34 | Review and update VME digitizer board and transition board | Using existing design | 1 | 6 |  | 2 | 2 |  | 2
35 | Draw schematic of conditioning module/chassis |  | 5 | 32 |  | 12 |  | 20
36 | Layout of conditioning module/chassis |  | 5 | 32 |  | 12 |  | 20
37 | Procure transition board and digitizer board (alexei) |  | 7 | 62 | 2000 |  | 2 |  |  |  |  | 60
38 | Order components for transition and digitizer board |  | 7 | 44 | 1000 |  | 4 |  |  |  |  | 40
39 | Order components for chassis, powers supply, etc.. |  | 7 | 44 | 500 |  | 4 |  |  |  |  | 40
40 | Assembly and test digitzer board and transition board |  | 7 | 60 |  | 20 | 20 |  | 20
| VME Infrastructure Hardware |  |  | 0
41 | Review and update VME digitizer system/software | Using existing design | 1 | 6 |  | 2 | 2 |  | 2
42 | Order specIfied standard VME hardware (VME64X crates, TCK decoder, crate controllers, etc.) |  | 7 | 44 | 8000 |  | 4 |  |  |  |  | 40
43 | Order VME commerical digitzer board (ICS-Bl24) |  | 7 | 64 | 8000 |  | 4 |  |  |  |  | 60
44 | Order acessories/connectors/etc. for VME digitizer board |  | 7 | 44 | 500 |  | 4 |  |  |  |  | 40
45 | Test basic operability/resolution/etc.. of VME digitizer |  | 7 | 60 |  | 20 | 20 |  | 20
46 | Layout rack space in service building |  | 1 | 4 |  | 2 | 2
47 | Install VME crate and electronics in designated service building |  | 3.5 | 16 |  | 4 | 12
| Front End Software Programming |  |  | 0
48 | Review and update digital signal processing for intensity measurements, baseline/droop corrections, etc.. | Using existing design | 1 | 4 |  | 2 |  |  | 2
49 | Review and update VME Interface code to Control System | Using existing design | 1 | 4 |  |  |  |  | 4
50 | Review and update control system devices/GUI/Page | Using existing design | 1 | 4 |  |  |  |  | 4
51 | Test digital signal processing with digitized, conditioned CT signals |  | 7 | 60 |  | 20 | 20 |  | 20
| Installation & Commissioning |  |  | 0
52 | Vacuum/Electrical/Alignment testing of tunnel installation |  | 21 | 66 | 500 |  |  |  |  | 6 | 60
53 | Review tunnel installation: terminate cables/connections/electrical isolation/pipe conductiviity etc… |  | 3.5 | 18 |  | 6 | 6 |  |  | 6
54 | System repair/maintenance (detector, connector, adapter, filters, ceramic break, mounting stands, electronics) |  | 7 | 40 | 250 | 20 | 20
55 | Calibrate/test intensity monitor system to verIfy operability and control system readiness |  | 7 | 30 |  | 10 | 10 |  | 10
56 | Finalize Intensity Monitoring System Documentation |  | 7 | 20 |  | 20
0

## Constants
Calibration Pulses |  |  |  | Cable Type | v/c
Equivalent | Pulse Width | Frequency Setting | LDF5-50A | 7/8" Heliax | 0.89
1NuMI Batch | 1.6e-06 | 312500 | LDF4-50A | 1/2" Heliax | 0.88
2NuMI Batch | 3.2e-06 | 156250 | LDF2-50 | 3/8" Heliax | 0.88
3NuMI Batch | 4.8e-06 | 104166.6667 | FSJ4-50B | 1/2" Superflex | 0.81
4NuMI Batch | 6.4e-06 | 78125 | FSJ1-50 | 1/4" Superflex | 0.78
5NuMI Batch | 8e-06 | 62500 | LDF4-50A | 1/2" Heliax | 0.88
6NuMI Batch | 9.6e-06 | 52083.3333 | LDF2-50 | 3/8" Heliax | 0.88
7NuMI Batch | 1.12e-05 | 44642.8571 | FSJ4-50B | 1/2" Superflex | 0.81
8NuMI Batch | 1.28e-05 | 39062.5 | FSJ1-50 | 1/4" Superflex | 0.78
1 | 1e-06 | 500000 |  | RG213 | 0.67
2 | 2e-06 | 250000 |  | RG58 | 0.67
3 | 3e-06 | 166666.6667 |  | RG174 | 0.67
4 | 4e-06 | 125000 |  | RG108 | 0.66
5 | 5e-06 | 100000 |  | TWC-78-2 | 0.66
6 | 6e-06 | 83333.3333
7 | 7e-06 | 71428.5714 |  | e_Charge | 1.6022e-19
8 | 8e-06 | 62500 |  | R,wvf gen | 50.54
9 | 9e-06 | 55555.5556
10 | 1e-05 | 50000 |  | Speed of Light
|  |  |  | c (m/s) | 299792458
|  |  |  | c(ft/s) | 983571056.43
|  |  |  | v/c @ 4Gev | 0.71305
|  |  |  | v/c @ 8Gev | 0.99447
|  |  |  | v/c @ 12Gev | 0.99997