## SUMMARY
[6 empty] | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7
|  | Description | M&S Cost | row | column | M&S Cost | Electrical Engineer | Electrical Technician | Front End Programmer | Machine Shop | ME Support (Drafter, Mech. Enginer, Mech. Tech) | Vauccm/Alignment Crews | EE Support (Schematic, PCB Drafter, Layout)
MINIMAL |  | Use existing toroids and insulators, and do not add a second toroid to the AP3 line. Except at new location for TOR109, all tunnel installations only have general maintenance performed on them. VME crate, controllers and timing cards will be repurposed from other locations. | 12000 | 26 | 12 | 12000 | 1538 | 1734 | 2080 | 60 | 130 | 60 | 240
MOST LIKELY | (1) | Use existing toroids and insulators, and do not add a second toroid to the AP3 line. Except at new location for TOR109, all tunnel installations only have general maintenance performed on them. VME crate, controllers and timing cards will be repurposed from other locations. New transition board for analog conditioning will be designed and procured. | 13800 | 26 | 12 | 13800 | 1538 | 1758 | 2080 | 60 | 130 | 60 | 320
| (2) | Use existing toroids and insulators. TOR109 will be moved. Install spare toroid and insulator from AP2 line to add a second toroid to the AP3 line. Only 2 tunnel installations will be replaced; all others only have general maintenance performed on them. VME crate, controllers and timing cards will be repurposed from other locations. New transition board for analog conditioning will be designed and procured. Note spare toroids are model 7737 and have ~11" ID. Also, datashee specifies only&MHz BWl; if accurate this may not be enough. | 21150 | 26 | 12 | 21150 | 1790 | 2070 | 2340 | 180 | 260 | 120 | 360
| (3) | Use existing toroids and insulators. TOR109 will be moved. Install newly purchased toroid (3100) and insulator to add a second toroid to the AP3 line. Only 2 tunnel installations will be replaced; all others only have general maintenance performed on them. VME crate, controllers and timing cards will be repurposed from other locations. New transition board for analog conditioning will be designed and procured. Note 3100 models have 3.5" ID. Also, although datasheet specifies only 7MHZ BW, almost all received CT have been measured to have 10-20MHz corner; benctest shows that it can detect 120ns bunch. | 26200 | 26 | 12 | 26200 | 1804 | 2073 | 2340 | 240 | 260 | 120 | 360
MAXIMUM |  | Use existing toroids and insulators. Install newly purchased toroid (3100) and insulator to add a second toroid to the AP3 line. All tunnel installation will be reviewed and modifited to follow standardized system model. New VME crate, controllers and timing cards will be purchased. New transition board for analog conditioning will be designed and procured. | 49650 | 26 | 12 | 49650 | 1820 | 2205 | 2340 | 540 | 400 | 120 | 360
** Costing assumes that the pre-target beam transport path is identical to g-2.Mu2E estimates assumes all work on the pretarget transport was done for g-2, except for moving Mu2E. To simplify Mu2E estimates, I assumed g-2 work included (1) installation of a 2nd toroid in the P2line, (2) procurement of a signal conditional board for all pretarget toroids, and (3) installation of VME electronics for all pre-target toroids. I am aware these issues have not yet been decided.

## MINIMUM
TOROID | LOCATION | NOTES | Task Descriptions ( excludes routine maintenance) | [7 empty] | M&S Costs | LABOR HOURS
|  |  | New Location/Install | New CT | New Ceramic Break | New RC | New Stand/Supports | New Cables | New ConditioningBrd | NEW VME FrontEnd |  | Electrical Engineer | Electrical Technician | Front End Programmer | Machine Shop | ME Support (Drafter, Mech. Enginer, Mech. Tech) | Vauccm/Alignment Crews | EE Support (Schematic, PCB Drafter, Layout)
P1 LINE (PreTarget Transport Line)
I:TOR914 (3100) | MI60N | Mu2E has same transport path as g-2; work was previously done for g-2. | n | n | n | n | n | n |  |  | 150 | 158 | 178 | 240 | 0 | 0 | 0 | 40
I:TOR902 (3100) | MI62 | Mu2E has same transport path as g-2; work was previously done for g-2. | n | n | n | n | n | n |  |  | 150 | 158 | 178 | 240 | 0 | 0 | 0 | 40
P2 LINE (PreTarget Transport Line)
I:TORF16 (3100) | F1 | Mu2E has same transport path as g-2; work was previously done for g-2. | n | n | n | n | n | n |  |  | 150 | 158 | 178 | 240 | 0 | 0 | 0 | 40
P2 Toroid #2 |  | This assumes that a 2nd toroid was previously installed for g-2. | n | n | n | n | n | n |  |  | 150 | 158 | 178 | 240 | 0 | 0 | 0 | 40
AP1 LINE (PreTarget Transport Line)
M:TR105B (3100) | AP0 | Mu2E has same transport path as g-2; work was previously done for g-2. | n | n | n | n | n | n |  |  | 150 | 158 | 178 | 240 | 0 | 0 | 0 | 40
M:TOR109 (3100) |  | This assumes the current toroid will NEED to be moved to a new location. For Mu2E, the beam will be bent to the AP3 line at EB6. At its current location, it would only see beam for g-2, NOT Mu2E. | y | n | n | n | y | y |  |  | 6150 | 248 | 288 | 260 | 60 | 130 | 60 | 40 | 1
AP3 LINE (PostTarget Transport Line)
D:TOR910 (3100) | AP30 | This assumes the current toroid will NOT need to be moved. For Mu2E, there is no target at AP0 so beam should be the same as p1->p2->ap1 (1e12 P+, 120nsec) | n | n | n | n | n | n | n | n | 2550 | 250 | 278 | 310 | 0 | 0 | 0 | 0
AP3 Toroid #2 |  | NO 2nd toroid in AP3 beam line | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AP2 LINE (Abort Line)
D:TOR704 (7737) | AP0 | WILL NOT BE MU2E BeamPath | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D:724TOR (7737) | AP50 | WILL NOT BE MU2E BeamPath | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D:TOR733 (3100) |  | This assumes the current toroid will NOT need to be moved; the abort line will be as far as the 726 location. For Mu2E, 3-5% of primary protons will be aborted after slow extraction (3-5e10, 120nsec). | n | n | n | n | n | n | n | n | 2550 | 250 | 278 | 310 | 0 | 0 | 0 | 0
D/A LINE
D:806TOR (7737) | AP10 | WILL NOT BE MU2E BeamPath | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D/A Toroid #2 |  | WILL NOT BE MU2E BeamPath | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Extraction Line to Experimental Hall
Toroid#1 | New Building | Toroid-based beam intensity NOT recommeded, because of low intensity p+ during slow extraction (1e12 every 56msec). | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Toroid#2 |  | Toroid-based beam intensity NOT recommeded, because of low intensity p+ during slow extraction (1e12 every 56msec). | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 12000 | 1538 | 1734 | 2080 | 60 | 130 | 60 | 240
Note on C1: cadornaa: as of adjusted Mu2E scope (12/2011- https://indico.fnal.gov/conferenceDisplay.py?confId=5068)'
Note on I2: cadornaa: cabling cost based on $2/Ft for 600ft per cable pull
Note on J2: cadornaa: previously installed for all pretarget toroids
Note on J11: cadornaa: minicircuits filters; pomoana-box conditioning
Note on J13: cadornaa: minicircuits filters; pomoana-box conditioning
Note on J18: cadornaa: minicircuits filters; pomoana-box conditioning
Note on K11: cadornaa: shares front end with TR105B
Note on K13: cadornaa: repurpose crate/control cards from lab; use Alexei's 125MHZ digitizer
Note on K18: cadornaa: repurpose crate/control cards from lab; use Alexei's 125MHZ digitizer

## MOST_LIKELY
TOROID | LOCATION | NOTES | Task Descriptions ( excludes routine maintenance) | [7 empty] | M&S Costs | LABOR HOURS
|  |  | New Location/Install | New CT | New Ceramic Break | New RC | New Stand/Supports | New Cables | New ConditioningBrd | NEW VME FrontEnd |  | Electrical Engineer | Electrical Technician | Front End Programmer | Machine Shop | ME Support (Drafter, Mech. Enginer, Mech. Tech) | Vauccm/Alignment Crews | EE Support (Schematic, PCB Drafter, Layout)
P1 LINE (PreTarget Transport Line)
I:TOR914 (3100) | MI60N | Mu2E has same transport path as g-2; work was previously done for g-2. | n | n | n | n | n | n |  |  | 150 | 158 | 178 | 240 | 0 | 0 | 0 | 40
I:TOR902 (3100) | MI62 | Mu2E has same transport path as g-2; work was previously done for g-2. | n | n | n | n | n | n |  |  | 150 | 158 | 178 | 240 | 0 | 0 | 0 | 40
P2 LINE (PreTarget Transport Line)
I:TORF16 (3100) | F1 | Mu2E has same transport path as g-2; work was previously done for g-2. | n | n | n | n | n | n |  |  | 150 | 158 | 178 | 240 | 0 | 0 | 0 | 40
P2 Toroid #2 |  | This assumes that a 2nd toroid was previously installed for g-2. | n | n | n | n | n | n |  |  | 150 | 158 | 178 | 240 | 0 | 0 | 0 | 40
AP1 LINE (PreTarget Transport Line)
M:TR105B (3100) | AP0 | Mu2E has same transport path as g-2; work was previously done for g-2. | n | n | n | n | n | n |  |  | 150 | 158 | 178 | 240 | 0 | 0 | 0 | 40
M:TOR109 (3100) |  | This assumes the current toroid will NEED to be moved to a new location. For Mu2E, the beam will be bent to the AP3 line at EB6. At its current location, it would only see beam for g-2, NOT Mu2E. | y | n | n | n | y | y |  |  | 6150 | 248 | 288 | 260 | 60 | 130 | 60 | 40 | 1
AP3 LINE (PostTarget Transport Line)
D:TOR910 (3100) | AP30 | This assumes the current toroid will NOT need to be moved. For Mu2E, there is no target at AP0 so beam should be the same as p1->p2->ap1 (1e12 P+, 120nsec) | n | n | n | n | n | n | y | n | 3450 | 250 | 290 | 310 | 0 | 0 | 0 | 40
AP3 Toroid #2 |  | NO 2nd toroid in AP3 beam line | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AP2 LINE (Abort Line)
D:TOR704 (7737) | AP0 | WILL NOT BE MU2E BeamPath | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D:724TOR (7737) | AP50 | WILL NOT BE MU2E BeamPath | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D:TOR733 (3100) |  | This assumes the current toroid will NOT need to be moved; the abort line will be as far as the 726 location. For Mu2E, 3-5% of primary protons will be aborted after slow extraction (3-5e10, 120nsec). | n | n | n | n | n | n | y | n | 3450 | 250 | 290 | 310 | 0 | 0 | 0 | 40
D/A LINE
D:806TOR (7737) | AP10 | WILL NOT BE MU2E BeamPath | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D/A Toroid #2 |  | WILL NOT BE MU2E BeamPath | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Extraction Line to Experimental Hall
Toroid#1 | New Building | Toroid-based beam intensity NOT recommeded, because of low intensity p+ during slow extraction (1e12 every 56msec). | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Toroid#2 |  | Toroid-based beam intensity NOT recommeded, because of low intensity p+ during slow extraction (1e12 every 56msec). | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 13800 | 1538 | 1758 | 2080 | 60 | 130 | 60 | 320
Note on C1: cadornaa: as of adjusted Mu2E scope (12/2011- https://indico.fnal.gov/conferenceDisplay.py?confId=5068)'
Note on I2: cadornaa: cabling cost based on $2/Ft for 600ft per cable pull
Note on J2: cadornaa: previously installed for all pretarget toroids
Note on K11: cadornaa: shares front end with TR105B
Note on K13: cadornaa: repurpose crate/control cards from lab; use Alexei's 125MHZ digitizer
Note on K14: cadornaa: shares front end with TR105B
Note on K18: cadornaa: repurpose crate/control cards from lab; use Alexei's 125MHZ digitizer

## MOST_LIKELY (2)
TOROID | LOCATION | NOTES | Task Descriptions ( excludes routine maintenance) | [7 empty] | M&S Costs | LABOR HOURS
|  |  | New Location/Install | New CT | New Ceramic Break | New RC | New Stand/Supports | New Cables | New ConditioningBrd | NEW VME FrontEnd |  | Electrical Engineer | Electrical Technician | Front End Programmer | Machine Shop | ME Support (Drafter, Mech. Enginer, Mech. Tech) | Vauccm/Alignment Crews | EE Support (Schematic, PCB Drafter, Layout)
P1 LINE (PreTarget Transport Line)
I:TOR914 (3100) | MI60N | Mu2E has same transport path as g-2; work was previously done for g-2. | n | n | n | n | n | n |  |  | 150 | 158 | 178 | 240 | 0 | 0 | 0 | 40
I:TOR902 (3100) | MI62 | Mu2E has same transport path as g-2; work was previously done for g-2. | n | n | n | n | n | n |  |  | 150 | 158 | 178 | 240 | 0 | 0 | 0 | 40
P2 LINE (PreTarget Transport Line)
I:TORF16 (3100) | F1 | Mu2E has same transport path as g-2; work was previously done for g-2. | n | n | n | n | n | n |  |  | 150 | 158 | 178 | 240 | 0 | 0 | 0 | 40
P2 Toroid #2 |  | This assumes that a 2nd toroid was previously installed for g-2. | n | n | n | n | n | n |  |  | 150 | 158 | 178 | 240 | 0 | 0 | 0 | 40
AP1 LINE (PreTarget Transport Line)
M:TR105B (3100) | AP0 | Mu2E has same transport path as g-2; work was previously done for g-2. | n | n | n | n | n | n |  |  | 150 | 158 | 178 | 240 | 0 | 0 | 0 | 40
M:TOR109 (3100) |  | This assumes the current toroid will NEED to be moved to a new location. For Mu2E, the beam will be bent to the AP3 line at EB6. At its current location, it would only see beam for g-2, NOT Mu2E. | y | n | n | n | y | y |  |  | 6150 | 248 | 288 | 260 | 60 | 130 | 60 | 40 | 1
AP3 LINE (PostTarget Transport Line)
D:TOR910 (3100) | AP30 | This assumes the current toroid will NOT need to be moved. For Mu2E, there is no target at AP0 so beam should be the same as p1->p2->ap1 (1e12 P+, 120nsec) | n | n | n | n | n | n | y | n | 3450 | 250 | 290 | 310 | 0 | 0 | 0 | 40
AP3 Toroid #2 |  | New installation reusing spare ceramic break and CT (7737) from AP2. | y | n | n | y | y | y | y |  | 7350 | 252 | 312 | 260 | 120 | 130 | 60 | 40
AP2 LINE (Abort Line)
D:TOR704 (7737) | AP0 | WILL NOT BE MU2E BeamPath | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D:724TOR (7737) | AP50 | WILL NOT BE MU2E BeamPath | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D:TOR733 (3100) |  | This assumes the current toroid will NOT need to be moved; the abort line will be as far as the 726 location. For Mu2E, 3-5% of primary protons will be aborted after slow extraction (3-5e10, 120nsec). | n | n | n | n | n | n | y | n | 3450 | 250 | 290 | 310 | 0 | 0 | 0 | 40
D/A LINE
D:806TOR (7737) | AP10 | WILL NOT BE MU2E BeamPath | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D/A Toroid #2 |  | WILL NOT BE MU2E BeamPath | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Extraction Line to Experimental Hall
Toroid#1 | New Building | Toroid-based beam intensity NOT recommeded, because of low intensity p+ during slow extraction (1e12 every 56msec). | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Toroid#2 |  | Toroid-based beam intensity NOT recommeded, because of low intensity p+ during slow extraction (1e12 every 56msec). | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 21150 | 1790 | 2070 | 2340 | 180 | 260 | 120 | 360
Note on C1: cadornaa: as of adjusted Mu2E scope (12/2011- https://indico.fnal.gov/conferenceDisplay.py?confId=5068)'
Note on I2: cadornaa: cabling cost based on $2/Ft for 600ft per cable pull
Note on J2: cadornaa: previously installed for all pretarget toroids
Note on K11: cadornaa: shares front end with TR105B
Note on K13: cadornaa: repurpose crate/control cards from lab; use Alexei's 125MHZ digitizer
Note on K14: cadornaa: shares front end with TOR910
Note on K18: cadornaa: repurpose crate/control cards from lab; use Alexei's 125MHZ digitizer

## MOST_LIKELY (3)
TOROID | LOCATION | NOTES | Task Descriptions ( excludes routine maintenance) | [7 empty] | M&S Costs | LABOR HOURS
|  |  | New Location/Install | New CT | New Ceramic Break | New RC | New Stand/Supports | New Cables | New ConditioningBrd | NEW VME FrontEnd |  | Electrical Engineer | Electrical Technician | Front End Programmer | Machine Shop | ME Support (Drafter, Mech. Enginer, Mech. Tech) | Vauccm/Alignment Crews | EE Support (Schematic, PCB Drafter, Layout)
P1 LINE (PreTarget Transport Line)
I:TOR914 (3100) | MI60N | Mu2E has same transport path as g-2; work was previously done for g-2. | n | n | n | n | n | n |  |  | 150 | 158 | 178 | 240 | 0 | 0 | 0 | 40
I:TOR902 (3100) | MI62 | Mu2E has same transport path as g-2; work was previously done for g-2. | n | n | n | n | n | n |  |  | 150 | 158 | 178 | 240 | 0 | 0 | 0 | 40
P2 LINE (PreTarget Transport Line)
I:TORF16 (3100) | F1 | Mu2E has same transport path as g-2; work was previously done for g-2. | n | n | n | n | n | n |  |  | 150 | 158 | 178 | 240 | 0 | 0 | 0 | 40
P2 Toroid #2 |  | This assumes that a 2nd toroid was previously installed for g-2. | n | n | n | n | n | n |  |  | 150 | 158 | 178 | 240 | 0 | 0 | 0 | 40
AP1 LINE (PreTarget Transport Line)
M:TR105B (3100) | AP0 | Mu2E has same transport path as g-2; work was previously done for g-2. | n | n | n | n | n | n |  |  | 150 | 158 | 178 | 240 | 0 | 0 | 0 | 40
M:TOR109 (3100) |  | This assumes the current toroid will NEED to be moved to a new location. For Mu2E, the beam will be bent to the AP3 line at EB6. At its current location, it would only see beam for g-2, NOT Mu2E. | y | n | n | n | y | y |  |  | 6150 | 248 | 288 | 260 | 60 | 130 | 60 | 40 | 1
AP3 LINE (PostTarget Transport Line)
D:TOR910 (3100) | AP30 | This assumes the current toroid will NOT need to be moved. For Mu2E, there is no target at AP0 so beam should be the same as p1->p2->ap1 (1e12 P+, 120nsec) | n | n | n | n | n | n | y | n | 3450 | 250 | 290 | 310 | 0 | 0 | 0 | 40
AP3 Toroid #2 |  | New installation with new ceramic break and CT (3100). | y | y | y | y | y | y | y |  | 12400 | 266 | 315 | 260 | 180 | 130 | 60 | 40
AP2 LINE (Abort Line)
D:TOR704 (7737) | AP0 | WILL NOT BE MU2E BeamPath | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D:724TOR (7737) | AP50 | WILL NOT BE MU2E BeamPath | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D:TOR733 (3100) |  | This assumes the current toroid will NOT need to be moved; the abort line will be as far as the 726 location. For Mu2E, 3-5% of primary protons will be aborted after slow extraction (3-5e10, 120nsec). | n | n | n | n | n | n | y | n | 3450 | 250 | 290 | 310 | 0 | 0 | 0 | 40
D/A LINE
D:806TOR (7737) | AP10 | WILL NOT BE MU2E BeamPath | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D/A Toroid #2 |  | WILL NOT BE MU2E BeamPath | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Extraction Line to Experimental Hall
Toroid#1 | New Building | Toroid-based beam intensity NOT recommeded, because of low intensity p+ during slow extraction (1e12 every 56msec). | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Toroid#2 |  | Toroid-based beam intensity NOT recommeded, because of low intensity p+ during slow extraction (1e12 every 56msec). | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 26200 | 1804 | 2073 | 2340 | 240 | 260 | 120 | 360
Note on C1: cadornaa: as of adjusted Mu2E scope (12/2011- https://indico.fnal.gov/conferenceDisplay.py?confId=5068)'
Note on I2: cadornaa: cabling cost based on $2/Ft for 600ft per cable pull
Note on J2: cadornaa: previously installed for all pretarget toroids
Note on K11: cadornaa: shares front end with TR105B
Note on K13: cadornaa: repurpose crate/control cards from lab; use Alexei's 125MHZ digitizer
Note on K14: cadornaa: shares front end with TOR910
Note on K18: cadornaa: repurpose crate/control cards from lab; use Alexei's 125MHZ digitizer

## MAXIMUM
TOROID | LOCATION | NOTES | Task Descriptions ( excludes routine maintenance) | [7 empty] | M&S Costs | LABOR HOURS
|  |  | New Location/Install | New CT | New Ceramic Break | New RC | New Stand/Supports | New Cables | New ConditioningBrd | NEW VME FrontEnd |  | Electrical Engineer | Electrical Technician | Front End Programmer | Machine Shop | ME Support (Drafter, Mech. Enginer, Mech. Tech) | Vauccm/Alignment Crews | EE Support (Schematic, PCB Drafter, Layout)
P1 LINE (PreTarget Transport Line)
I:TOR914 (3100) | MI60N | Mu2E has same transport path as g-2; work was previously done for g-2. | n | n | n | n | n | n |  |  | 150 | 158 | 178 | 240 | 0 | 0 | 0 | 40
I:TOR902 (3100) | MI62 | Mu2E has same transport path as g-2; work was previously done for g-2. | n | n | n | n | n | n |  |  | 150 | 158 | 178 | 240 | 0 | 0 | 0 | 40
P2 LINE (PreTarget Transport Line)
I:TORF16 (3100) | F1 | Mu2E has same transport path as g-2; work was previously done for g-2. | n | n | n | n | n | n |  |  | 150 | 158 | 178 | 240 | 0 | 0 | 0 | 40
P2 Toroid #2 |  | This assumes that a 2nd toroid was previously installed for g-2. | n | n | n | n | n | n |  |  | 150 | 158 | 178 | 240 | 0 | 0 | 0 | 40
AP1 LINE (PreTarget Transport Line)
M:TR105B (3100) | AP0 | Mu2E has same transport path as g-2; work was previously done for g-2. | n | n | n | n | n | n |  |  | 150 | 158 | 178 | 240 | 0 | 0 | 0 | 40
M:TOR109 (3100) |  | This assumes the current toroid will NEED to be moved to a new location. For Mu2E, the beam will be bent to the AP3 line at EB6. At its current location, it would only see beam for g-2, NOT Mu2E. | y | n | n | y | y | y |  |  | 6300 | 252 | 312 | 260 | 120 | 130 | 60 | 40 | 1
AP3 LINE (PostTarget Transport Line)
D:TOR910 (3100) | AP30 | This assumes the current toroid will NOT need to be moved. For Mu2E, there is no target at AP0 so beam should be the same as p1->p2->ap1 (1e12 P+, 120nsec) | n | n | n | y | y | y | y | y | 15100 | 256 | 344 | 310 | 120 | 70 | 0 | 40
AP3 Toroid #2 |  | New installation with new ceramic break and CT (3100). | y | y | y | y | y | y | y |  | 12400 | 266 | 315 | 260 | 180 | 130 | 60 | 40
AP2 LINE (Abort Line)
D:TOR704 (7737) | AP0 | WILL NOT BE MU2E BeamPath | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D:724TOR (7737) | AP50 | WILL NOT BE MU2E BeamPath | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D:TOR733 (3100) |  | This assumes the current toroid will NOT need to be moved; the abort line will be as far as the 726 location. For Mu2E, 3-5% of primary protons will be aborted after slow extraction (3-5e10, 120nsec). | n | n | n | y | y | y | y | y | 15100 | 256 | 344 | 310 | 120 | 70 | 0 | 40
D/A LINE
D:806TOR (7737) | AP10 | WILL NOT BE MU2E BeamPath | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D/A Toroid #2 |  | WILL NOT BE MU2E BeamPath | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Extraction Line to Experimental Hall
Toroid#1 | New Building | Toroid-based beam intensity NOT recommeded, because of low intensity p+ during slow extraction (1e12 every 56msec). | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Toroid#2 |  | Toroid-based beam intensity NOT recommeded, because of low intensity p+ during slow extraction (1e12 every 56msec). | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 49650 | 1820 | 2205 | 2340 | 540 | 400 | 120 | 360
Note on C1: cadornaa: as of adjusted Mu2E scope (12/2011- https://indico.fnal.gov/conferenceDisplay.py?confId=5068)'
Note on I2: cadornaa: cabling cost based on $2/Ft for 600ft per cable pull
Note on J2: cadornaa: previously installed for all pretarget toroids
Note on K11: cadornaa: shares front end with TR105B
Note on K14: cadornaa: shares front end with TOR910

## COSTING REFERENCE
NOTE: COSTING BELOW IS BASED ON 1 COMPLETE INTENSITY MONITOR SYSTEM with Pearson 3100. NO SPARES ARE INCLUDED HERE. | [17 empty] | Electrical Engineer | Electrical Technician | Front End Programmer | Machine Shop | ME Support (Drafter, Mech. Enginer, Mech. Tech) | Vauccm/Alignment Crews | EE Support (Schematic, PCB Drafter, Layout)
Task# | Task Name/Description | Comments | Preceeding Task # | Task Duration (Total Days) | Manpower Labor (Total Hours for Crew) |  | Material Services (Purchases/Contracts) | [5 empty] | Description | Row | Column | Column Index | MS | Electrical Engineer | Electrical Technician | FrontEnd Programmer | Machine Shop | ME Support (Drafter/Technician) | Vacuum Alignment Crews | EE Suport (Drafter & PCB Layout)
| CT | [6 empty] | 23 | 173 | 0 | 3050 | CT | New CT | 3 | L | 12 | 3050 | 10 | 3
1 | Specify Current Transformer (CT) | Still awaiting beam layout information | CD-0 | 1 | 4 | Electrical Engineer | [6 empty] | New Stand | 9 | L | 12 | 1500 |  | 12 |  | 60 | 70
2 | Procure current transformers (CT) -3100 Model from Pearson |  | 1 | 20 | 160 | Custom Manufacturer | 3000 | [5 empty] | New Ceramic Break | 15 | L | 12 | 2000 | 4 |  |  | 60
3 | Procure calibration loop components |  | 1 | 0.5 | 2 | Technician | 50 | [5 empty] | New Gap RC | 19 | L | 12 | 150 | 4 | 24 |  | 60
4 | Install calibration loop |  | 2 | 0.5 | 1 | Technician | [6 empty] | New Cables | 23 | L | 12 | 2400 | 2 | 6
5 | Perform benchtests on CT's time/frequency response |  | 4 | 1 | 6 | Electrical Engineer | [6 empty] | New Conditioning Board | 26 | L | 12 | 1050 | 44 | 94 |  |  |  |  | 40
| Stand/Mounting Hardware | [6 empty] | 36 | 142 | 0 | 1500 | Stand/Mounting Hardware | Analog Conditioning (no new board) | 31 | H | 8 | 150 | 44 | 82
6 | Survey and measure exact location/space limitations/etc. of each CT | Still awaiting beam layout information | 1 | 5 | 20 | (ME)Designer Draftsman | 250 | [5 empty] | New Vme | 36 | L | 12 | 9850 | 92 | 124 | 70
7 | Review and update CT mounting stand mechanical drawings | Using Exising Design | 6 | 5 | 20 | (ME)Designer Draftsman | [6 empty] | VME Infrastructure | 38 | H | 8 | 7600 |  | 12
8 | Procure any mounting stand materials/ connectors/ etc. |  | 7 | 3.5 | 12 | Technician | 250 | [5 empty] | New Firmware | 47 | L | 12 | 0 | 50 | 20 | 110
9 | Machine CT housing/mounting stand |  | 8 | 15 | 60 | Machine Shop | 1000 | [5 empty] | New Installation | 52 | L | 12 | 2100 | 88 | 92 | 20 |  | 60 | 60
10 | Build CT mounting stands |  | 9 | 7.5 | 30 | Mechanical Engineer | [6 empty] | Total Cost |  |  |  | 22100 | 294 | 375 | 200 | 120 | 130 | 60 | 40
| Ceramic Break | [6 empty] | 36 | 224 | 0 | 2000 | Ceramic Break | Maintenance | 61 | H | 8 | 150 | 64 | 44 | 20
11 | Specify ceramic break | Still awaiting beam layout information | CD-0 | 1 | 4 | Electrical Engineer | [6 empty] | Repurpose VME |  |  |  | 2250 | 92 | 112 | 70 | 0 | 0 | 0 | 0
12 | Procure ceramic break |  | 11 | 20 | 160 | Custom Manufacturer | 1000
13 | Weld/machine ceramic break in series with a section of beam pipe |  | 12 | 15 | 60 | Machine Shop | 1000
| Gap Impedance Circuit | [6 empty] | 8 | 28 | 0 | 150 | Gap Impedance Circuit
14 | Review and update gap impedance network circuit | Using Exising Design | 11 | 1 | 4 | Electrical Engineer
15 | Procure gap imepedance network circuit parts/connectors etc. | cost will increase if teflon/copper band needed | 14 | 3.5 | 12 | Technician | 150
16 | Build gap impedance network circuit |  | 15 | 3.5 | 12 | Technician
| Signal and Calibration Cables | [6 empty] | 2 | 8 | 0 | 2400 | Signal and Calibration Cables
17 | Specify signal and calibration cables and connectors (1 signal cable + 1 calibration cable per CT) | Still awaiting information about beam layout, penetrations, service buildings, etc.. | CD-0 | 0.5 | 2 | Electrical Engineer
18 | Procure signal and calibration cables and connectors | cost based on $2/ft for 600ft * 2 pulls | 17 | 1.5 | 6 | Technician | 2400
| Analog Conditioning Board | [6 empty] | 39 | 198 | 0 | 1050 | Analog Conditioning Board
19 | Review and update CT analog conditioning circuit | Using Exising Design | 1 | 1 | 4 | Electrical Engineer
20 | Draw schematic of conditioning module/chassis | if not necessary, skip to task #25 | 19 | 5 | 20 | (EE) Designer/Drafter
21 | Layout of conditioning module/chassis |  | 20 | 5 | 20 | (EE) Drafter
22 | Procure conditioning board |  | 21 | 7.5 | 60 | Board Assembler House | 500
23 | Order components for conditioning circuit |  | 21 | 1.5 | 12 | Technician | 150
24 | Order components for chassis, powers supply, etc.. |  | 21 | 1.5 | 12 | Technician | 400
25 | Assembly conditioning circuit/chassis |  | 23 & 24 | 7.5 | 30 | Technician
26 | Test received analog conditioning circuit in lab |  | 25 | 5 | 20 | Electrical Engineer / Technician
27 | Perform benchtests on CT's response with analog conditioning circuit |  | 5 & 26 | 5 | 20 | Electrical Engineer / Technician
| VME Hardware | [6 empty] | 52.5 | 236 | 0 | 9850 | VME Hardware
28 | Specify standard VME components (VME64X crates, TCK decoder, crate controllers, etc.) | Still awaiting information about service building locations etc. | CD-0 | 0.5 | 2 | Electrical Engineer
29 | Order specified standard VME hardware (VME64X crates, TCK decoder, crate controllers, etc.) |  | 28 | 3.5 | 12 | Technician | 7600
30 | Setup VME testbed & test operability of standard VME hardware |  | 29 | 7.5 | 30 | Electrical Engineer / Technician
31 | Review and update VME digitizer board schematic/design/fpga software | Using Exising Design | CD-0 | 5 | 20 | Electrical Engineer
32 | Procure VME digitzer board | Will increase if commerical digitizer used | 31 | 7.5 | 60 | Board Assembler House | 1500
33 | Order components for VME digitizer board | if commerical digitizer used, skip to task #35 | 32 | 3.5 | 12 | Technician | 750
34 | Assembly VME digitizer board |  | 33 | 7.5 | 30 | Technician
35 | Review and update VME digitizer driver software | Using Exising Design unless commerical board used | 34 | 7.5 | 30 | Front End Programmer
36 | Test basic operability/resolution/etc.. of VME digitizer |  | 35 | 5 | 20 | Electrical Engineer / Technician / Front End Programmer
37 | Test operability/resolution/etc.. of VME digitizer with conditioned CT signals |  | 27 & 36 | 5 | 20 | Electrical Engineer / Technician / Front End Programmer
| Front End Software Programming | [6 empty] | 27.5 | 110 | 0 | 0 | Front End Software Programming
38 | Develop digital signal processing for intensity measurements, baseline/droop corrections, etc.. |  | 37 | 7.5 | 30 | Electrical Engineer / Front End Programmer
39 | Test digital signal processing with digitized, conditioned CT signals in lab |  | 38 | 5 | 20 | Electrical Engineer / Technician / Front End Programmer
40 | Develop VME Interface code to Control System |  | 37 | 7.5 | 30 | Front End Programmer
41 | Design and implement control system GUI/Page for intensity measurements & waveform displays |  | 39 & 40 | 7.5 | 30 | Front End Programmer
| Installation & Commissioning | [6 empty] | 87.5 | 244 | 0 | 2100 | Installation & Commissioning
42 | Install CT, ceramic break, & mounting stands in tunnel |  | 4 & 10 & 13 | 21 | 60 | Mechanical Support | 250
43 | Vacuum/Electrical/Alignment testing of tunnel installation |  | 42 | 21 | 60 | Vaccuum/Alignment Crews | 500
44 | Install gap imepedance circuit |  | 16 & 42 | 3.5 | 12 | Electrical Engineer / Technician
45 | Layout rack space in service building | Still awaiting information about service building locations etc. | CD-0 | 3.5 | 12 | Electrical Engineer / Technician
46 | Install VME crate and electronics in designated service building |  | 29 & 45 | 3.5 | 12 | Technician
47 | Pull cables from tunnel location via penetrations to designated service buildings | estimated $100/hr | 18 & 45 | 10.5 | 12 | Contracted electricians | 1200
48 | Terminate both end of pulled cables & check for open/shorts |  | 47 | 3.5 | 12 | Technician
49 | Review tunnel installation: connect cables/CT/electrical isolation/pipe conductiviity etc… |  | 44 & 48 | 3.5 | 12 | Electrical Engineer / Technician
49 | Repair/maintenance CT, ceramic break, & mounting stands in tunnel |  | 41 & 49 | 3.5 | 12 | Electrical Engineer / Technician | 150
50 | Calibrate/test intensity monitor system to verify operability and control system readiness |  | 49 | 7 | 20 | Electrical Engineer / Technician / Front End Programmer
51 | Finalize Intensity Monitoring System Documentation |  | 50 | 7 | 20 | Electrical Engineer

## CURRENT INVENTORY
TOROID |  | TUNNEL HARDWARE | [8 empty] | NOTES
|  | KEY | LOCATION | MODEL | BW | Sensitivity | Toroid ID | PreAmp/Etc?
P1 LINE
| I:TOR914 | TEV-F | Q914C | 3100 | 40-7MHZ | 1 V/A | 3.5" | N | *Model 7737 is a special version of the Pearson 1010.
| I:TOR902 | MI | Q617E | 3100 | 40-7MHZ | 1 V/A | 3.5" | N | SPECIAL 1010 CURRENT
P2 LINE | [8 empty] | TRANSFORMER MODIFIED FOR 1.0 V/A
x4678 @F1 / X3543 @F0 | I:TORF16 | TEV-F | QF16 | 3100 | 40-7MHZ | 1 V/A | 3.5" | N | OUTPUT PER PEARSON ELECTRONICS
AP1 LINE | [8 empty] | Purchased on PO 558088
| M:TR105B |  |  | 3100 | 40-7MHZ | 1 V/A | 3.5" | N | 23 Jun 2004, $2200 each.
| M:TRO109 |  |  | 3100 | 40-7MHZ | 1 V/A | 3.5" | N
AP2 LINE
| D:TOR704 |  | IQ704 | 7737* | 400-7MHz | 1 V/A | 10.75" | N
| D:724TOR |  | IQ724 | 7737* | 400-7MHz | 1 V/A | 10.75" | Special
| D:TOR733 |  | IQ733 | 3100 | 40-7MHZ | 1 V/A | 3.5" | Special
AP3 LINE
| D:TOR910 |  | EQ910 | 3100 | 40-7MHZ | 1 V/A | 3.5" | N
D/A LINE
| D:806TOR |  | TQ806 | 7737* | 400-7MHz | 1 V/A | 10.75" | Very Special
TOROID |  | CABLE TYPES | [5 empty] | CABLE LENGTH
|  | SIGNAL | CALIBRATION | CAMAC | VME | 6V PWR | EXTRA? | (SECONDS) | (FEET)
P1 LINE
| I:TOR914 | Trompeter | Heliax | Black | N/A | N/A | Heliax | 9.72e-07 | 361
| I:TOR902 | Trompeter | Heliax | Black | N/A | N/A | Heliax | 1.44e-06 | 535
P2 LINE
x4678 @F1 / X3543 @F0 | I:TORF16 | Trompeter | Foam RG08 | Black | N/A | N/A | Heliax | 1.08e-06 | 401
AP1 LINE
| M:TR105B | Twinax | RG58
| M:TOR109 | Twinax | RG58
AP2 LINE
| D:TOR704 | Twinax
| D:724TOR | Twinax | Heliax
| D:TOR733 | Twinax
AP3 LINE
| D:TOR910 | Twinax | RG58
D/A LINE
| D:806TOR | Twinax
TOROID |  | LOCATION |  | ELECTRONICS
|  | SERV BLDG | RACK | FPGA CHKSUM | SUBTRACT? | BCD GATE | FULL-SCALE | UNITS
P1 LINE
| I:TOR914 | MI 60N | MI60219 | 192D824.POF | Y | 1e-05 | 10000000000000 | E11
| I:TOR902 | MI 62 | MI62106 | 192D824.POF | Y | 1e-05 | 10000000000000 | E11
P2 LINE
x4678 @F1 / X3543 @F0 | I:TORF16 | F1 | F112 | 192D824.POF | Y | 1e-05 | 10000000000000 | E12
AP1 LINE
| M:TR105B | AP0 | THSBS R1
| M:TRO109 | AP0 | THSBS R1
AP2 LINE
| D:TOR704 | AP0 | THSBS R1
| D:724TOR | AP50 | B51R06
| D:TOR733 | AP50 | B51R06
AP3 LINE
| D:TOR910 | AP30 | B37R03
D/A LINE
| D:806TOR | AP10 | A17R03
TOROID |  | MADC 190 / 290 |  |  |  |  | Digital I/O? | CAMAC C184/284 |  | Timing Channel
|  | CRATE | 12-/14-Bit? | MADC # | SLOT | CHANNEL |  | CRATE | SLOT
P1 LINE
| I:TOR914 | MI $73 | 14 | 38 | 23 | 37 | C184 | MI $72 | 11
| I:TOR902 | MI $6B | 14 | 67 | 23 | 5 | C184 | MI $6B | 2
P2 LINE
x4678 @F1 / X3543 @F0 | I:TORF16 | TEV $F9 | 12 | 54 | 1 | 32 | C184 | TEV $F9 | 5
AP1 LINE
| M:TR105B | Pbar $73 |  |  | 1 | 42,45 |  |  |  | Cr 70, Sl 16, Ch 6
| M:TRO109 | Pbar $73 |  |  | 1 | 43,53 |  |  |  | Cr 70, Sl 16, Ch 7
AP2 LINE
| D:TOR704 | Pbar $73 |  |  | 1 | 44 |  |  |  | Cr 70, Sl 16, Ch 4
| D:724TOR | Pbar $55 |  |  | 1 | 8 |  |  |  | Cr 50, Sl 4, Ch 0
| D:TOR733 | Pbar $55 |  |  | 1 | 9 |  |  |  | Cr 50, Sl 4, Ch 0
AP3 LINE
| D:TOR910 | Pbar $38 |  |  | 1 | 44 |  |  |  | Cr 1B, Sl 4, Ch 6
D/A LINE
| D:806TOR | Pbar $1A |  |  | 1 | 26 |  |  |  | Cr 38, Sl 14, Ch 0

## Constants
Calibration Pulses |  |  |  | Cable Type | v/c
Equivalent | Pulse Width | Frequency Setting | LDF5-50A | 7/8" Heliax | 0.89
1NuMI Batch | 1.6e-06 | 312500 | LDF4-50A | 1/2" Heliax | 0.88
2NuMI Batch | 3.2e-06 | 156250 | LDF2-50 | 3/8" Heliax | 0.88
3NuMI Batch | 4.8e-06 | 104166.6667 | FSJ4-50B | 1/2" Superflex | 0.81
4NuMI Batch | 6.4e-06 | 78125 | FSJ1-50 | 1/4" Superflex | 0.78
5NuMI Batch | 8e-06 | 62500 | LDF4-50A | 1/2" Heliax | 0.88
6NuMI Batch | 9.6e-06 | 52083.3333 | LDF2-50 | 3/8" Heliax | 0.88
7NuMI Batch | 1.12e-05 | 44642.8571 | FSJ4-50B | 1/2" Superflex | 0.81
8NuMI Batch | 1.28e-05 | 39062.5 | FSJ1-50 | 1/4" Superflex | 0.78
1 | 1e-06 | 500000 |  | RG213 | 0.67
2 | 2e-06 | 250000 |  | RG58 | 0.67
3 | 3e-06 | 166666.6667 |  | RG174 | 0.67
4 | 4e-06 | 125000 |  | RG108 | 0.66
5 | 5e-06 | 100000 |  | TWC-78-2 | 0.66
6 | 6e-06 | 83333.3333
7 | 7e-06 | 71428.5714 |  | e_Charge | 1.6022e-19
8 | 8e-06 | 62500 |  | R,wvf gen | 50.54
9 | 9e-06 | 55555.5556
10 | 1e-05 | 50000 |  | Speed of Light
|  |  |  | c (m/s) | 299792458
|  |  |  | c(ft/s) | 983571056.43
|  |  |  | v/c @ 4Gev | 0.71305
|  |  |  | v/c @ 8Gev | 0.99447
|  |  |  | v/c @ 12Gev | 0.99997