## Slide 1: Update and discussion

## Slide 2: Installation Schedule
BCR 1007 was implemented in December which revised the schedule and cost estimate for the FD1 and 2 detector installation.
  This implemented the combined top CRP and cathode installation plan.
The FD2 installation schedule was refined to reflect a row-by-row level of detail for the installation.
  This was done first in the sandbox
  Mapping the 6 day work week onto the 5 day P6 calander meant the durations became non-integer
  The overall cost impact was minimal so this was implemented in the master schedule.
Now going through the consortia to verify the changes made to the consortia installation activities and update as needed.

## Slide 3: Reviews
FD2 installation is looking at a preliminary design review in June.
  Planned a couple months after the consortia PDR
  I will suggest installation presentations from the consortia
  I will discuss with Marzio and you the consortia deliverables to this review (documents, drawings, and so on)
    Interfaces will be very important for this review as for all PDRs
Integration including FD1/FD2 installation will have an FDR in Fall.
These are in addition to the other planned DOE/DUNE/Consortia reviews