## Slide 1: Challenges and Lessons Learned from fabrication, test and analysis of ~10 MQXFA Low Beta Quadrupoles for HL-LHC
Giorgio Ambrosio and the MQXFA team

## Slide 2: Acknowledgement
US HL-LHC Accelerator Upgrade Project (AUP)
  BNL: K. Amm, M. Anerella, A. Ben Yahia, H. Hocker, P. Joshi, J. Muratore, J. Schmalzle, H. Song, P. Wanderer
  FNAL: G. Ambrosio, G. Apollinari, M. Baldini, J. Blowers, R. Bossert, R. Carcagno, G. Chlachidze, J. DiMarco, S. Feher, S. Krave, V. Lombardo, C. Narug, A. Nobrega, V. Marinozzi, C. Orozco, T. Page M. Parker, S. Stoynev, T. Strauss, M. Turenne, D. Turrioni, A. Vouris, M. Yu
  LBNL: D. Cheng, P. Ferracin, L. Garcia Fajardo, E. Lee, M. Marchevsky, M. Naus, H. Pan, I. Pong, S. Prestemon, K. Ray, G. Sabbi, G. Vallone, X. Wang
  NHMFL: L. Cooley, J. Levitan, J. Lu, R. Walsh
CERN: HL-LHC Project
  G. Arnau Izquierdo, A. Ballarino, M. Bajko, C. Barth, N. Bourcey, B. Bulat, M. Cruovizier, A. Devred, H. Felice, S. Ferradas Troitino, L. Fiscarelli, J. Fleiter, M. Guinchard, O. Housiaux, S. Izquierdo Bermudez, N. Lusa, F. Mangiarotti, A. Milanese, A. Moros, P. Moyret, C. Petrone, J.C. Perez, H. Prin, R. Principe, E. Ravaioli, T. Sahner, S. Sgobba, P. Tavares Coutinho Borges De Sousa, E. Todesco, J. Ferradas Troitino, R. Van Weelderen, G. Willering

## Slide 3: Outline
MQXFA magnets
Fabrication and test status
Analysis of magnets with limited performance
Lessons learned and corrective actions
MQXFA endurance and resilience
Conclusions

## Slide 4: US Contribution to HL-LHC
From HL-LHC Project Leader
O. Bruning - CERN
HL-LHC AUP
HL-LHC: from 300 fb-1 to 3000/4000 fb-1
LARP (DOE supported R&D Program) established the necessary technology for the HL-LHC Focusing Magnets and Crab Cavities
DOE baselined HL-LHC Accelerator Upgrade Project (AUP), coordinating efforts from US Labs (FNAL, BNL, LBNL with contributions from SLAC, JLAB, ODU & FSU)
Crab
Cavities
Beam size
Quad
Magnets
Slide by G. Apollinari
Notes: Overall goal

## Slide 5: 20 MQXFA Magnets for HL-LHC Inner Triplets
10 Q1/Q3 Cryo-assemblies (including 2 spares)
2 magnets in each cryo-assembly

## Slide 6: MQXFA/B Design
Parameter | Unit | MQXFA/B
Coil aperture | mm | 150
Magnetic length | m | 4.2/7.15
N. of layers |  | 2
N. of turns Inner-Outer layer |  | 22-28
Operation temperature | K | 1.9
Nominal gradient | T/m | 132.2
Nominal current | kA | 16.23
Peak field at nom. current | T | 11.3
Stored energy at nom. curr. | MJ/m | 1.15
Diff. inductance | mH/m | 8.26
Strand diameter | mm | 0.85
Strand number |  | 40
Cable width | mm | 18.15
Cable mid thickness | mm | 1.525
Keystone angle |  | 0.4
P. Ferracin et al., “Development of MQXF, the Nb3Sn Low-β Quadrupole for the HiLumi LHC ” IEEE Trans App. Supercond. Vol. 26, no. 4, 4000207
Nb3Sn Conductor
RRP 108/127
G. Ambrosio et al., “First Test Results of the 150 mm Aperture IR Quadrupole Models for the High Luminosity LHC” NAPAC16, FERMILAB-CONF-16-440-TD
E. Takala et al., “Mechanical Comparison of Short Models of Nb3 Sn
Low-β Quadrupole for the Hi-Lumi LHC” IEEE TAS. Vol. 31, no. 5, 4000306

## Slide 7: MQXFA Fabrication Status I
Conductor: 2560 Km received out of 2660 Km
Cables: 97 fabricated out of 109 (89%)
  Yield is 91.9%
Coils: 83 fabricated out of 102 (81%)
  Fabrication yield is 85.5%
  Yield after magnet assembly & test is 78.9%
Conductor verification and test at FNAL & FSU
Cabling at LBNL
Coil parts procurement at FNAL
Coil fabrication at BNL & FNAL
Structure procurement & Magnet assembly at LBNL
Courtesy of A. Nobrega

## Slide 8: MQXFA Fabrication Status II
9 magnets have been assembled: MQXFA03-11
1 magnet has been disassembled after preload
  MQXFA09
8 magnets have been tested
  MQXFA03-08 and MQXFA10-11
1 magnet has been dis-assembled after test & re-assembled with a new coil
  MQXFA08  MQXFA08b
MQXFA03 during final preparation at LBNL
K. Ray et al., “Applied metrology for the assembly of Nb3Sn MQXFA quadrupole magnets for the HL-LHC AUP” 3LPo1A-02

## Slide 9: MQXFA Vertical Test
  MQXFA magnets are vertically tested at BNL
  Test plan demonstrates:
    Holding at Acceptance Current: Nominal + 300 A
    Temperature margin: Nominal curr. at 4.5 K
    Memory after thermal cycle
    Other requirements (next slide)
9
MQXFA @ BNL

## Slide 10: Vertical Test Summary
Magnets are accepted for use in LMQXFA Cold Mass if they meet all Vertical Test Requirements
  Hold current at nominal current + 300 A
  Field Quality
  Integrated gradient
  Ramp to/from I_nom at ±30 A/s
  100 A/s ramp down w/o quench (max for power supply)
  Temperature margin
  Training memory
  Splice resistance (less than 1 nW)
  All electrical requirements
S. Feher et al., “AUP first pre-series Cryo-Assembly Design Production and Test Overview” 2LOr2A-04

## Slide 11: Vertical Test: Training
MQXFA03-06 and MQXFA10-11 reached and held Acceptance Current and met all requirements tested at BNL
6 out of 8 magnets tested

## Slide 12: Integrated Gradient & Field Quality @ BNL
Mechanical data and analysis:
L. Garcia Fajardo et al., “Analysis of the mechanical performance of the 4.5 m long MQXFA Pre-Series magnets for the Hi-Lumi LHC Upgrade” 3LPo1A-01
Average IG at 16.23 kA: 561.92 T
In order to obtain a consistent comparison, correction factors were applied to several magnets to account for measurements taken at different currents as well as changes in the measurement setup and coil design
Courtesy of G. Sabbi and A. Ben Yahia
Field Quality in Straight Section vs expectation
Before b6 correction in cross-section

## Slide 13: Outline
MQXFA magnets
Fabrication and test status
Analysis of magnets with limited performance
  MQXFA07 and MQXFA08
Lessons learned and corrective actions
MQXFA endurance & resilience
Conclusions
US-HiLumi-doc-4293
CERN EDMS 2777612

## Slide 14
Courtesy of J. Muratore and A. Ben Yahia
Location based on Quench Antenna and Voltage Taps
Reverse temperature dependence
Reverse ramp-rate dependence
Same features and location in MQXFA08

## Slide 15: Limitation “Mechanism”
Self-field instability triggered by a local issue, likely affecting only some strands, that pushes more current in adjacent strand(s)
  Field in quenching turn is between 6 and 9 T
Similar mechanism in other magnets:
  MQXFS03 showed a reversible component
  LARP Long Quadrupole #2 showed “enhanced thermo-magnetic instability” in mid-plane block
  With flux jumps
H. Bajas et al., “Test Results of the Short Models MQXFS3 and MQXFS5 for the HL-LHC Upgrade”, IEEE Trans. Appl. Superc. Vol 28, # 4007006 (2018)
Ref: G. Ambrosio et al., “Progress in the Long Nb3Sn Quadrupole R&D by LARP”, IEEE Trans Appl, Superc. Vol 22, # 4003804 (2012)
B. Bordini, et al., IEEE Trans. Appl. Superc., vol. 22, 2012, # 4705804
A. K. Ghosh, IEEE Trans. Appl. Superc., vol. 23, 2013, # 7100407

## Slide 16: Coil Fabrication Analysis
A few discrepancies during fabrication:
  Some strands popped out during winding, were fixed, popped out overnight and were fixed a second time (BNL DR AM-164)
  Limiting coil was affected by COVID lockdown
    14 weeks stop after winding & curing of inner layer
  No other NCR nor traveler data anomaly
coil 214 as it was setup for the lab shutdown
Inner layer coil showing in yellow the position of coil-214 cable affected by DR AM-164
Courtesy of J. Schmalzle

## Slide 17: Structure Analysis & MQXFA07 Disassembly
Yoke
Al shell
Gap key
Cooling
holes
Collar
Pad
Pole key
Axial rod
location
Master
keys
Load
key
Bladder
location
A pole-key gap asymmetry was found during MQXFA07 and MQXFA08 disassembly:
- Gaps closed in quadrant 3
- Gaps open in other quadrants
Courtesy of P. Ferracin and D. Cheng

## Slide 18: Pole-key gaps in MQXFA07
The measured pole-key gaps were not as uniform in MQXFA07 and MQXFA08 as in past magnets; this is particularly apparent on the limiting coils (Q3 for both magnets)
Only the total average (on the 4 keys) was targeted in the specification. The underlying assumption was that the gaps would be redistributed across coils during loading.
Investigation of the effect of this non-uniformity on the mechanical performances with 2D and 3D FE models
  2D effect: preload variation within acceptable range
Courtesy of P. Ferracin and D. Cheng
LL1

## Slide 19: Possible Damage at Wedge-Spacer Interface
At cold the coil with less azimuthal preload ends up with less longitudinal preload
At nominal current tension develops between the inner wedge and the end spacer, and a (small) gap may open
This may result in high longitudinal strain (up to 0.4%) in that location
  This location is consistent with quench data
  Effect is larger on the pole block, but also visible on the mid plane block
Courtesy of G. Vallone and P. Ferracin
LL2

## Slide 20: Micrographic Analysis of Coil 214 Lead End
No anomalies found in cross-section #1.
Therefore, we did longitudinal sections
Analysis started with sample #1: wedge-spacer interface
CT-scan, dye-penetrant test and metallurgical analysis by CERN teams
OUTSTANDING!
By M. Crouvizier, A. Moros, S. Sgobba, CERN
By B. Bulat, CERN
S. Sgobba et al., “Advanced Examination of Nb3Sn Coils and Conductors for the LHC luminosity upgrade: Computed Tomography and Materialographic Analyses”, this session

## Slide 21: Metallurgical inspection: the smoking gun!
Longitudinal cuts on cables adjacent to the end-spacer/copper-wedge transition
  Localized field of broken filaments (red dots), especially at pole block
By M. Crouvizier, A. Moros, S. Sgobba, CERN
# | Samples adjacent to W-S transition from coil 214 Lead End | Number of cracked filaments
1 | Layer-jump side, cable in midplane block, side adjacent to W-S transition | 0
2 | Layer-jump side, cable in pole block, side adjacent to W-S transition | 532
3 | Non-layer-jump side, cable in midplane block, side adjacent to W-S transition | 54
4 | Non-layer-jump side, cable in pole block, side adjacent to W-S transition | 728
5 | Same cable of sample 4, side opposite to the W-S transition | 0

## Slide 22: MQXFA08 Analysis
Same features as in MQXFA07
Metallographic analysis of lead end shows broken filaments at wedge-spacer interface
By M. Crouvizier, A. Moros, S. Sgobba, CERN
S. Sgobba et al., “Advanced Examination of Nb3Sn Coils and Conductors for the LHC luminosity upgrade: Computed Tomography and Materialographic Analyses”, this session

## Slide 23: Covid impact
Changes to assembly procedures caused by COVID requirements
  #1: change in bolting procedure for increasing tech distance
  #2: the technician who had been leading the coil-pack assembly operations was removed from that task (starting from MQXFA06) because not vaccinated.
COVID lockdown
   Stop in fabrication of coil 214 after Inner-Layer was cured may have weakened wedge-spacer bond
Less supervision caused by COVID
   increased probability of non-uniform pole-key gaps and other differences.
Courtesy of P. Ferracin and D. Cheng

## Slide 24: Preventive Actions
In order to prevent reoccurrence of this issue,
Design change for larger pole-key gaps:
  From 200 mm to 400 mm - average pole key gap per side
Revised MQXFA Series Magnet Production Specification:
  Added spec for minimum gap on each coil at each longitudinal location: 300 mm per side
MQXFA10 Quench History
MQXFA10 Pole-key gaps
Courtesy of A. Ben Yahia
Courtesy of P. Ferracin
D. Cheng et al., “The challenges and solutions of meeting the assembly specifications for the 4.5 m long MQXFA magnets for the Hi-Luminosity LHC” 2LOr2A-02

## Slide 25: Endurance Tests
Previous endurance tests were successfully performed on short models
MQXFA05 met requirements after 5 thermal cycles, 52 quenches and 79 powering cycles
5 Thermal cycles
52 quenches (10 spontaneous + 42 induced)
79 power cycles (52 quenches + 27 cycles w/o quench) above 10 kA.

## Slide 26: MQXFA11 “Resilience Test”
The truck transporting the MQXFA11 magnet from LBNL to BNL was rear ended by another truck.
The main hit took place on the right back corner. During the incident the truck rear axle disengaged as displayed below. Nobody was injured.
The magnet was moved to FNAL. Upon arrival a visual inspection was performed followed by electrical checkout, metrology survey, analysis of the fiber optic sensors and accelerometer data analysis
  Max shock: 6 or 10 g vertical (depending on the device in the same accelerometer unit)
  Duration: 5 ms
All tests and analyses were OK. Magnet was shipped to BNL
Courtesy of J. Blowers
Courtesy of T. Cruise

## Slide 27: MQXFA11 “Maverick” Quench History
Courtesy of A. Ben Yahia

## Slide 28: Conclusions - I
AUP is close to 50% MQXFA magnet fabrication
6 out 8 magnets met vertical test requirements
MQXFA07/08 “smoking gun” was found
  Mechanism is understood
  Covid restrictions and lockdown contributed to the degradation mechanism
  Design change (larger gaps) and Specification revision (minimum gaps spec.) are going to prevent reoccurrence in future magnets
  MQXFA10 & MQXFA11 demonstrated that this issue is over
MQXFA05 demonstrated Endurance
MQXFA11 demonstrated Resilience

## Slide 29: Question & Answer
Is it possible to fabricate Nb3Sn magnets for particle accelerator?
Yes!
  It is challenging because Nb3Sn is strain sensitive and brittle
  Therefore, design and specifications must assure that all points in the acceptable-tolerance space are safe
    Including: parts tolerances, assembly tolerances, procedure variabilities, operation variabilities, …
  And cost per magnet should be reduced
G. Ambrosio et al., “Development and demonstration of next generation technology for Nb3Sn accelerator magnets with lower cost, improved performance uniformity, and higher operating point in the 12-14 T range” http://arxiv.org/abs/2203.07352

## Slide 30: Backup Slides

## Slide 31
Based on these findings, we understand that coil 214 pole-key gaps were closed at cold, whereas those of other coils were open. During magnet energization this difference caused tensile strain at wedge-spacer interfaces in coil 214 ends. In early ramps to quench (possibly before or during ramp #4) the bonding between the copper wedge and the resin (filled with S-e glass) gave away in the lead end increasing the strain on the strands closest to that interface. The “increased” strain degraded some strands and triggered the enhanced self-field instability behavior. This mechanism caused quench #4 and all subsequent quenches at 1.9 K and 20 A/s.
These quenches with hot-spot close to the wedge-spacer interface may have exacerbated this mechanism increasing the local strain and strand damage, and therefore causing the current drop (~1 kA) from quench #4 to #8.

## Slide 32: MQXFA08 Quench History
Fixed 42-nohm splice to test facility
Connected voltage taps to coil 213 LE

## Slide 33: Magnet Dis-assembly
Pressure imprint in Q3 pole-key gaps
Unusual marks at wedge-spacer interface in lead end

## Slide 34: Covid impact on Magnet Assembly
Changes to magnet assembly procedures due to Covid requirements:
#1: change in bolting procedure for increasing tech distance
#2: the technician who had been leading the coil-pack assembly operations up to magnet MQXFA05 was removed from that task (starting from MQXFA06) because not vaccinated.
Before change #1
After change #1

## Slide 35: Assessment of MQXFA Data & Travelers
Completed assessment of travelers for Coil Fabrication at BNL, and Magnet Assembly at LBNL:
Assessment of coil parameters, which are being tracked, did not show any anomaly
Coil traveler assessment did not show any issue in addition to known DRs
Assessment of magnet assembly & preload data in next slides

## Slide 36
Left: coil section after samples were extracted for metallographic inspection.
Center: color scheme used to show the position of filament cracks with respect to the W-S transition in the following figure. A: End spacer + ceramic coating ≈ 0,5 mm; B: resin (filled with S-2 glass) between end spacer and wedge ≈ 1,5 mm; C: copper wedge.
Right: color scheme applied on sample with broken filaments.
Copper wedge
End spacer & ceramic coating
Resin with S-2 glass
By M. Crouvizier, A. Moros, S. Sgobba, CERN