## Slide 1: Plans for Data Challenge 4: Introduction
Steven Timm / Doug Benjamin / Wenlong Yuan / Igor Mandrichenko

## Slide 2: Two Parts to Data Challenge
Phase 1: Data Pipeline Test:
  From Experimental Hall EHN-1 to CERN Public EOS to Fermilab
  Current schedule June 13-17
  Will discuss that in this section
Phase 2: Distributed Processing Test:
  Testing processing of data with the new workflow manager tools
  No current schedule yet
  Will be discussed in next session
GOALS FOR THIS MEETING
  Identify information we need from other groups to plan joint sessions @ Collaboration meeting
  Get decisions on key decision points
  Show the critical path items and where effort is needed

## Slide 3: Project Plan
https://github.com/orgs/DUNE/projects/4/views/1
Scope document: https://docs.google.com/document/d/1dtFxDV7RwU2RGSQkR5xJqWDc-bkLTTuE-FDt9v74_pI/edit
6 defined milestones (two initial dates already past)
Goals and Scope of Data Challenge Finalized (April 25)
Component Functionality Testing Completed. (May 2)
Benchmarking testing completed (May 16)
Data Processing Final Component Selection (May 31)
Data Pipeline Final Component Selection(May 31)
Start of Data Challenge(June 13 for phase 1)

## Slide 4: How Much Data and How Fast
Demonstrate sustained bandwidth of 10Gbit/s DC from EHN-1 to CERN data center to Fermilab for 1 week (5 working days) [This will be ~ ½ PB]
Try to get a burst of 40Gbit/s DC if possible near the end
100TB / 4 GB = 25000 files a day!
INFORMATION NEEDED: Is this rate enough? Is it way too much? Need real NP04 data rates and sizes for second beam run.
Conservatively assuming 25MB/s per 4GB file across Atlantic, need 50 simultaneous transfers going continuously to use 10Gbit/s (1.25GB/s)
Reliability goal:
  Generate enough test data to send 100TB
  Run for 24 hrs/day or until we send 100TB whichever comes first
  Monitor systems during Europe and US business hours (0800-2200 UTC)

## Slide 5: DAQ Machines
NP02 (vertical drift)
np02eos1, np02eos2
Need to shift from pushing file to EOS, to having ingest daemon do 3rd party transfer between np02eosx and eospublic
vd-coldbox-top (top electronics) data set available for test, 50 TB of root files
Vd-coldbox-bottom (bottom electronics) data set available, 15 TB of HDF5 files (so far)
NP04(horizontal drift)
Np04-srv-00[1-4]
Need to add authentication to xrootd servers
What data to use for horizontal drift test?
  No MC available yet
  HD Coldbox stuff not analyzable

## Slide 6: Data Generation for challenge
For Phase 1, data pipeline, we could use anything as long as it’s the right file size.
But it would be ideal to use the data pipeline to get the files for Phase 2 (processing) in place, otherwise we will have to do that too.
Can use a small collection of either Monte Carlo or Data files but ideally whatever we use should be reconstructable
Write shell script to copy these files to the target directories on the DAQ machines but change the file names and the metadata in the following ways
  DC4 included in file name and DUNE.Campaign
  A timestamp in every single file to make the name unique
  A DC4 special scope and file family for all the data
  Emulate a series of increasing run numbers preferably in a nonused run number range.. This is needed both for storage and for rucio data sets.

## Slide 7: Ingest Daemon (FTS-Light)
Developer Responsible—Igor Mandrichenko—FNAL
Status—Beta testing ready to go.
Differences from before: Now use FTS-3 to do the file transfer from EHN1 to CERN Public EOS, instead of the daemon doing it directly

## Slide 8: Declaration Daemon (Temp. F-FTS Repl).
Responsible Developer: Igor Mandrichenko (FNAL)
Status: Coding in progress
Differences from before: Trust Rucio / FTS3 to do the cross—Atlantic file transfers rather than doing them itself
This is *temp* solution for the data challenge and will be re-evaluated later.
This is critical path but we expect it can be ready on schedule

## Slide 9: Rucio mods for R/W RSE’s
Responsible developer: James Perry, Edinburgh
Status: Ready for test
Testing responsibility: B. White / FNAL, S. Timm / FNAL
Differences from before:
  Forcing everything new declared in Rucio to have also been declared in MetaCat already
  Supplying a new LFN-to-PFN path
Critical path.. Can’t use Rucio to move data until FNAL_DCACHE and CERN_PDUNE_CASTOR (CTA) are read/write
Critical Path: Need all clients packaged and in CVMFS.

## Slide 10: MetaCat
Developer responsible: Igor Mandrichenko (FNAL)
Status: Stable but need to test at scale.
New features: now datasets can have metadata as well as files
Critical Path:
  Need to give DAQ instructions on how to make metadata JSON files that can be used with either MetaCat or SAM
  Need to give offline instructions on how to make metadata within a job

## Slide 11: Benchmark testing on file transfers
Responsible: TBD
How to optimize 3rd party transfers for xrootd and https
How to make sure we can get the rate of 100TB/day (10Gbit/s)
Are there any roadblocks in Rucio itself or in FTS3
Point to point iperf from inside EOS to inside FNAL to check network bandwidth and routing of new transfers
Information needed: Need help from CERN for right access point for benchmarking and how to access the network. (We have names of whom to contact but not the info yet).

## Slide 12: Monitoring:
Responsible: TBD
Status: OMG
We have names of people to contact but no answers yet.
In Phase 2, data dispatcher and workflow allocator need to be hooked up to ElasticSearch (to give access to similar monitoring as we’ve done for SAM)
In Phase 1, have to make sure existing Rucio monitoring keeps working stably and find the existing FTS3 monitoring.