## Slide 1
Performance and Plans for Fermilab Accelerator Complex Operations
Michael Lindgren
Fermilab PAC summer meeting
21 June 2022

## Slide 2: Outline
Accelerator operations
    P5/Scope
    2016 to present
    Plan until long shutdown
Modernization
COVID impacts
Workforce
Summary

## Slide 3: Alignment
P5 plan has been in place for some time, and still the guide
Recommendations related to Fermilab accelerator operations:
  Recommendation 1: Pursue the most important opportunities wherever they are, and host unique, world-class facilities that engage the global scientific community.
  Recommendation 12: In collaboration with international partners, develop a coherent short- and long-baseline neutrino program hosted at Fermilab.
  Recommendation 14: Upgrade the Fermilab proton accelerator complex to produce higher intensity beams. R&D for the Proton Improvement Plan II (PIP-II) should proceed immediately, followed by construction, to provide proton beams of >1 MW by the time of first operation of the new long-baseline neutrino facility.
  Recommendation 22: Complete the Mu2e and muon g-2 projects.
Strong focus on these recommendations continues

## Slide 4: Accelerator Operations Scope
Funding provided by DOE HEP for the operation of the Fermilab accelerator complex to supply particle beams to Intensity Frontier Experiments and the Test Beams
  NOvA, g-2, ANNIE, ICARUS, SwitchYard 120 GeV (SY120) test beam program, MeV Test Area (MTA/ITA) – Spinquest (NE) and SBND (FY23)
  Includes electrical power and computing activities for accelerator operations needs
  Short and mid-term accelerator R&D
  eg. Booster Studies joint task force with PIP-II, Accelerator complex studies task force
  Special Process Spares(SPS), Accelerator Improvement Projects(AIP) are funded in separate operations Field Work Proposals, but considered operations.
Roughly speaking, an $80M budget has $60M labor, $10M power, and $10M other M&S.

## Slide 5: Accelerator Operations funding
2016 Review Accelerator Operations Closeout Assumptions
    The funding plan for Accelerator Operations including Accelerator Improvement Projects (AIP) from FY15 to FY20 is about flat: FY15: $81M, FY16: $91M, FY17: $87M, FY18: $89M, FY19: $89M, FY20: $91M.
B&R | All Divisions |  |  |  |  | 
 | FY16 Budget | FY17 Budget | FY18 Budget | FY19 Budget | FY20 Budget | FY21 Budget
KA 22 02 021 - Intensity Facilities - Accelerator Operations | $ 74,005,000 | $ 75,545,000 | $ 70,972,000 | $ 72,300,000 | $ 81,300,000 | $ 77,583,000
KA 22 02 021 - Intensity Facilities - Accelerator EQU | $ 8,325,000 | $ 11,000,000 | $ 4,592,000 | $ - | $ 1,000,000 | $ 1,500,000
KA 22 02 021 - Intensity Facilities - AIP | $ 7,450,000 | $ (1,800,000) | $ - | $ 5,600,000 | $ - | $ -
KA 22 02 811 - Inventory - Special process Spares | $ (2,400,000) | $ (2,565,000) | $ - | $ - | $ 900,000 | $ 1,500,000
Totals | $ 87,380,000 | $ 82,180,000 | $ 75,564,000 | $ 77,900,000 | $ 83,200,000 | $ 80,583,000
B&R | All Divisions |  |  |  |  | 
 | FY16 FTE | FY17 FTE | FY18 FTE | FY19 FTE | FY20 FTE | FY21 FTE
KA 22 02 021 Intensity Facilities - Accelerator EQU | 19.3 | 21.1 | 8.6 | 0.6 | 0.4 | 1.3
KA 22 02 021 Intensity Facilities - Accelerator Operations | 218.5 | 218.5 | 240.7 | 226.2 | 232.9 | 247.0
KA 22 02 021 Intensity Facilities - AIP | 20.4 | 11.0 | 1.1 | 4.4 | 4.7 | 2.0
KA 22 02 811 Inventory - Special Process Spares | 8.5 | 5.3 | 2.9 | 4.0 | 4.5 | 7.7
Totals | 266.8 | 255.9 | 253.3 | 235.1 | 242.5 | 258.0
Have not quite met the anticipated levels, overall budget alignment with P5 the priority

## Slide 6: Current Accelerator Operations Beam Delivery
Muon Campus:
(g-2, Mu2e)
Long Baseline Neutrino:
NOvA, (LBNF/DUNE)
Short Baseline Neutrino:
MicroBooNE (completed), ICARUS,ANNIE, SBND
SwitchYard 120:
SpinQuest, Emphatic, test beam (FTBF)
NOvA
MTA/ITA

## Slide 7: NuMI operations
Completion of PIP allowed consistent ~650kW to NuMI when SY/BNB/g-2 running
Power limited by booster throughput/losses
Plan to run until ~2026

## Slide 8: NuMI operations
Substantial downtime this running period
  Quadrupole (IQC) failure in MI-30 High Radiation Area
  Limited Spares, and failures of those
  HRA work planning
  Munters – supply chain
Did achieve 893 kW power
  Keeping losses under control key to sustainable higher power running

## Slide 9: BNB operations
BNB operations generally stable and delivering beam when experiments are ready
MicroBooNE competed
ANNIE, ICARUS in operations
SBND online next year
Will run program until ~2026 (long shutdown for PIP-II/LBNF)

## Slide 10: BNB operations
BNB startup slow this run period
  Power panel failure in RAW system
Otherwise as needed by experiments

## Slide 11: Muon Campus operations
g-2 beam operations since 2018
Accumulate ~19 BNL datasets by end of FY22 run
  Accelerator downtime in 2019 from unexpected lens failures
  Collider components – gradient reduced, at 340M pulses on current lens
  Reduced data delivery rate
g-2 has delivered high impact science results from early running
  Proposed FY23 run in opposite polarity mode – accumulate 4x BNL mu- data

## Slide 12: Muon Campus operations
Normal running for most of this run period
  Some experiment startup issues
  Downtimes coordinated with mu2e beamline work
g-2 proposed FY23 run in opposite polarity mode
  Goal - 4x BNL mu- data
  Reduces NOvA POT’s
  Requires polarity reversals at beginning and end of run period
  Was done in TeV era, believe we can execute safely

## Slide 13: Operations plan through the long shutdown

## Slide 14: Beam delivery plan
Long shutdown for LBNF/PIP-II now begins January 2027
  Will continue running NOvA, ICARUS, SBND
  Mu2e helped – possible to get close to a year of physics data given current schedule
  FY20 shutdown for LBNF site prep  6 mo + COVID
  FY21-FY25 planned 10-week shutdowns  14 weeks FY21
  skip the summer 2026 shutdown(?)
  Electrical costs a recent concern
  Plan for complex to be down for ~two years for PIP-II and LBNF starting January 2027
ICARUS
SBND

## Slide 15: Beam Delivery estimates going forward
Actuals vs original predictions, then future predictions starting from current point
“Design” is the upper (red) curve on the previous annual delivery plots

## Slide 16: Mu2e Operations planning
Commissioning behind original schedule
  conflicts of funding, personnel availability, project delays, and g-2 running
Delivery of first proton beam to the M4 diagnostic absorber – KPP met
Accelerator scope remaining before operating Mu2e
Operations scope
  Installation coordination
  Software
  Beam Commissioning
  Delivery Ring BPMs
  Remote handling system
  Spill control electronics
  Shielding Assessments
  Additional in tunnel shielding
  Instrumentation for extraction
  Design and install target air barrier
  Radiation protection improvements
  Obtain spares (ESS, AC dipole, targets etc.)
  Install ESS
  Completion of berm
  Install end of M4 beam line
  Install hatch blocks
  SAD chapter update
  ARR
  Collimator upgrade
  Abort kicker controls
Project scope
  Assemble Extraction septa
  ESS power supplies
  Assemble AC Dipoles and install
  Complete tune monitor system
  M4 final focus vacuum installation
  ESS fluorinert skid
  AC Dipole power supplies
  Install extinction monitor system
  Insert HRS into PS
  Install target into HRS
  Install power supply for skew quads
  Complete low level RF system
Ongoing activities
Not yet begun

## Slide 17: Accelerator improvements since ~2016
Proton Improvement Plan (PIP) largely completed by 2017
NuMI 1MW target AIP installed – 900 kW operations enabled
MTA/ITA facility designed, built, commissioned, and in operation
PreAcc - Laser notcher installed
Linac - Marx Modulators installed (increased tube lifetime)
Booster - RF solid state driver upgrade, final 3 RF cavities, BPM electronics upgrade
  -> 15 Hz operations, up from 7.5 Hz historically
MI/RR - 2016 RR collimators, 2019 Addition of Sextupoles in RR, 2020 1.2 second ramp implemented in MI, 2022 Off axis injection in RR reduced losses
  Increased beam power by 30% (700-900KW) and decreased losses by a factor of 2.

## Slide 18: Accelerator Modernization Plans
PIP-II, LBNF/DUNE are major investments and upgrades to complex
ACNET is current accelerator controls system
  1980’s system design, capable, but obsolete, increasingly
  ACORN (Accelerator Controls and Operations Research Network) project proposed
Additional target/horn fabrication and target materials R&D capability planned
2019 Detector and Accelerator Modernization Plan
  Identified equipment and facility needs to increase capability, reliability, and or system resilience. 54 total within the accelerator complex. 39 proposals support the main injector, 3 proposals support the booster, 1 supports the LINAC, and 11 support the general complex.
  Look ahead to needs largely outside of major project scope – will attack according to priority and funding in concert with HEP

## Slide 19: PIP-II - Scope and Layout
Booster
BTL
Existing Main
Ring
F37 Service Building
HighBay Building (HBB)
Linac Gallery
Linac Tunnel
Tunnel Extension Option
Cryoplant
Future muon line
800 MeV H−, 2mA, CW-compatible linac
Linac-to-Booster transfer line
Accelerator Complex Upgrades
  Booster
  Recycler Ring
  Main injector
Conventional Facilities
Plenary-Pozdeyev

## Slide 20: PIP-II and Operations before 2027 Shutdown
Interfaces coordinated with Accelerator Division - CF (Booster connection), Controls, Upgrades to Booster, Recycler, and Main Injector
Several PIP-II Accelerator Upgrade systems are delivered and tested with beam before the long shutdown
  Booster DCCT (installed), Booster collimators (2023), Booster longitudinal dampers (2023), Booster Transverse dampers (2025), _t jump for MI (2024), MI RF stations (12 out of 20 installed before long shutdown)
  Early installation and test of these systems will benefit operations of the Accelerator Complex, speed up the power ramp-up in PIP-II era, and reduce risk
  Matrixed with operations experts
Joint Booster Intensity Team (PIP-II, Accelerator Division, Scientific Computing Division) conducts synergetic, comprehensive numerical and experiential studies to understand sources of beam losses and intensity limits in Booster in PIP-II era

## Slide 21: LBNF/DUNE
Provides a beamline to support a 1.2 MW proton beam used to produce high-intensity muon neutrino beam for the DUNE experiment.
    Upgradeable to 2.4MW
LBNF Near Site prep largely completed during extended 2020 shutdown
  Extensive work done close to MI/RR – completed with minimal impact to MI/RR
  Valuable exercise in project and operations coordination - lessons learned document
Matrixed workforce for beamline with Accelerator Division
AD facilities needed
  Increased target/horn production capability and R&D for multi-MW - Proposal for TSIB GPP with HEP
  Other staging/storage locations

## Slide 22: Covid impacts
Accelerator operations paused mid-March 2020, and a decision to not attempt to restart before the scheduled summer shutdown was made in early April 2020.
  Advanced shutdown work planning efforts and LBNF site prep
  Protocols for on-site work developed and increased WPC implemented
Beam operations restarted Nov 2020
Lower efficiency in on-site work and response time
Supply chain issues and external workforce concerns common to SC complex
Issues related to remote work and new employee’s mirror impacts noted at all the operations focused SC labs https://www.osti.gov/biblio/1785683/
No known cases of COVID transmission related to accelerator operations

## Slide 23: Workforce Planning - Accelerator Ops
Major effort in 2019 Detector and Accelerator Modernization (DAM) plan was to initiate a better workforce planning process
Effort has continued – annual process projecting out 10 years
~Flat to beginning of PIP-II operations

## Slide 24: Workforce Planning – Accelerator ops attrition

## Slide 25: Workforce - New AD colleagues since March 15, 2020

## Slide 26: New AD colleagues (continued)
New to Division: 86

## Slide 27: Workforce – departing AD colleagues since March 15, 2020

## Slide 28: Former AD colleagues (since March 15, 2020)
Departed: 58

## Slide 29: Operational Safety
Strong safety performance
Existing work planning and controls tools have been augmented with IMPACT software and extensive Rad Safety changes
  Parts of enclosures have higher activation levels with higher beam power
  Have continued to keep personnel exposure low
  Contamination increasingly an issue
  Tritium, Beryllium-7
  We work with equipment that has other dangers as well – much equipment in use that was a different era in safety

## Slide 30: Summary
Delivering on DOE science mission – operations work scope aligned with P5 and available funding
COVID navigated successfully – no known transmission on-site, operations made extensive adjustments to continue safe work, beam and shutdown
Critical Modernizations needed are understood and underway or planned
Projects and operations coordinate to share resources/support
  These projects are building the future of Fermilab accelerator complex operations
Ten-year workforce plan developed and updated annually
We feel we have had a strong safety record, and as beam power increases the rad safety requirements must increase in step. ES&H is vital to successful operations
Continued focus on successful mission delivery through operations, while also working with projects to build the future laboratory

## Slide 31: Backup slides