## Slide 1
PIP-II 2nd Technical Workshop, WG#1
Status of HB650 Prototype CM Assembly
Chuck Grimm
Fermilab
12-14 July 2022

## Slide 2: Outline
Team Background
  Roles
  Support Teams
Cavity String Details
Phase Assembly Overview
  Phase 1A – Beam Line Assembly (F10152132) - Complete
  Phase 1B – Strongback Fitment and Assembly (F10152150) – In Progress
  Phase 1C – Strongback and Beamline Merger (F10152201)
  Phase 2 – Coldmass Assembly (F10152230)
  Phase 3 – Insertion of Coldmass into Vacuum Vessel (F10152239)
  Phase 4 – Final Cryomodule Assembly (F10152255)
Look Ahead
Misc. Work
  Thermal Shield Assembly
  Titanium Cavity Support Fabrication

## Slide 3: Team Background
Experienced teams with over 30 cryomodules built to date. **
  Consisting of 3.9 GHz, 1.3 GHz, 650MHz, 325 MHz (SSR1) modules
**Some minor changes for PIP-II modules

## Slide 4: String Details
Mixture of B92 and B90 cavities
Four cavities with internal instrumentation
All Cavities dressed at FNAL

## Slide 5: Phase 1A: Beam Line Assembly
Reference Drawing: F10152132
Traveler: 464613
Main Tasks
  Assemble beamline in the cleanroom - complete
  Receive beamline from cleanroom - complete
  Connect beamline to the lifting tooling - complete
  Install B92 tuners - complete
  Install B90 tuners - complete
  Install local magnetic shields - complete
  Weld cooldown line – complete
Traveler will be closed once all DR’s are dispositioned

## Slide 6: Phase 1A: Beam Line Assembly
Roll out was easy, glided smooth on the rails
View Downstream Looking Upstream
RRCAT-502

## Slide 7: Phase 1A: Beam Line Assembly
Post cleanroom alignment check
  Coupler-to-coupler spacing could have been a little better
  Overall length of string, end plate to end plate 16mm too long, needed minor adjustment to correct spacing
Data Courtesy of Virgil Bocean

## Slide 8: Phase 1A: Beam Line Assembly
Temperature Sensors and Heaters
  25W heater installed under vessel secured with Stycast and G-10 cover
  Two temp. sensors installed on each tank, one on top and bottom, secured with Stycast and G-10 “Garage”

## Slide 9: Phase 1A: Beam Line Assembly
MLI Blanket Installation
  10-Layer blankets – hand made
  Folded at joints to avoid thermal shorts, “best practice”

## Slide 10: Phase 1A: Beam Line Assembly
Magnetic Shield and Lifting Plate/Coupler Support

## Slide 11: Phase 1A: Beam Line Assembly
Install Lifting Fixture to the String
  Position string centered under to the lifting fixture
  Install threaded rod connections and torque all hardware
US End Supports
DS End Supports
Cavity Supports

## Slide 12: Phase 1A: Beam Line Assembly
Install Lifting Fixture to the String
  Torque all connections to proper values
  Check all connections in preparation for lift
Final View Attached to Lifting Fixture and Cleanroom Posts

## Slide 13: Phase 1A: Beam Line Assembly
Lift String From the Cleanroom Stands
  Disconnect connections of cleanroom stands and back off alignment screws
  Slowly lift until loose from cleanroom stands
  Move stands back into the cleanroom

## Slide 14: Phase 1A: Beam Line Assembly
Install all Downstream Magnetic Shield Endcaps
  Must have cleanroom posts removed for this step
  Upstream endcaps are part of tuner installation
RRCAT-502 Assembly

## Slide 15: Phase 1A: Beam Line Assembly
Install B92 Lever Tuners
  Upstream endcaps are part of tuner installation
RRCAT-502 Assembly

## Slide 16: Phase 1A: Beam Line Assembly
Install B90 Lever Tuners
  Upstream endcaps are part of tuner installation
AES-007 Assembly

## Slide 17: Phase 1A: Beam Line Assembly
Weld Cooldown Line
  Line fabricated at FNAL, pressure tested, and leak checked before installation
  This activity completes Phase 1A assembly
Offsets in CD Line to Compensate for Pipe Shrinkage

## Slide 18: Phase 1B: Strongback Fitment and Assembly
Reference Drawing: F10152150
Traveler: 464613
Main Tasks
  Set up vacuum vessel
    Install global magnetic shields - complete
  Assemble strongback on rail - complete
  Strongback fitment in vessel – in progress
  Install strongback magnetic shields and MLI
  Install G-11 posts
  Install lower thermal shield weldment
  Install 5K line and cavity supports
  Demagnetize strongback assembly – not required

## Slide 19: Phase 1B: Strongback Fitment and Assembly
Setup Vacuum Vessel
  Permeability measurements on bare vessel
  Demag vacuum vessel
Before and after demag coil installation

## Slide 20: Phase 1B: Strongback Fitment and Assembly
Setup Vacuum Vessel
  Install global magnetic shields

## Slide 21: Phase 1B: Strongback Fitment and Assembly
Setup Vacuum Vessel
  Install global magnetic shields

## Slide 22: Phase 1B: Strongback Fitment and Assembly
Setup Vacuum Vessel
  Permeability measurements

## Slide 23: Phase 1B: Strongback Fitment and Assembly
Set and Capture Alignment Data for Strongback Supports
  Set pin height to final height and measure bottom of pins via laser tracker

## Slide 24: Phase 1B: Strongback Fitment and Assembly
Set and Capture Alignment Data for Strongback Supports
  Set pin height to final height and measure bottom of pins via laser tracker
Data used for final coldmass alignment inside the vacuum vessel

## Slide 25: Phase 1B: Strongback Fitment and Assembly
Assemble Strongback on Rail
  Six sections comprise strongback, pinned and bolted together
  Remove the 14 supports from vacuum vessel and mount to rail supports
Upstream End Must be Assembled First

## Slide 26: Phase 1B: Strongback Fitment and Assembly
Assemble Strongback on Rail
  Six sections comprise strongback, pinned and bolted

## Slide 27: Phase 1B: Strongback Fitment and Assembly
Straddle Vacuum Vessel over Rails
  Align and level vacuum vessel over rails to except strongback for fitment test
  Vessel resting on eight 6 ton leveling jacks
    Four used for leveling
    Four used for additional stability

## Slide 28: Phase 1B: Strongback Fitment and Assembly
Strongback fitment test/alignment
  Insert strongback and transfer loads to support pins

## Slide 29: Phase 1B: Strongback Fitment and Assembly
Strongback fitment test/alignment
  Set up “dummy” endplates and align positions to capture “real” plates

## Slide 30: Phase 1B: Strongback Fitment and Assembly
Strongback removed from vacuum vessel
  Pin the conical plate to the strongback

## Slide 31: Look Ahead
Complete final Phase 1B steps
  Install strongback magnetic shields and MLI blanket
  Install G-11 posts
  Install lower thermal shields
  Install 5K line and cavity supports
  Close Phase 1B
Prepare for Phase 1C assembly
  Strongback and Beamline Merger

## Slide 32: Misc. Work
Thermal Shield Assembly

## Slide 33: Misc. Work
Titanium Cavity Support Fabrication

## Slide 34: Misc. Work
Titanium Cavity Support Fabrication
Completed Cavity Supports

## Slide 35
Thank you!