## Slide 1
STFC HB650 cavity and Nb procurement
Anna Shabalina
2nd PIP-II Technical workshop
13 July, 2022

## Slide 2: HB650 Cavity scope
Procurement of the production Niobium
2 pre-series cavities: Vendor validation
  Bare cavities will be tested at FNAL
  Tested at STFC after jacketing
18 series cavities
  Tested jacketed at STFC one cavity at a time
  Cryomodule integration at STFC
Supporting high Qo
  Fast CoolDown
  Enhanced magnetic hygiene
Documentation

## Slide 3: Production Niobium procurement
Market survey
  Tokyo Denkai (Japan) – some technical limitations
  ATI Metals (USA) – at full capacity
  OTIC Ningxia (China) – some technical limitations
  Heraeus (Germany) – not on the market
Manufacturing specifications adjustments
  Hardness
  Elongation
  Strain Hardening Coefficient
Tender exercise
  OTIC – cheap and fast
  ATI – cheap and slow
  TD – expensive and very slow
3

## Slide 4
Surface quality issues
  Identified during Eddy Current Scanning (ECS) at DESY late September 2021
At least 10-30 m by 40-70 m surface defects on all sheets (225 disks)
  Uniformly distributed on the entire surface
  Definition of a defect caused some friction with the vendor
Widespread problem
  All orders since May 2021 were affected, including PIP-II and SHINE projects
  At least 500 sheets checked by November’21
Production Niobium Procurement

## Slide 5: Production Niobium procurement
Resolution hindered
  Miscommunication
  Travel restrictions
  Proprietary information
  Lack of transparency
Proposed repair methods verified by ECS at DESY
  Samples of PIP-II and SHINE material
  Various etching and polishing combinations
  Acceptable recipe found ~January 2022
  Final adjustments made in May 2022

## Slide 6: Production Niobium procurement
Current status: 45 disks tested, 35 accepted.
  90% success rate for reworked sheets
  75% success rate for the first batch of new disks
  Only 3/187 of reworked sheets are expected to be unrecoverable
  First batch of 88 reworked disks arrived at DESY last week
6
Surface investigation | 35 new disks | 10 reworked disks
Areas inspected by 3D microscopy | 91 | 3
Average | 2.6 | 0.3
Element analysis performed | 4 | -
Root cause
  Excessive BCP of a dirty surface

## Slide 7: Production Niobium: QC
Extra measures
3D scans of randomly selected areas on both sides
Local thickness measurements after local grinding
Improvements at OTIC
New 3D microscope being commissioned
New ultrasonic thickness measurement device

## Slide 8: Production Niobium: Final recipe
Surface treatment process | Process before 2021 | 35 new disks | Remaining new disks
Polishing with 180 mesh abrasive belt | 50μm | 50μm | 50μm
240 mesh | 25μm | 25μm | 25μm
320 mesh | 15μm | 15μm | 15μm
BCP | 10μm | 25μm | 10μm
400 mesh |  | 10μm | 10μm
BCP |  | 10μm | 10μm
Surface treatment process | 10 reworked disks | Remaining disks
Polishing with 400 mesh abrasive belt | 15μm | 25μm
BCP | 10μm | 10μm

## Slide 9
Production Niobium Procurement

## Slide 10
HB650 cavity procurement

## Slide 11: HB650 cavity procurement
Market survey
  Specifications overview
  Sets expectations and “brackets”
  Requests vendors input
Manufacturing specifications
  Highlight Key Characteristics
  Incorporated information and lessons learned from other projects (ESS, LCLS-II, SNS PPU, CEBAF upgrades)
  Use the LB650, SSR1 and HB650 prototype experience
  Award questionnaire designed to draw out the level of vendor’s interest in the project
Cavity manufacturing
  FNAL experts will be involved with the STFC’s chosen vendor from the start
  QC, MIP, and NCR processes will be developed in close collaboration with the vendor
11
September 29, 2021

## Slide 12: HB650 Cavity: QA/QC
Technical Specifications and Vendor Qualification: APQP-inspired.
  Early engagement: setting QC expectations
  Product and process Key Characteristics
  Process flow (PF) development
  Control plans (CP) development
  Reaction plans development
Pre-series cavities
  Very detailed and involved QC
  Fine-tuning PF and CP
  Verifying recipes and techniques
Series cavities
  Benefit from vendor qualification activities
  Minimize start/stop of the production
  Optimize data review
EXAMPLE
APQP – Advanced Product Quality Planning
12
Fermilab
input

## Slide 13
Cavity procurement strategy
Specifications development
  APQP approach
  Key characteristics
  The “what”, not the “how”
  Document readability and flow
Award questionnaire
  The “how”
  Strategy depends on the potential bidders
  No generic boiler plate submissions – prove they’ve read my requirements.
  “Show and tell”: bind them to a commitment to meet the specs with a yes/no question, ask to prove it in the next one
  Page limit for answers – it is harder to summarize, vendors need to think of what’s important

## Slide 14
Cavity procurement strategy
Confirm your ability to meet the specs – flexibility for the vendor to suggest changes and relax some requirements, freedom for me to reject and still be sure they can make it
Provide a statement outlining the technical challenges of this project, and opportunities for improvement – vendors need to analyze the specs and show me they know which parameters are critical
Can you meet the schedule – pre-series focuses on quality, series focuses on the delivery rate, vendors need to prove it with a schedule management plan
Capacity for performing work – do they have the machinery, how busy is the plant going to be, equipment redundancy
Necessary skillset – staff availability through the life of the project, understanding of the necessary skillset, plan for unexpected loss of expertise
Quality Assurance and Control plan example and statement – requires distilling the QA/QC manual to a couple of lines per topic from our specs, assesses vendor’s attention to details

## Slide 15
Cavity procurement strategy: current status
Now
  Tender is closed
  Winner identified
  Award letter will going out today
Next
  Work out pricing schedule
  Refine delivery schedule
  Review proposed design changes
  Work with the vendor to develop QC tools
Expecting Manufacturing Readiness Review in September

## Slide 16: Thank you

## Slide 17: Test Facilities
Dose Rate & Energy Spectrum Detectors
Dose Rate Detectors
Dose Rate & Energy Spectrum Detectors
Dose Rate & Energy Spectrum Detectors
Dose Rate Detectors
Dose Rate Detectors
STFC Test Stand
DESY Test Stand
Wall thickness 10-25mm
End of cavity to outer wall
  Left (Coupler) 19.1cm
  Right (Pick-up) 24.8cm
Coupler (left) detector ~ 25 cm
Pick-up (right) detector ~30 cm
Distance from end of cavity to Lid about 1740mm
Distance from end of cavity to radiation detector ~2m
Several cm of metal for lid, radiation baffles etc
DESY measurements from the top detector
*Installed January 2021

## Slide 18: VTS configuration (FNAL)
Blank flange FP side
Connector flange coupler side
Burst disk
(1619)

## Slide 19
STFC Design Change: Two-phase Pipe Interface
19
September 29, 2021
Background
  STFC’s vertical test setup requires a flanged connection to the 2-phase pipe
  Max radius to the Helium Tee is 572 mm
  STFC’s and leading cavity suppliers HPR can accommodate up to 325 mm radius
Design optimization
  Weld the Tee after the cold test
  Simplify joint
  Fit into the HPR
  Minimize handling after test
Split CF flange
Longer transition joint