## Slide 1: FI Status Report
Mine Altunay
FI Technical Lead
August 25, 2022

## Slide 2: Current Status
Will report on the following items in detail:
Vault in production.
WLCG Timeline and its impact on us.
  VOMS Support
Jobsub-lite status and testing.
Managed tokens
Phase 2 issues
  Ferry
  DUNE VOMS
  FTS and Rucio Timeline

## Slide 3: Moving Vault to Production
Have been working with the Authentication Team.
3 Vault instances, Dev, Test and Prod have already been installed and running by the Authentication group
The Dev and Test Vault instances can obtain tokens without a problem and are available for our users.
Prod Vault instance will be completed very soon, too.
Working on putting the Vault in ServiceNow and creating an SLA document.

## Slide 4: WLCG Timeline
Some changes made to the timeline.
Schedule is pushed back to 2026.
  Expect to finish all work by 2025
  Become certificate optional by 2026
  Some WLCG members think even this is an ambitious timeline
  FTS and Rucio developments are planned to be done by 2024. Will discuss this more
WLCG current focus is on retiring VOMS-Admin and transitioning to IAM.
  This has no impact on us since we do not use VOMS-Admin and replaced it with Ferry.
However, we are concerned about continuing support for VOMS
  After CERN’s switch to IAM, we are concerned that support for VOMS may be neglected.
  I brought up our concern at last WLCG meeting.
  WLCG and VOMS developers agree that support of VOMS should go beyond 2024 until certificates become truly optional.
  Will continue to bring this up at WLCG meetings.

## Slide 5: Jobsub-lite Status
Development work continues along with figuring out deployment issues.
One standing issue is to be able to renew the tokens that are sent with the jobs.
Jobsub-lite is integrated with the Vault servers for obtaining tokens.
Testing with experiments is well underway:
  Mu2e: Waiting for the storage token scope issue to be addressed.
  Dune: Testing production workflows with POMS.
  Sbnd: Basic test jobs being run. No complete workflows.
  Uboone: Starting to test basic jobs.

## Slide 6: Managed tokens
Proof of concept is working well.
Pushing Vault tokens to all Mu2e and Dune interactive nodes that are currently receiving managed proxies.

## Slide 7: FTS and Rucio Timeline
If we transition to tokens before 2024, which is our current plan, this means FTS and Rucio will still have to work with certificates because WLCG plans FTS and Rucio to complete their development work by 2024.
This will have an impact on Dune.
Our current plan is to use certificates and tokens side by side for each job and data access such that FTS and Rucio continues to work.
  This is a major test for us.
  We will schedule this for after our Jobsub-lite and Vault testing ends.
  Without success in this area, we will not transition to tokens.
  Even with successful results, we are cautious if this will bring more complexity to Dune workflows.
  I will meet with Dune computing to explain our current plans.

## Slide 8: Phase 2 Issues
As we get closer to finishing our testing and start transitioning to tokens, we also start planning for our project Phase 2.
Phase 2: We start including international users in our federated access mode.
  As a reminder Phase 1 includes only users with Fermilab accounts.
  In Phase 2, we will have international users who will not be required to have Fermilab accounts.
Ferry:
  Ferry has been designed for internal Fermilab users who have computing accounts.
  Earlier when we designed Ferry, we discussed this with senior management in detail. The decision was that Ferry was for Fermilab account holders only.
  At the time, the thinking was that all Dune users would have to obtain Fermilab accounts.
  Now that we are going the federated access route, we want to revisit some of these points.

## Slide 9: Phase 2 – Ferry and DUNE VOMS
Should Ferry continue to be designed for only Fermilab users?
If this is the case, how should we treat Dune users?
  VOMS servers are populated from Ferry. We got rid of VOMS-Admin and replaced it with Ferry.
  This is not an issue for internal Fermilab VOs, but this is a problem for international VOs.
  Do we still expect Dune users to get Fermilab accounts?
If we need to change Ferry, this is significant design and implementation work
  Ferry gets information from userdb. We will need to find other sources to get international users data, process it and insert into Ferry.
Ferry is also designed based on certificates. Each user is identified by their certificate DN. We will have to change this as certificates go away and replace with token subject names.

## Slide 10: Phase 2– Policy work
We will start seeking guidance from the chief security officer and the security team on creating and enforcing policies for our Phase 2.
Topics such as:
  Should we continue to treat our international grid users in the same manner as we are currently doing with certificates?
  Switching to tokens from certificate is just a technical change, but will it also bring any changes in policy?
  Do we have any new lab policies or requirements?