## Slide 1: OSG PKI Transition: Status and Next Steps (and Lessons Learned)
Von Welch
OSG PKI Transition Lead
Indiana University Center for Applied Cybersecurity Research

## Slide 2: Key Message
DOE Grids CA stops issuing new certificates March 23rd, 2013.
(in 10 days)
VOs should already have:
1) Enrolled with new OSG PKI
2) Be ready to handle new user identities
3) Updated documentation and processes

## Slide 3: Project Overview and Goals
DOE/ESnet has announced shutdown of DOE Grids CA.
OSG is transitioning that CA functionality to an OSG service.
In coordination with ESnet, project goal is to manage a smooth transition of PKI functionality to the new OSG service.

## Slide 4: Community-wide Responsibilities
Previously ESnet and now OSG, will set policy and process, and provide mechanism to issue certificates.
VO and RPs continue to vet their user communities and authorize based on certificates.

## Slide 5: What VOs need to do…
Enroll RAs with OSG PKI
  https://oim.grid.iu.edu/oim/vo
Be prepared to handle changing user identities (DNs)
Update documentation and internal processes
https://www.opensciencegrid.org/bin/view/Security/PKIDocumentationIndex

## Slide 6: Resources
OSG PKI Service: idmanager.opensciencegrid.org
Manuals, how-tos, experiences:
  https://www.opensciencegrid.org/bin/view/Security/PKIDocumentationIndex
Tomorrow:
  9:45am: Security for administrators, RA, GA IT-159
    Also: https://twiki.grid.iu.edu/bin/view/Security/OSGPKITraining
  11:00am: Ask the Experts IT-152

## Slide 7: Status
PKI is in operations –
  39 VOs registered
  Issued 300+ user certificates
  Handled 350+ host requests (some for up to 50 certificates)
Web and command-line clients
We are listening and learning what’s missing/wrong in new PKI.

## Slide 8: Next Steps
Expect more missing features exposed as 23rd approaches and passes.
OSG PKI works at strong level (IGTF) to enable collaboration with EU and others. There is room for other solutions (e.g. CILogon) for those with lower security needs.

## Slide 9: Lessons Learned
Not going to cover today, will include in slides.

## Slide 10: Contributors to the Transition
Mine Altunay, Jim Basney, Tim Cartwright, Alain Deximo, Jeremy Fischer, Soichi Hayashi, John Hover, Viplav Khadke, Christiane A. Ludescher-Furth, Ruth Pordes, Rohan Mathure, Robert Quick, Alain Roy, Chander Sehgal, Mátyás Selmeci, Anthony Tiradani, and John Volmer
Also thanks to Dhiva Muruganantham and Lauren Rotman of ESnet

## Slide 11: Conclusion
DOE Grids CA stops issuing new certificates March 23rd, 2013.
(in 10 days)
VOs should already have:
1) Enrolled with new OSG PKI
2) Be ready to handle new user identities
3) Updated documentation and processes

## Slide 12: Lessons Learned

## Slide 13: Project Phases
Project was divided into Pilot, Planning, Development, Deployment and Transition Phases
Allowed for good checkpoints on project
Perhaps a couple phases too many?
  Hard to get management engaged to review five times.
One phase too short at one month

## Slide 14: Underestimated VO role in transition
VO is responsible for both for vetting when users enroll in PKI and consuming certificates when used.
We should have had focused effort on VO impact and communication of that from the project start.
In particular, FNAL was central to many VOs.

## Slide 15: VO Engagement Critical
Communication via twiki, weekly calls, email list.
Worked well with those that engaged.
Needed more effort to engage with those that didn’t engage.
  Both VOs and other OSG project teams.
  Not enough budgeted effort to communication.

## Slide 16: Collaboration with ESnet was Critical
Coordinated communications between two organizations.
Access to historical data about PKI usage.
Deep insights as to how the PKI was used.

## Slide 17: We don’t know how OSG uses PKI…
DOE Grids CA was around for 10+ years with web and HTTP/REST interfaces
Plethora of usage patterns, client tools
We still don’t know how PKI is used by all parties.

## Slide 18: Use of Browser PKI Functionality
DOE Grids PKI used the browser heavily to generate/renew keys.
This caused lots of browser version dependencies and issues
Following CILogon, OSG PKI implemented key generation in OIM. Seems to have worked out well.

## Slide 19: Everything is a VO?
Treating sites (Argonne, ORNL, etc.) as VOs seems to be working well.
We initially thought of host certificates requests as being an issue of domain (e.g. uiuc.edu) and not VO. This was probably wrong, and these requests should have been VO-centric.

## Slide 20: DigiCert (Commercial vendor) Relationship
Nomenclature was different and took time to work through.
Policy agreements were time consuming.
Contract was complicated.
Should have budgeted more time for all the above.

## Slide 21: Separation of Web (HTTPS) and Grid Certificates
By focusing our relationship with DigiCert on Grid certificates and using a separate CA that doesn’t issue certificates trusted by browser, we made life much easier for all.
  Only have to meet IGTF policies and not CAB Forum policies – much lower bar.
Downside is OSG PKI certificates are not good web server certificates.

## Slide 22: Bulk Request is a very special case
Bulk request of host certificates is not something PKIs outside of the Grid support.
Was a source of a lot of interaction issues with DigiCert.
Lots of tricky details.
Should have scheduled more time and effort for this specific case.

## Slide 23: Audit
We are now undergoing our first self-audit with DigiCert.
  This is a normal annual event.
Audit is based on policy.
Questions indicate some different interpretations of policy.
  Will be worked out.
Having a test audit prior to implementation would have been useful.

## Slide 24: If I could budget over…
I would add effort for:
Use case documentation & requirements
QA/Testing
Documentation
Communication/VO engagement
Policy/legal/contracts

## Slide 25: CLI Client Development
During development of CLI clients, a release often and early approach would have been nice.
  Community wants RPMs not head-of-SVN.
OSG doesn’t do software development, they do integration. Have limited release, testing, etc.
Should have established own SW processes as independent team.
  And then wound down after transition.

## Slide 26: Panda/Gridsite issue
When ATLAS started testing, discovered show-stopping problem with Panda.
Turns out Panda is not represented in the OSG test bed (ITB)
Gridsite (a Panda component) is known to be picky about PKI implementation.
Should have been hit early and often with new PKI.

## Slide 27: Using a Commercial CA
Use of a commercial CA for a backend is a new model and was somewhat controversial.
I still have no doubt it was the right choice. OSG deploying and operating a CA with all the IGTF requirements would easily have been more expensive.

## Slide 28: Lessons Learned Caveat
It’s not over yet, we certainly have more lessons to learn.

## Slide 29: OSG PKI Reports
Pilot Phase
  https://osg-docdb.opensciencegrid.org:440/cgi-bin/ShowDocument?docid=1097
Planning Phase
  https://osg-docdb.opensciencegrid.org:440/cgi-bin/ShowDocument?docid=1120
Development and Deployment Phases
  http://osg-docdb.opensciencegrid.org/cgi-bin/ShowDocument?docid=1145
Transition Phase
  https://osg-docdb.opensciencegrid.org:440/cgi-bin/ShowDocument?docid=1148