## Slide 1
Main Injector 2022 Shutdown Status
M. Murphy/D. Morris
9 o’clock Meeting
September 2nd, 2022

## Slide 2
Tunnel Work
9/1/2022
MI Department Meeting | D. Morris
2
Main Injector jobs: 230
Recycler Jobs: 22
MI-8 Line: 20
RF maintenance continues
MI RF cavity #14 and #15 have been removed
from tunnel for water rework.
#14 should be ready for installation in two
weeks.
Cavity #15 will be reworked and become our
spare cavity.

## Slide 3
Tunnel Work
9/1/2022
MI Department Meeting | D. Morris
3
Ops with AD/MSD: Worked on LCW white hose replacement for the remaining
2/3rds of the ring. Completed MI-30 (from 314 on) and MI40.

## Slide 4
Tunnel Work
9/1/2022
MI Department Meeting | D. Morris
4
SEY sample change out.
Issue with sample retrieval system
Retrieval system required maintenance.
Samples have been changed out.
Retrieval system is fully functional.
SEY station is under vacuum.
Scheduled for another SEY data run prior to startup

## Slide 5
Tunnel Work
9/1/2022
MI Department Meeting | D. Morris
5
Recycler 232 aperture improvement underway:
Final alignment completed.
Installation of remaining vacuum beam pipe and weld preparation in progress.
Welding scheduled for next Tuesday.

## Slide 6
Schedule
9/1/2022
MI Department Meeting | D. Morris
6
Power outages: (https://www-bd.fnal.gov/ops/calendar/)
September 6th: Kautz Road switched to Master Sub back-feed
Switch back is scheduled for the morning of the 12th
MI-8 Line:
Sept. 19th : Re-Core to operational keys
Sept. 20th : Search and Secure and SS Testing
Sept. 26th : CDC Testing
MI/RR:
Sept. 21st : Re-Core to operational keys
Sept. 22nd : Search and Secure
Sept. 23rd : Safety System Testing
Sept. 27th : CDC Test
Sept. 28th : Ramp/Studies

## Slide 7
FESS Excavations
9/1/2022
MI Department Meeting | D. Morris
7
MI-20 sump discharge
Being abandoned/
Being replaced.
MI-62 Culvert
MI-62 sump discharge
Sink hole
Kautz Rd/NuMI site
riser sink hole
MI-50 Culvert
Sink hole behind MI-50
Pond inlet for MI-52
MI-60 pond inlet
Kautz Rd Culvert