## Slide 1: MQXFA13 Coil Acceptance Review Introduction & Charge
Giorgio Ambrosio
Magnets L2
U.S. HL-LHC Accelerator Upgrade Project
MQXFA13 Coil Acceptance Review
November 2, 2022

## Slide 2
Committee
Steve Gourlay (chairperson), LBNL
Arup Ghosh, BNL retired
Susana Izquierdo Bermudez, CERN
Date and Time
November 2, 2022.
Start time is 7/9/10/15 (LBNL/FNAL/BNL-FSU/CERN)
Location/Connection
Video-link by Zoom, info by email.
Link to agenda with talks and other documents
https://indico.fnal.gov/event/56491/

## Slide 3: Review Goals
The HL-LHC AUP project is planning to start assembly of MQXFA13. This is the 6th series low-beta quadrupole magnet (MQXFA) for the Inner Triplet of the High Luminosity LHC. If MQXFA13 meets MQXFA requirements [1] it will be used in a Q1/Q3 cryo-assembly to be installed in the HL-LHC.
For MQXFA13 assembly AUP is planning to use QXFA coils: 139, 141, 227 and 229. Coil 218 is planned for future use in MQXFA07b and is a spare coil for MQXFA12. Coil 218 was reviewed during the Coils Acceptance Review for MQXFA07b and MQXFA11 [2]. Another spare coil is coil 220. Coil 220 was reviewed during the MQXFA10 Coils Acceptance Review [3] and during the MQXFA12 Coils Acceptance Review [4].
Conductor and series coil specifications are presented in [5-9]. Discrepancy or Non-conformity Reports are generated whenever a component does not meet specifications.
The reviewers are requested to review discrepancies and non-conformities in strands, cables and coils, for the following coils: 139 (cable P43OL1164), 141 (cable P43OL1167), 227 (cable P43OL1156), and 229 (cable P43OL1161).

## Slide 4: References
MQXFA Functional Requirements Specification, US-HiLumi-doc-36
Coils Acceptance Review for MQXFA07b and MQXFA11, US-HiLumi-doc-4224.
MQXFA10 Coils Acceptance Review, US-HiLumi-doc-4186
MQXFA12 Coils Acceptance Review, US-HiLumi-doc-4321
Specification for Quadrupole Magnet Conductor, US-HiLumi-doc-40
Cable Specification, US-HiLumi-doc-74
Quadrupole Magnet Cable Insulation, US-HiLumi-doc-75
QXFA Series Coil Production Specification, US-HiLumi-doc-2986
QXFA Series Coil Fabrication Electrical QC plan, US-HiLumi-doc-521
All docs are on the Review Indico page
Coil CMM measurements for acceptance are performed at LBNL
Coil CMM at BNL and FNAL are used for feedback to L3s

## Slide 5: CHARGE Questions
The committee is requested to answer the following questions:
Have Discrepancies and Non-conformities been adequately documented and processed?
If there are critical Discrepancies/Non-conformities, have they been adequately documented and processed?
Did the L3s properly identified critical Discrepancies/Non-conformities?
Is there any coil that you recommend not to use in MQXFA13?
Do you have any other comment or recommendation regarding these coils and their conductor for allowing MQXFA13 to meet MQXFA requirements [1]?

## Slide 6: Critical DR/NCR:
Critical nonconformance: a nonconformance which meets at least one of the following:
  affects form, fit, or function in the as-found condition
  involves damage, or suspected damage, to the coil conductor
  is likely to trigger yellow or red schedule or cost variance reporting thresholds
  meets the requirements of “Moderate” or higher per the CERN Impact Matrix (for collaborations) in EDMS 1863763
Handling of Discrepancies and Nonconformances
US-HiLumi-doc-2484

## Slide 7: Coil Ordering
The use of coils with different conductor properties (RRR and Cu/NCu) may increase Coil-Ground voltages
Since CLIQ is introducing an asymmetric behavior, coil ordering may be used to compensate for different conductor properties
Therefore, starting from MQXFA03, AUP is checking peak Coil-Ground voltages for any possible coil ordering
  All options with peak voltage above spec will be forbidden
  Voltages of other options will be taken into account together with other data, when deciding coil ordering
 talk “Coil Ordering based on Conductor Properties”

## Slide 8: Traveler status on MTF
We added this topic following a request from Susana

## Slide 9: Past Recommendations
Recommendation from MQXFA12 Coil Acceptance Review:
“Re-measure coil 136 at LBNL and cross-check again with the FNAL measurements. The committee further suggests to make measurement cross-checks a standard procedure.
Coil 136 was re-measured. Plans for cross-checks are under discussion.

## Slide 10: Schedule
Today:
  Talks
  Q&A
Following days:
  Closed session(s)
  Possibly Q&A by email
Report by email or Zoom mtg in ~2 weeks

## Slide 11: MQXFA Status
AUP is close to 50% MQXFA magnet fabrication
6 out 8 magnets met vertical test requirements
MQXFA07/08 “smoking gun” was found
  Mechanism is understood
  Covid restrictions and lockdown contributed to the degradation mechanism
  Design change (larger gaps) and Specification revision (minimum gaps spec.) are going to prevent reoccurrence in future magnets
  MQXFA10 & MQXFA11 demonstrated that this issue is over
MQXFA05 demonstrated Endurance
MQXFA11 demonstrated Resilience