## Slide 1: Magnets 302.2.03 Cable Fabrication
Ian Pong – LBNL (L3 and CAM)
Elizabeth Lee – LBNL (L3 deputy)
Mike Naus – LBNL (CAM deputy)
HL-LHC AUP Rebaseline DOE Rev. – Dec. 13th–15th 2022

## Slide 2: General Outline
Scope, Interfaces, Dependencies & Team
Achievements since CD-3
Contingency Consumption
COVID and Abnormal Escalation Impacts
Schedule
Cost and Schedule Performance
Estimate at Completion
QA/QC
Risks
ES&H
Summary

## Slide 3: Functional Requirement Specifications
ID | Description
R-T-03 | The MQXFA magnet must be capable of operating at steady state providing an integrated gradient of 556.9 T in superfluid helium at (HeII) bath at 1.3 bar and at a temperature of 1.9 K
R-T-16 | The MQXFA magnet coils and quench protection heaters shall pass the hi-pot tests specified in Table 2.
Specification for Conductor (US-HiLumi-doc-40)
Specification for Cable (US-HiLumi-doc-74)
  Define performance and length of conductor
  Address FRS R-T-03
Specification for Cable Insulation (US-HiLumi-doc-75)
  Defines glass fiber braiding for cable insulation
  Addresses R-T-16
FRS (US-HiLumi-doc-36)
Charges #2, #9

## Slide 4: WBS 302.2.03: Scope
Hitherto 96 AUP QXFA cables completed, 10 failed/on hold cable
US-HiLumi-doc-39
Charges #2, #9

## Slide 5: WBS 302.2.03: Scope
Scope: fabricate 109 under AUP
Assumed yield 90%  98 delivered AUP cables
4 from LARP  total cables for coils = 102
Scope includes:
  Fabricate bare cables at LBNL
  Insulation (braiding)
  Extracted strand RRR QC
This task is near completion: its EV/BAC is >86% as of September 31st EVMS data.
Charges #2, #9

## Slide 6: WBS 302.2.03: Interfaces
US-HiLumi-doc-219
Not changed since CD-3
Charge #9

## Slide 7: WBS 302.2.03: Team
302.2
MQXFA Magnets Fabrication
L2: G. Ambrosio
(M. Baldini, P. Ferracin)
302.2.01
Magnets Integration and Coordination
L3/CAM: G. Ambrosio
(M. Baldini)
302.2.04
Coil Parts, Materials and Tooling Procurement
L3/CAM: M. Yu (A. Nobrega)
302.2.05
Coil Fabrication at FNAL
L3/CAM: A. Nobrega (M. Yu)
302.2.06
Coil Fabrication at BNL
L3/CAM: J. Schmalzle
(M. Anerella)
302.2.07
Structure Fabrication and Magnets Assembly
L3/CAM: S. Prestemon
(D. Cheng)
302.2.03
Cable Fabrication
L3/CAM: I. Pong (E. Lee)
CAM Dep: I. Pong (M. Naus)
302.2.02
Strand Procurement
L3: L. Cooley (V. Lombardo)
CAM: V. Lombardo
Control Account
US HL-LHC Accelerator Upgrade Project: 302.2 MQXFA Magnets Fabrication
Core Members:
Ian Pong
Elizabeth Lee (new L3 deputy)
Mike Naus (new CAM deputy)
Andy Lin
Al Baskys (new research scientist)
Assisting Members:
Li Wang (cryo)
Hugh Higley (Retiree)
Dan Dietderich (Retiree)
US-HiLumi-doc-104
Charge #4

## Slide 8: WBS 302.2.03: Achievements since CD-3b
CD-3b approval for full production
CDR, PDR, FDR, ICDR, PRR all completed
No Action Items from previous Reviews
Yield in line with assumption
>86% complete (as of September 2022 by EV)
Charges #5, #11
We have been making technical progress despite all the challenges

## Slide 9: WBS 302.2.03: WBS Contingency Consumption by COVID Causes
Limited COVID impact on this task (total $400k). Major items:
  Efficiencies remained high: 87.5% for 302.2.03.1040, 100% for other activities ($257k)
  COVID Attribution portion of Addition of 5 Cables ($94k)
Charge #1

## Slide 10: WBS 302.2.03: COVID, Abnormal Escalation, and Other Impacts
Limited COVID impact (total $400k). Major items:
  Inefficiencies ($257k)
  COVID Attribution portion of Addition of 5 Cables ($94k)
  Lockdown in 2020 LOE adjustment ($31k)
  A current period BCR #267 ($11k), due to COVID sickness and close contact isolation requirements
No Abnormal Escalation attributable
Other BCR / Adjustment (total $417k).
Charge #1

## Slide 11: WBS 302.2.03: Schedule
Charge #2
302.2.03 is not on but will be close to the critical path in Jan 2023 due to staff shortage half a year ago

## Slide 12: WBS 302.2.03: Cost and Schedule Performance
Charges #2, 7
Control Account cost and schedule historical performance
is reasonable and has been stable during COVID;
variances well understood and documented
Deputy resigned
BCR #120
(CA PSPS)
New members joined
COVID
COVID
Cumulative to Date |  |  |  |  |  |  |  | 
Budget | Earned | Actuals | SV | SV (%) | CV | CV (%) | SPI | CPI
$ 5,655,479 | $ 5,322,748 | $ 5,243,512 | $ (322,731) | -5.9% | $ 79,236 | 1.5% | 0.94 | 1.02
BCR #145
(ETC 2020)

## Slide 13: WBS 302.2.03: Estimate at Completion
Charges #2, 7
  CPI = 1.02  Positive VAC, AC < EV
  EV/BAC >86% -- nearly complete
  SPI < 1  EV < PV
At Complete |  |  |  |  |  | 
BAC | EAC | VAC | % Spent | EV/BAC | PV/BAC | AC/BAC
$ 6,133,110 | $ 6,078,207 | $ 54,904 | 86.3% | 86.8% | 92.2% | 85.5%

## Slide 14: WBS 302.2.03: QA/QC
MIP approved by CERN (EDMS 1866230)
AUP Quality Plan (Doc 903)
Three failed cables at time of manufacture
  Wire crossover (DR 11712)
  Mid-run bay brake activation (Traveler 464234)
  Roller bearing failure (Traveler 464234)
Six impacted cables at time of coil winding
  3 on-hold cables (DRs 12321,12323, 12799, 12822)
  3 failures (DRs 12194, 12412, 12413, 12414, 12863, 12867)
  Related to wire excess lubricant causing mechanical instability during coil winding. See also: US-HiLumi Docs. 4172, 4318
One cable on hold due to braiding issue

## Slide 15: WBS 302.2.03: Risks
Charge #3
Three threats
One opportunity
One relevant project-wide threat
Risk-ID | Title | Risk Rank
RT-302-2-03-001* | Number of cables fails to meet specifications | Medium
RT-302-2-03-004* | Failure of insulation contractor to deliver on time | Low
RT-302-2-03-003 | Significant breakdown of cabling machine | Low
Opportunity-ID | Title | Risk Rank
RO-302-2-03-001 | Mapping optimization allows leftover from wire spools to be converted to a cable UL | Medium
Risk-ID | Title | Risk Rank
RT-302-1-005 | Need to replace key personnel | Low
* These risks have a separate COVID component in the risk register to account for additional probability/impact due to COVID pandemic.

## Slide 16: WBS 302.2.03: ES&H
Regular meetings at LBNL, minutes & roster kept in Google Drive with access control
WPC, Procedures, HAR (§9.1), etc. are in place
No injury-causing accident for >25,000 labor-hr!
Fire sprinkler leak in 2019
  Causal Analysis Report made by the LBNL PIMD, EHS, and IA&I.
COVID control effective: no onsite transmission
Lab protocols and guidelines continually updated per DOE and CDC guidance
Charge #10

## Slide 17: WBS 302.2.03: Summary
302.2.03 is nearing completion (EV >86%)
Technical work is proceeding according to the baseline plan
Cost is under control
Schedule performance has been stable since 2020
Hiring and retention have been the biggest challenge
Quality, Risk, and ES&H are well managed

## Slide 18: Back up slides

## Slide 19: WBS 302.2.03: WBS Contingency Consumption by COVID Causes

## Slide 20: WBS 302.2.03: WBS Contingency Consumption by Other Causes

## Slide 21: 302.2.03 Resource Type Breakdown
77% Labor, 23% M&S
M&S Includes contractors (braiding vendor), travel, shipment, etc.
Charge #4

## Slide 22: 302.2.03 Estimate Quality
Charge #4

## Slide 23: 302.2.03 FTE Breakdown
Charge #4

## Slide 24: 302.2.03 Cost Performance Report
BAC = $6.133M
Cumulative SPI = 0.94, CPI = 1.02
Charge #4