## Slide 1: Magnets 302.2.07 - Structure Fabrications and Magnet Assembly at LBNL
Soren Prestemon – LBNL (L3/CAM)
Dan Cheng– LBNL (Deputy L3/CAM)
HL-LHC AUP Rebaseline DOE Rev. – Dec. 13th–15th 2022

## Slide 2: General Outline
Scope, Interfaces, Dependencies & Team
Achievements since CD-3
Contingency Consumption
COVID and Abnormal Escalation Impacts
Procurement Status
Schedule
Cost and Schedule Performance & VAR Reports
Estimate at Completion
Risks
QA/QC
ES&H
Summary

## Slide 3: WBS 302.2.07: Scope and Interfaces
Scope of Work
Re-assemble magnet prototype MQXFAP-1b, fabricate 5 pre-series magnets (from MQXFA-03 to MQXFA-07), and fabricate 20 MQXFA series production magnets. Scope includes:
  Parts procurement for 21 magnet structures (shell, Yoke, masters, pads, collars, axial support components, keys, strain gauges and wires)
  26 magnet assemblies (1 prototype re-assembly, 5 pre-series, 16 series production, and 4 re-assemblies).
    Assembly includes install strain gauges on shells, Fabricate Yoke/Shell subassemblies. Receive and check coils, perform CMM measurements and prepare coils for magnet assembly. Assemble collar packs and coil packs. Insert coil packs, setup bladders, and perform azimuthal and axial preload, and conduct electrical QC
  Prepare for shipment and ship the magnet assembly to BNL for vertical testing.
Charge #2

## Slide 4: WBS 302.2.07: Overview of deliverables

## Slide 5: WBS 302.2.07: Work Flow and Interfaces
5
Coils from FNAL
302.2.05
Coils from BNL
302.2.06
US-HiLumi-doc-309
US-HiLumi-doc-252
Magnet shipped to BNL
302.4.1
US-HiLumi-doc-321
Fiducialization Data to FNAL
302.4.02
US-HiLumi-doc-216
Coil components
302.2.04
US-HiLumi-doc-273
Charge #9

## Slide 6: WBS Deliverables & Yield Assumptions
WBS Deliverables
  Re-assembled prototype magnet MQXFA-1b, 4 accepted pre-series magnets, and a minimum of 17 accepted production MQXFA magnets with their corresponding QC reports.
Yield Assumptions:
  3 of the 16 series magnets and one of the 5 pre-series magnets are assumed to be re-worked before passing acceptance test. Parts are assumed to be re-used for this re-work.
  1 Magnet structure is assumed to be irreversibly damaged, due to shipping and handling, and therefore assumed lost.

## Slide 7: Interfaces with incoming coils and with magnet testing
Charge #9

## Slide 8: WBS 302.2.07: External Dependencies
Original CLIQ leads were provided by CERN (see interface control document US-HiLumi-doc-375); described in US-HiLumi-doc-998 (now obsolete)
Recently a modified procedure has been defined
  Described in US-HiLumi-doc-4328
    Based on CERN version of the assembly procedure (EDMS 2772060)
  ICD US-HiLumi-doc-375 has been updated
  Update to ICD US-HiLumi-doc-998 is underway
All CLIQ lead material had been received from CERN in Feb 2020
New material will be needed per doc-4328
  Components will be procured by CERN and assembled at LBNL
Charge #6 & #9

## Slide 9: WBS 302.2.07: Team
Very established team
  Additional technicians planned
Soren Prestemon, L3 Manager
Dan Cheng, Deputy L3 Manager
Paolo Ferracin, Deputy L2 Manager
Laura Garcia Fajardo
QA:
Katherine Ray
Jennifer Doyle
Mike Solis (also procurements)
Technicians:
Joshua Herrera, lead
Juan Rodriguez
Jonathan Hekmat
Matt Reynolds
Bob Memmo (Electrical)
Target staffing & training level:
At least one additional technician to minimize disruption from vacation, illness, etc.
Cross-train to avoid potential bottlenecks or single-point failures
  Ex.: recent training of 2 junior techs on instrumentation
Charge #4

## Slide 10: WBS 302.2.07: Achievements since CD-3
Completed tooling for full parallel assembly capability needed for production magnets
Completed assembly of all pre-series scope (MQXFA03-A07)
Assembled MQXFA08-12 and reassembled MQXFA08b
Key technical milestones since DOE CD-3 review
  PRR (4005 Feb. 2021)
  MQXFA Series Magnet Specifications updated (DocDb 4009-v6)
  Coil selection, Structure & Shim reviews; Handoff meeting for each magnet delivered to BNL
Chart: 
| Ordered and received | Ordered but not received yet | Not ordered yet
Structures Procurement | 18 | 3 | 0
Facility improvements (lab-supplied):
- HVAC and roofing of assembly building
Charge #5

## Slide 11: Magnet fabrication process – a pictorial view
Shell-Yoke Assembly
Coil Prep
Radial Shim Prep
Fuji Paper Exposure
Charge #5

## Slide 12: Magnet fabrication process – a pictorial view
Fully assembled magnet
Final Coil pack assembly
Coilpack Insertion
Preloading
Splicing and Connectorization
Charge #5

## Slide 13: Examples of issues and resolutions
Cooling hole bore clearance – ECN-0233
GPI fold issue in MQXFA09 – NCR-0313 (critical)
  The two associated coils have been rejected
Fiberoptics installed (upper coils only) – DCR-4190
Increase in pole-key gaps – DCR-4304

## Slide 14: Lesson’s learned resulted in improved process of assembly, demonstrated with MQXFA10
Identified during MQXFA07 disassembly
Lessons learned and preventive actions are being implemented on all magnets going forward

## Slide 15: WBS 302.2.07: WBS Contingency Consumption by COVID
Charge #1

## Slide 16: WBS 302.2.07: Procurement Status
Remaining procurements may include:
  Magnetic shims, and other consumables
Additional exposure to inflation is minimal for Structures
All major components have been ordered
  ”Master Agreements” proved valuable
    Enabled timely PO placements
    Likely avoided additional costs due to inflation
Majority have been received and are in-use or in storage
Charge #9

## Slide 17: WBS 302.2.07: Schedule
Structures not on critical path, but…
  Need vigilance to meet P6 schedule
  Actions are being taken and remaining risks identified
Note: we have two fully functioning assembly lines to support meeting the schedule
Charge #2

## Slide 18: WBS 302.2.07: Schedule considerations
Anticipated “full production” mode has been disrupted by:
  Disassembly of MQXFA07 for post-mortem
  Disassembly of MQXFA08 and re-use in MQXFA08b
  Disassembly of MQXFA09 and use of structure in MQXFA11
  Unloading and reloading of MQXFA10 to address “squareness” lessons-learned
Nevertheless:
  We are confident in our ability to deliver to the schedule
    Labor estimates and durations in BOEs demonstrated on each step of the Assembly Breakdown Structure
    All major procurements orders have been placed
    Most major procurement orders have been received
  Actions taken:
    Training staff for some level of redundancy
    Out-sourced some assembly steps to industry
  Remaining concern:
    Challenging market for tech expertise – hard to hire and to retain
Charge #2

## Slide 19: WBS 302.2.07: Cost and Schedule Performance & VAR Reports
Major variances earlier in project stemmed from large procurements and various vendor issues in delivering on schedule
  Most significant example was ARMCO steel order
Recent variances typically associated with individual component delivery delays (e.g. due to vendor rework), mismatch of receipt and earning of article, and overruns/underruns on certain labor elements
Charge #2

## Slide 20: WBS 302.2.07: Estimate at Completion
  Minor Variance at Completion (BAC- EAC) = $71K on $33.7M
Charge #2

## Slide 21: WBS 302.2.07: Risks
Risks are monitored and reviewed regularly
  RT-302-2-07-002: “Bladder pressurizing system failure” was realized; spare had been procured as part of mitigation, resulting in negligeable delay
  RT-302-2-07-007: “Magnet disassembly and reassembly needed to meet the requirements” has been realized with the disassembly and reassembly of MQXFA10
    Updated entry reflect residual risk of having to disassemble and reassemble between 0 and 2 magnets between now and the end of the project.
Charge #3
RT-302-2-07-007 (*) | Magnet disassembly and reassembly needed to meet the requirements | Medium
RT-302-2-07-001 | Magnet assembly matrixed or shared resources unavailable when needed | Medium
RT-302-2-07-006 | Production is stopped because more QC testing/discussions need to be carried out | Medium
RT-302-2-07-004 (*) | Magnet structure vendor delivery delays | Low
RT-302-2-07-002 | Bladder pressurizing system failure | Low
(*) These risks have a separate COVID-19 component in the risk register to account for additional probability/impact due to COVID-19 pandemic.

## Slide 22: WBS 302.2.07: QA/QC
Area | QC / Work Instructions | QA – MIP element
Coil Selection and Shimming Plan Review | Coil Acceptance WI SU-1011-5294; Coil CMM WI SU-1012-3958 | 1.1
Incoming Shells and Yokes & inspection |  | 2.2
Assemble Yoke Half-Stacks | Yoke Pre-Stack SU-1008-8072; Yoke Half Stack SU-1009-7829 | 2.2
Put strain gauges on shells | Shell Instrumentation SU-1009-3745 | 2.3
Complete Shell-Yoke Assembly | Shell-Yoke Assembly SU-1008-2169 | 2.4
Incoming coil pack assembly parts inspection | Load Pad Pre-Stack SU-1008-8075 | 3.1
Dressed Coil | Dressed Coil SU-1008-8073 | 3.2
Pad Collar Assembly | Pad-Collar Assembly SU-1010-1610 | 3.3
Coil Pack Assembly | Coil Pack Subassembly SU-1008-8074 | 3.4
Coil Pack Electrical Tests | MQXF Magnet Electrical QA at LBNL SU-1010-1903 | 3.5
Coil Pack Magnetic Measurements | Magnetic Meas. SU-1010-2018 | 3.6
Area | QC / Work Instructions | QA – MIP element
Incoming parts inspection (Master Keys, etc.) |  | 4.1
Strain Gauges on Axial Rods | Axial Rods Instrumented SU-1008-8069 | 4.4
Magnet Integration and Loading | MQXFA Loading and Integration WI SU-1011-5637 | 4.5
Post-preload Electrical QC | MQXF Magnet Electrical QA at LBNL SU-1010-1903 | 4.6
Finish Wiring | Connectors and Finishing WI SU-101205517 | 4.7
Assemble Splice Box and verify Bore ID Clearance | Splice Box WI SU-1008-8067 | 4.8
Magnetic Measurements, Fiducial Structure | Magnetic Measurements SU-1010-2018 | 4.10
Final Electrical QC | MQXF Magnet Electrical QA at LBNL SU-1010-1903 | 4.11
Strain Gauge Reading |  | 4.12
Prepare for Shipment |  | 4.13
MIP has been approved by all parties
QC data for each magnet is uploaded to Vector and to the CERN MTF – all magnet data is then available to subsequent WBS elements
Charge #3

## Slide 23: WBS 302.2.07 QA/QC process
Detailed tracking sheet is maintained
Monthly reports submitted to L2 and Project QA Manager, as well as regular meetings
  Clear process for informing L2 of an issue and for resolution
  Excellent relations within AUP and with CERN – strong team, very transparent
Charge #3

## Slide 24: WBS 302.2.07: ES&H
We have regular LBNL HL-LHC AUP EH&S meetings
Meeting agenda’s and notes are shared regularly with FNAL Project EH&S Manager Amy Pavnica
Excellent safety record to-date
Magnet Survey and Alignment has a Work Planning and Control (WPC) Activity (laser tracker has Hazard Level 2); staff are trained accordingly
Crane failed in assembly area:
  Resulted in halt of use until inspected and operation recovered
  Spare parts have been procured, maintenance will be planned when all parts are in-house and when AUP schedule is minimally impacted
Charge #10

## Slide 25: WBS 302.2.07: Summary
The Magnet Assembly WBS is in full production mode, deep into production magnet assembly
Strong team, now well-versed in all technical, QC/QA, and EVMS aspects of the project
COVID has had a significant impact on multiple fronts – these are now understood and addressed
We have procured all major components for the magnet assemblies, alleviating a major concern with inflation and supply-chain
Risks are being managed and addressed – plenty to worry about… but plenty to be proud about!

## Slide 26: Backup Slides

## Slide 27: WBS 302.2.07: WBS Contingency Consumption by Other Causes

## Slide 28: 302.2.07 Resource Type Breakdown
77% Labor, 23% M&S
M&S predominantly under “Master Agreements” that have all been exercised
Charge #4

## Slide 29: 302.2.07 Estimate Quality
Estimate quality is generally very advanced
  M&S largely based on Master Agreements that have been fully exercised, or existing quotes
Preliminary is related to bladder vendor switches

## Slide 30: 302.2.07 FTE Breakdown
Charge #4

## Slide 31: 302.2.07 Cost Performance Report
BAC = $33.8M
Current Period Cost and Schedule thresholds crossed
Cumulative SPI = 0.96, CPI = 1.03
Charge #5