## Sheet1
Category | Document | EDMS | Controlled by | Required for Final Design Review | Notes:
Design Documents | TDR Chapter |  | DUNE EB | No additional requirements for Final Design Review. | Completed.
| Design Updates |  | Consortium | Updated, stand-alone version of orginal TDR chapter that accurately describes sub-system design at time of Final Design Review. The document should include information on any prototyping activites since the Preliminary Design Review that have impacted the Final Design. | Bob Wilson, Editor. Additional contributors:
| Grounding & Shielding Plan | xxxxxx | DUNE TB | Final document should include a sub-system grounding diagram with all components and cables identified, text which notes any sub-system grounding or isolation requirements, and EDMS references to documentation on all cables and custom or commercial equipment included in the grounding diagram. Physical implementation of grounding connections should also be described - this can be done through pictures, schematics, or mechanical drawings of the hardware connections. Plan should have sign-off from DUNE Grounding & Shielding Committee (contact Terri Shaw at tshaw@fnal.gov). An example of a grounding diagram (TPC electronics) can be found in EDMS 2364510. Detector system grounding rules for cables & shields can be found in EDMS 2095958. Infrastructure grounding rules are posted in EDMS 2095975. | Nearly complete. Edits: C. Gotti, P. Carniti. Others? | 12/16 Draft
| Mechanical CAD Model for Sub-system | xxxxxx | Consortium | Final CAD model that serves as the basis for all production drawings. Although drawings include additional detail beyond that contained within the model, the drawings themselves should be being generated directly from this released model. | To be updated based on ProtoDUNE 2 (and this meeting!) underway. Z. Rautio, J. Jablonski D. Warner. Others? | 12/16 Draft
| Mechanical Engineering Drawings | xxxxxx | Consortium | Drawings should be of the quality to send to an outside vendor for production and marked "For Module Zero Production". Drawing details should include materials of construction, component masses, pointers to higher-level drawings, default and critical tolerances, part finishes, cleaning procedures, as well as weld parameters and certifications where applicable. All drawings need to be released and set up within a versioning framework providing proper engineering change notification documentation. | To be updated based on ProtoDUNE 2 (and this meeting!) underway. Z. Rautio, J. Jablonski D. Warner. Others? | 1/13 Draft
| Mechanical Assembly Drawings and Parts Lists | xxxxxx | Consortium | Assembly drawings should be of the quality to send to an outside vendor for production and marked "For Module Zero Production". Drawing details should include references to applicable assembly procedures, bills of materials, list of assembly tools to be procured, CG markers, assembly masses (both wet and dry), indications of the proper orientations for asymmetric parts, and pointers to higher-level drawings. All drawings need to be released and set up within a versioning framework that provides proper engineering change notification documentation. | To be updated based on ProtoDUNE 2 (and this meeting!) underway. Z. Rautio, J. Jablonski D. Warner. Others? | 1/13 Draft
| Electrical Schematics & Board Layouts | xxxxxx | Consortium | Production schematic and manufacture information for all boards should be posted and released. ECOs from the pre-production boards should be listed and explained. A performance document should be included which shows that relevant system requirements have been met. A plan for tracking any future hardware modifications should be in place. A plan for tracking the history of individual boards (e.g. location & repairs) should also be in place | Needs to be re-visited. Need DAPHNE, Flange, cold electronics, signal routing PCB, monitoring system. AECB and SASEBO included in rail/cable PRR | 12/16 All but DAPHNE. 1/13 DAPHNE
| Specification of Electrical Cabling and Wiring Connections | xxxxxx | Consortium | All cable specifications and drawings must be final and released in EDMS. Examples of cable specifications/drawings can be found in EDMS 2413129. Final wiring diagram must show connections between all subcomponents with connecting cables clearly identified. Analysis of all power paths must be included to demonstrate that connectors, wires, and boards can handle maximum possible currents and voltages or are protected/fused. Information provided must be sufficient for satisfying Operational Readiness Clearance (ORC) requirements, which as currently prescribed for FNAL are described in FESHM Chapter 2005 (https://eshq.fnal.gov/manuals/feshm/). | Needs to be re-visited. Need LV power supply cables, APA-Flange cable, warm cables. Cables inside APA included in rail/cable PRR | 12/16 Draft
| Bills of Materials for Electronic Board Components | xxxxxx | Consortium | Final BOMs should be released in EDMS. A plan should be in place to track any board ECOs. | C. Gotti P. Carniti J. Ameel Z. Djurcic | 12/16 All but DAPHNE. 1/13 DAPHNE
| Documentation Links for Commercial, Off-the-Shelf Powered Components | xxxxxx | Consortium | Links to full documentation must be provided for any powered equipment which is commercial off-the-shelf (examples include power supplies, crates, commercial modules, …) This will be required for ORC. | J. Ameel. Others? | 12/16 Draft
Requirements Documents | EB-Held Requirements | 2346091 | DUNE EB | No additional requirements for Final Design Review. | Re-check and finalize (Ettore et. Al.) | 12/16 Check
| TB-Held Requirements | 2346092 | DUNE TB | No additional requirements for Final Design Review. | Re-check and finalize (Ettore et. Al.) | 12/16 Check
| Consortium-held Requirements |  | Consortium | No additional requirements for Final Design Review. | Re-check and finalize. Mechanical, electrical, Calibration, Physics, ??? | 12/16 Check
Installation Documents | Detector Installation Plan | 2233449 | Integration Office | The relevant chapters need to be finalized. Must include requirements on positional tolerances. Any ProtoDUNE-II and initial DUNE installation tests at Ash River should be completed and lessons-learned from these exercises incorporated within the installation plan. Once finalized, the document needs to be approved and signed-off on. | D. Warner lead. E. Segreto, D. Moreno, J. Ameel. Will contact others for input. INCLUDE TRANSPORTATION | 1/13 Draft
| ProtoDUNE-II Installation Plan | xxxxxx | Integration Office | Plan describing how the module zero components will be installed in ProtoDUNE-II. | N. Gallici, M. A.G. Peris, D. Warner, others? | 1/13 Draft
Interface Documents | Consortium-Consortium | xxxxxx xxxxxx xxxxxx xxxxxx xxxxxx xxxxxx | DUNE TB | Document should be updated to reflect any negatiated changes to interfaces that have occured since Preliminary Design Review. All "To do" list items must be resolved and all referenced documents must be completed and available (released) in EDMS. Final document must also be released and have all required signatures (as prescribed through the project sign-off process) | Documents in place. To be re-checked. PD-APA: Warner. PD-HV: Martinez(?) PD-DAQ D. Christian & C. Gotti(?) | 12/13 Drafts
| Consortium-Installation | xxxxxx | Integration Office | Document should be updated to reflect any negatiated changes to interfaces that have occured since Preliminary Design Review. All "To do" list items must be resolved and all referenced documents must be completed and available (released) in EDMS. Final document must also be released and have all required signatures (as prescribed through the project sign-off process) | Warner lead, will contact others | 1/13 Draft
| Consortium-DSS | xxxxxx | Integration Office | Document should be updated to reflect any negatiated changes to interfaces that have occured since Preliminary Design Review. All "To do" list items must be resolved and all referenced documents must be completed and available (released) in EDMS. Final document must also be released and have all required signatures (as prescribed through the project sign-off process) | Warner lead. Will contact others. | 1/13 Draft
| Consortium-Facilities | xxxxxx | Integration Office | Document should be updated to reflect any negatiated changes to interfaces that have occured since Preliminary Design Review. All "To do" list items must be resolved and all referenced documents must be completed and available (released) in EDMS. Final document must also be released and have all required signatures (as prescribed through the project sign-off process) | D. Martinez, C. Gotti, P. Carniti lead, will contact others | 1/13 Draft
| Interface Drawings |  | DUNE TB & Integration Office | Interface drawings are one type of referenced documents within the interface documents described above. As such, they must all be finalized and released in EDMS. All interface drawings referenced in the documents need to be available at the time of the Final Design Review. | Module Mechanical: Warner. Monitoring mechanical: Z. Djurcic. Electrical: C. Gotti, P. Carniti, J. Ameel | 1/13 Draft
Engineering Analysis Documents | Analysis Plan | xxxxxx | Consortium & Compliance Office | Analysis Plan should be updated to include details of the FEA model(s) and methods used for analyzing the different load cases as further clarification of the required deliverables. Final document needs to be jointly signed-off by the consortium and compliance office. | Documents mostly complete from rail/cable PRR. Warner lead. | 12/16 Check
| Structural Analysis Note(s) | xxxxxx | Consortium | Engineering note(s) need to be updated to address all recommendations received on the previous note version from the Compliance Office and through the Preliminary Design Review. Source models used in carrying out the analysis should be made available in EDMS along with the note. Updated note(s) need to be re-reviewed and approved by the Compliance Office. | Documents mostly complete from rail/cable PRR. Warner lead. | 12/16 6heck
| Independent Review Report(s) | xxxxxx | Compliance Office | Final report indicating concurrence with actions taken based on all previous recommendations and overall Compliance Office approval must be in place at least one month prior to date of Final Design Review. | Mechanical review report in place. Electrical outstanding. P. Carniti? | 12/16 Check Mechanical. Electrical 1/13
QA/QC Documents | Preliminary QA/QC Plan | xxxxxx | Consortium | Plan needs to be updated to provide further clarfication of items that had not been fully developed or were unknown at the time of the Preliminary Design Review. Plan should include information about codes and standards that will be applied during the testing process (e.g. those used in determining the quality of welds) | Need representative from each WG. | 1/13 Draft
| ProtoDUNE Lessons-Learned | xxxxxx | Consortium | No additional requirements for Final Design Review. | Need summary report. Guided by this meeting(!) | 12/16 Draft
| Preliminary Manufacturing and Procurement Plan | xxxxxx | Consortium | Plan needs to be updated to provide further clarfication of items that had not been fully developed or were unknown at the time of the Preliminary Design Review. Plans for local storage of items prior to them being shipped to the near or far site should be described. | Need representative from each WG. D. | 1/13 Draft
| Plan for Prototyping Activities | xxxxxx | Consortium | New document describing any planned prototyping activities subsequent to the Final Design Review. Include information on any planned testing at Ash River or ProtoDUNE-II that could potentially lead to design changes between Final Design Review and Production Readiness Review. | Particularly for DAPHNE (D. Christian, D. Moreno), module mechanical (D. Warner) | 1/13 Draft
| Fabrication, Inspection, and Test Procedures | xxxxxx | Consortium | Written procedures for the detailed steps necessary to fabricate, inspect, and test each of the sub-system components and assemblies. | Need representative from each WG. | 1/13 Draft
| Fabrication, Inspection, and Test Forms (Travelers, Test Reports, and Inspection Reports) | xxxxxx | Consortium | Completed templates of all necessary forms for recording QC information during the fabrication, inspection, and testing of the sub-system components and assemblies. | Need representative from each WG.Include part identifiers, Database. G. Valdiviesso | 1/13 Draft
Cost/Schedule Documents | Cost Estimate |  | DUNE EB | Resource-loaded actvity schedule in P6 should be finalized such that a full sub-system cost estimate can be extracted. Extracted cost estimate that is presented to Neutrino Cost Group (NCG) should also be made available for Final Design Review. | P6 schedule in place can be made available | 12/16 Check
| Insitutional Responsibilities |  | DUNE EB | List of all system deliverables with the responsible collaboration institutes. | In place, to be checked (E. Segretto, D.Warner, F. Terranova) | 12/16 Check
| Schedule Summary |  | DUNE TB | Summarized information from finalized P6 schedule including high-level milestones. Schedule for the delivery of system components to the near and far sites should be highlighted. | D. Warner lead. Will contact others for input | 12/16 Check
Tracking Documents | Responses to Past Review Recommendations | xxxxxx | Review Office | Spreadsheet should be updated to include recommendations and responses from the Preliminary Design Review and any additional reviews that have occured in the interim. | Spreadsheet being completed by D. Warner. May contact others for clarification as needed. | 12/16 Check
| Review Office Report on Responses to Past Reviews | xxxxxx | Review Office | Memo from Review Office confirming that all prior review recommendations (as documented in spreadsheet) have been acted on appropriately. This memo should be in place and signed-off on at least four weeks prior to the scheduled Final Design Review date. | S. Kettel | 1/13(?)