## Slide 1: Summary pf ProtoDUNE 2 Lessons Learned
David Warner
11/16/22

## Slide 2
Overview
Module design and Assembly
Cold Electronics
Monitoring System
Warm Electronics
Summary

## Slide 3: Overview
In general the PDS installation if ProtoDUNE was successful
  40 modules installed in2 configurations, single and double-sided, were installed in 4 APAs
  10 monitoring system diffusers were installed and fibers routed. LED flasher controllers (Modified SSPs) were installed and demonstrated to interface with DAQ
  Two DAPHNE configurations tested. Readout over full-length cables was demonstrated to meet analog requirements

## Slide 4: Module Design and Installation
Pre-assembly of supercells followed by post-assembly into a full module can be done, but is difficult and time consuming, requiring highly-trained professionals and significant time.
  THIS WAS NEVER THE INTENDED DESIGN PLAN, AND WAS ONLY IMPLEMENTED DUE TO SUPPLY-CHAIN DRIVEN DELAYS IN SiPM AND DICHROIC FILTER PRODUCTION. IT WILL NOT BE DONE IN DUNE
There are a large number of components and fasteners in the design. We should try to minimize
  THE DESIGN WAS OPTIMIZED TO MAXIMIZE THE NUMBER OF PARTS ABLE TO BE CUT WITH A WATER JET TO FACILITATE MANUFACTURING. WE ARE WORKING TO EVOLVE THE DESIGN TO MINIMIZE PART AND FASTENER COUNT

## Slide 5: Module Design and Installation (ii)
A few components were discovered not to have been fabricated as specified in the drawings, particularly tapped through holes and clearance slots in filter clamping plates (necessitating using cumbersome spacer washers during assembly).
  WE ARE WORKING CLOSELY WITH VENDORS TO RESOLVE THIS PROBLEM
It is critical that the modules be assembled straight and flat to ensure ease of assembly
  ASSEMBLY FIXTURES WILL BE USED TO ENSURE FLAT ASSEMBLY
Screws frequently loosened during handling and transportation
  USE THREAD LOCKER ADHESIVE DURING ASSEMBLY

## Slide 6: Module Design and Installation (iii)
Repeated assembly and dis-assembly of module components was required, particularly during filter plate assembly.
  THIS WAS PRIMARILY A RESULT OF THE ASSEMBLY OF MODULES FROM PRE-ASSEMBLED SUPERCELLS, BUT ALSO FROM ATTEMPTS TO HAVE SINGLE PIECES SERVE MULTIPLE UNRELATED MECHANICAL PURPOSES (MODULE STRUCTURAL + FILTER HOLDING). MODIFY DESIGN TO MINIMIZE THIS PROBLEM (NOTE THIS MAY INCREASE PART COUNT)
Filter installation (particularly double-sided modules) was difficult
  SIMPLIFY CLAMPING, AND SEPARATE FUNCTIONALITY OF PIECES. INVESTIGATE POSSIBILITY OF SHIPPING MODULES WITH FILTER PLATES INSTALLED (PROMISSING INDICATIONS DURING PROTODUNE 2 SHIPPING)

## Slide 7: Module Design and Installation (iv)
Module end blocks and captive screws were observed not to work satisfactorily during installation and primarily during module removal
  RE-DESIGN END BLOCKS TO ENSURE PROPER CAPTIVE SCREW FUNCTION. INCREASE STRENGTH OF JUNCTION BETWEEN END BLOCKS AND MODULES.
Module removal too difficult
  MODIFY MODULE GUIDE FEATURES TO ENSURE PROPER GUIDANCE DURING INSERTION AND REMOVAL
Tolerance of SiPM pins larger that originally specified
  MODIFY DESIGN TO ENSURE PROPER PIN ENGAGEMENT INTO SIGNAL ROUTING PCB CONNECTORS AND PROPER PROTECTION FROM PIN EXPOSURE TO APA FRAME

## Slide 8: Cold Electronics
Cold electronics amplifiers functioned well in ProtoDUNE
  NO OBSERVED FAILURES IN COLD TESTING OR OPERATION
  CONSIDER SINGLE INTEGRATED AMPLIFIER BOARD DESIGN RATHER THAN MOTHERBOARD/DAUGHTERCARD DESIGN.
  CONSIDER COMPONENT CHANGE TO MINIMIZE UNDERSHOOT
Signal routing board (AKA signal lead board) pin connectors occasionally blocked during soldering
  ADDRESS WITH MANUFACTURER
SiPM PCB pins occasionally fail to fully engage in connectors
  MODIFY MODULE DESIGN TO ENSURE PROPER PIN ENGAGEMENT INTO SIGNAL ROUTING PCB CONNECTORS AND PROPER PROTECTION FROM PIN EXPOSURE TO APA FRAME

## Slide 9: Monitoring System (i)
The monitoring system installation in ProtoDUNE 2 functioned well
  10 diffusers mounted to cathode
    TWO DIFUSER HOUSING DESIGNS IN PROTODUNE. SINGLE FASTENER DESIGN PREFERRED FOR ASSEMBLY. WILL BE VALIDATED DURING PROTODUNE
  Fiber routing worked well, significant improvement in ease and reliability over ProtoDUNE 1
    THREE FIBER ROUTING PATH WILL BE VALIDATED IN RUNNING
  Two candidate fiber jackets will be tested in ProtoDUNE 2
    TEFZEL OPTION REPRESENTS POTENTIAL COST SAVINGS AT SOME LOSS OF PERFORMANCE. INVESTIGATE COST OF DOWN-SELECTING TO OTHER OPTION PRIOR TO FDR AND LEAVING TEFZEL AS RISK OPPORTUNITY FOLLOWING PROTODUNE 2 VALIDATION

## Slide 10: Monitoring System (ii)
LED Controller Module tested at PROTODUNE 2, demonstrated to interface with DAQ
  TWO CANDIDATE LED WAVELENGTHS UNDER TEST. WILL BE VALIDATED IN PROTODUNE 2. BOTH MAY BE SELECT AS OFFERING COMPLIMENTARY FUNCTIONALITY. CONSIDER PROPOSING BOTH AS BASELINE DESIGN PRIOR TO FDR?
Monitoring photodiodes not yet demonstrated in ProtoDUNE
  WILL BE VALIDATED IN PROTODUNE 2 RUNNING

## Slide 11: Warm Electronics (DAPHNE) (i)
DAPHNE V2 operated at ProtoDUNE 2 and demonstrated to meet nearly all requirements (tests remaining)
  S/N >4 FOR END TO END READOUT DEMONSTRATED
  TIMING RESOLUTION <100ns DEMONSTRATED
  COMMUNICATION WITH DAQ DEMONSTRATED
    COMMUNICATION WITH FELIX (AS IN CURRENT INTERNACE DOCUMENT) >5GBS DEMONSTRATED
    SUMMICIENT DATA TRANSFER RATES WITH PROPOSED ETHERNET CUMMUNICATION PROTOCOL FOR DAQEXISTING ARCHITECTURE POSSIBLE (USING MULTIPLE DATA LINKS) NEED TO CONFIRM WE CAN MAKE THIS STATEMENT
Need to demonstrate interface with DAQ clock system
  TO BE VALIDATED IN COLD BOX SHORTLY

## Slide 12: Warm Electronics (DAPHNE) (ii)
A risk in the DUNE FD1 Risk Register was activated to allow modifications to the DAPHNE design to optimize communication with the DAQ at 10GBS using a single readout fiber
  MINIMAL COST INCREASE TO PRODUCTION EXPECTED
  SHOULD SIMPLIFY LAYOUR AND ASSEMBLY, SIMPLIFY PROGRAMMING
  ALLOWS SYNERGIED WITH CE-WIB DESIGN
  EXPEDITED DESIGN CYCLE WILL ALLOW PROTOTYPE BOARDS TO BE AVAILABLE PRIOR TO CD2-3 IN SUMMER 2023
May require additional FDR refresh after prototype testing
  PLANNED TESTING IN SPRING 2023.

## Slide 13: Summary– Path to FDR (i)
Module design: Minor changes to basic module design will result in increased reliability, ease of assembly.
  Prototypes will be fabricated and tested at CERN prior to FDR.
  Present modified design at FDR
Cold Electronics as designed meet reliability and performance goals
  Present current design with daughter cards as baseline
  Present single board design as possible cost reduction opportunity, to be evaluated prior to PRR
  Present possible component change as performance opportunity, to be evaluated prior to PRR

## Slide 14: Summary– Path to FDR (ii)
Monitoring system as designed appears to meet all requirements.
  Present single-fastener, three fiber option as baseline
  Present Tefzel fiber jacket as risk opportunity to reduce cost, to be evaluated prior to PRR
  Present multiple-wavelength LEDs as design, to allow monitoring of coating performance. Select sort wavelength option as principle option
Warm Electronics as designed meet reliability and performance goals
  Present DAPHNE v2 as baseline design at FDR
  Present DAPHNE v3 as activated risk being aggressively followed to leverage potential improvements possible with Ethernet DAQ protocol.
  Propose possible FDR refresh prior to CD2-3 to certify DAPHNE V3 as baseline following prototype testing in cold box.