## Labor
LBNF EXTRACTION LINE
MI-10 Q-103 thru Q-107 LCW & BUS RETROFIT
LABOR ESTIMATE - LIST OF TASKS
|  | FERMI |  | TRADES |  | MIN. TASK
|  | LABOR |  | LABOR |  | DURATION | NOTES
|  | Type | Hours | Type | Hours | Days
FINAL DESIGN
| Final Design | Fluids Eng'r | 200 |  |  | 25
|  | Magnet Eng'r | 24
|  | Elec. Eng'r | 24
|  | Drafter/Designer | 400 |  |  | 50
| Final Design Review | Fluids Eng'r | 60 |  |  | 8
|  | Magnet Eng'r | 16
|  | Elec. Eng'r | 16
|  | Drafter/Designer | 100 |  |  | 13
|  | Machine Eng/Phys | 60
| Installation | Fluids Eng'r | 120 |  |  | 15
|  | Magnet Eng'r | 20
|  | Elec. Eng'r | 20
|  | Drafter/Designer | 40 |  |  | 5
| Installation Document Review & As-Builts | Fluids Eng'r | 40 |  |  | 5
|  | Magnet Eng'r | 4
|  | Elec. Eng'r | 4
|  | Drafter/Designer | 60 |  |  | 8
PIPE & BUS REMOVAL
Global LCW Pipe:
| Shut down MI LCW system, isolate, drain and prep for long term shutdown | Fluids Tech | 48 |  |  | 2 | 3 techs x 2 days
| Disconnect dipoles, quads, remove hoses, flags, move to storage | Fluids Tech | 48 |  |  | 2 | 3 techs x 2 days
| Stage and prep for Q100 tunnel work - LCW & bus removal |  |  | Pipfitter | 16 | 1 | 2 pf x 1 days
| Mark & cut LCW pipe, move to storage |  |  | Pipfitter | 80 | 5 | 2 pf x 5 days
Quadrupole Bus:
| Mark & cut quad bus, move to storage |  |  | Pipfitter | 120 | 5 | min 6 man crew, DS alcove walll @ Q-103 thru D-107-1 & -2, 8 lbs/ft ttl ~ 550', ~ 4600 lbs
| Remove header & bus wall brackets, move to storage |  |  | Pipfitter | 16 | 2
Dipole Bus:
| Remove dipole bus & brackets, move to storage |  |  | Pipfitter | 120 | 5 | min 6 man crew, Q-103 thru Q-107, 15 lbs/ft, 5 pair in sets @ ~ 600 lbs/set
MI-14 LCW & Fluorinert Pipe:
| Shut down MI-14 Fluorinert system, isolate, drain both LCW and Fuorinert sides of system | Fluids Tech | 48 |  |  | 2 | 3 techs x 2 days
|  | Kicker Tech | 8 |  |  |  | 1 tech x 1 day
| Empty MI-14 Girardi box, and penetrations to Q-105 | Fluids Tech | 16 |  |  | 2 | 2 days, cubic yards of poly beads to deal with
|  | Rad Tech | 16
|  | Bead Removal Crew | 32
| Stage and prep for Q-105 & MI-14 work - LCW & Fluorinert removal |  |  | Pipfitter | 16 | 2 | 2 pf x 1 day
| Mark & cut pipes @ Q-105 |  |  | Pipfitter | 8 |  | 2 pf x 0.5 day
| Mark & cut pipes @ MI-14 |  |  | Pipfitter | 8 |  | 2 pf x 0.5 day
| Extract pipes from top of Girardi box thru MI-14, move to storage | Fluids Tech |  | Pipfitter | 80 | 5 | all 4 runs are around 50' length, 2 each at about a 40 degree angle thru the penetration, with spiders, and barely fit installation inside of roof by bending pipe what it would sag by weight
| Close & protect all open ends to systems | Fluids Tech | 16 | Pipfitter |  | 1
| Clean up, remove equipment, all work shelved |  | 4 | Pipfitter | 16 | 2
| Task Manager for above | Fluids Tech | 120 |  |  |  | Full length of construction + prep / wrap up
ENCLOSURE UTILITIES PREP FOR TO REINSTALL
Beneficial occupancy, all survey & layout work complete
| Move, lower, relocate grounding strap on outer enclosure (magnet) wall bottom |  |  | Electrician | 32 | 2 | 2 elec x 2 days
| Lower cable trays in center of overhead to enable installation of LCW crossover piping |  |  | Electrician | 64 | 2 | 4 elec x 2 days
| Move, lower, relocate lighting and conduits on Aisle side |  |  | Electrician | 80 | 5 | 2 elec x 5 days
| Raise & return cable trays in center of overhead to proper elevation |  |  | Electrician | 64 | 2 | 4 elec x 2 days
PIPE & BUS INSTALLATION
Global LCW Pipe:
| Stage and prep and layout for Q100 tunnel work - LCW & bus installation |  | 24 | Pipfitter |  | 1 | 3 pf x 1 day, placement of manifolds and taps, valves, on upper aisle side
| Retrieve header piping, brackets, etc from storage and/or delivery |  | 24 | Pipfitter |  | 1 | 3 pf x 1 day
| Remove, modify, and reinstall manifolds w/ crossovers |  | 160 | Pipfitter |  | 12 | 2 pf x 10 day
| Install header pipe hangers on aisle side |  | 32 | Pipfitter |  | 2 | 2 pf x 2 day
| Install header piping for Q-107 cross-over |  | 80 | Pipfitter |  | 5 | 2 pf x 5 day
| Install header piping from Q-103 alcove to Q-107 cross-over |  | 240 | Pipfitter |  | 12 | 3 pf x 10 day
| Reinstall all hoses, brackets, any misc. | Fluids Tech | 32 |  |  | 2 | 2 techs x 2 days
| Fill & test system headers | Fluids Tech | 16 |  |  | 1 | 2 techs x 1 day - DO NOT FILL UNTIL READY! hydrostatic test not required nor advisable
| Bring system to operational status | Fluids Tech | 16 |  |  | 1 | 2 techs x 1 day
| Valve in quad cells | Fluids Tech | 8 |  |  | 1 | 2 techs x 0.5 days
| Task Manager for above | Fluids Tech | 240 |  |  |  | 30 DAYS Min. Full length of construction + prep / wrap up
MI-14 Fluorinert & LCW Pipe:
| Inspect & prep penetrations between MI-14 to Q-105 for piping fit | Fluids Eng'r | 8 |  |  | 2
|  | Drafter/Designer | 8
|  | Task Manager | 12
| Retrieve & stage LCW and Fluorinert piping, brackets, etc from storage and/or delivery | Fluids Tech | 8 | Pipfitter | 8 | 1
| Reinstall LCW and Fluorinert lines through penetrations to MI-14 system |  |  | Pipfitter | 120 | 7 | 3 pf x 5 Day
| Install Fluorinert lines to kickers |  |  | Pipfitter | 32 | 2 | 2 pf x 2 day
| Installl modified piping runs across ceiling, similar to manifolds |  |  | Pipfitter | 32 | 2 | 2 pf x 2 day
| Install LCW hoses to header | Fluids Tech | 4 |  |  | 1
| Fill & test MI-14 skid system | Fluids Tech | 4 |  |  | 1
| Refill MI-14 Girardi box, and penetrations to Q-105 | Fluids Tech | 8 |  |  | 2 | cubic yards of poly beads to deal with
|  | Rad Tech | 8
|  | Bead Refill Crew | 24
z | Reinstall all hoses, brackets, any misc. | Fluids Tech | 8 |  |  | 1
| Fill & test system headers, Valve in kickers | Fluids Tech | 8 |  |  | 1 | NOT UNTIL READY! hydrostatic test not required nor a good idea
|  | Kicker Tech | 8
| Task Manager for above | Fluids Tech | 120 |  |  |  | Full length of construction + prep / wrap up
| Primary Beamline LCW Fill Line Pipe: | [5 empty] | New line, no removal necessary
| Install PBE fill line piping at Q-105 cross-over |  |  | Pipfitter | 32 | 3
| Install all hoses, brackets, any misc. | Fluids Tech | 8
| Fill & test system line | Fluids Tech | 4 |  |  |  | NOT UNTIL READY! hydrostatic test not required nor a good idea
| Task Manager for above | Fluids Tech | 24 |  |  |  | Full length of construction + prep / wrap up
Quadrupole Bus:
| Retrieve & stage quad bus, brackets, etc from storage and/or delivery | Fluids Tech | 8 | Pipfitter | 8
| Reinstall quadrupole bus & hangers in new location |  |  | Pipfitter / Electrician | 480 | 12 | 6 x 10 day, min 6 man crew, DS alcove walll @ Q-103 thru D-107-1 & -2, 8 lbs/ft , ttl ~ 550', ~ 4600 lbs
| On-site fab & braze of 7/8" bus connection x 2 at each quad | Fluids Tech | 32 |  |  |  | Often lab insisted to be Fermi techs for magnet connections
| Task Manager for above | Fluids Tech | 96 |  |  |  | Full length of construction + prep / wrap up
| Dipole Bus: | [5 empty] | min 6 man crew, Q-103 thru Q-107, 15 lbs/ft, 5 pair in sets @ ~ 600 lbs/set; requires sync w/ magnet installation
| Retrieve dipole bus, flags, brackets, etc from storage and/or delivery | Fluids Tech | 8 |  |  |  | 2 techs x .5 day
| Reinstall dipole bus & hangers in existing location at each quad |  |  | Pipfitter / Electrician | 200 | 6 | 5 crew x 5 day
| Reinstall & certify flags | Elec. Tech | 16 |  |  |  | 2 techs x 2 days
| Reinstall hoses | Fluids Tech | 16
| Task Manager for above | Fluids Tech | 40 |  |  |  | Full length of construction + prep / wrap up
| LABOR HOUR TOTALS - FERMILAB | TYPE | HOURS
|  | Bead Crew | 56
|  | Drafter/Designer | 608
|  | Elec. Eng'r | 64
|  | Elec. Tech | 32
|  | Fluids Eng'r | 428
|  | Fluids Tech | 856
|  | Machine Eng/Phys | 60
|  | Magnet Eng'r | 64
|  | Rad Tech | 24
| LABOR HOUR TOTALS - TRADE | SOLO CREW | COMBINED CREW - 3 | TOTAL |  |  | NOTES ON TRADES:
| Pipfitter - note 1 | 232 | 240 | 472 |  |  | 1 – PIPEFITTER SOLO CREW is primarily pipe work
| Electrician - note 2 | 240 | 440 | 680 |  |  | 2 – ELECTRICIAN SOLO CREW is estimate for Utilities work, refer to C. Gatusso work for more accurate values
3 – COMBINED CREW is for the mixed crew for Buswork
REFER TO C. GATTUSO ESTIMATE,
BOE Report 131.NSCFB.03.05.05_Installation Coordination

## Labor Tallies - Fermi
LBNF EXTRACTION LINE
MI-10 Q-103 thru Q-107 LCW & BUS RETROFIT
LABOR ESTIMATE - FERMILAB
|  | Bead Crew | 24
|  | Bead Crew | 32
|  |  | 56 | TOTAL
|  | Drafter/Designer | 400
|  | Drafter/Designer | 100
|  | Drafter/Designer | 40
|  | Drafter/Designer | 60
|  | Drafter/Designer | 8
|  |  | 608 | TOTAL
|  | Elec. Eng'r | 24
|  | Elec. Eng'r | 16
|  | Elec. Eng'r | 20
|  | Elec. Eng'r | 4
|  |  | 64 | TOTAL
| Reinstall & certify flags | Elec. Tech | 16 |  |  | 2 techs x 2 days
|  | Kicker Tech | 8 |  |  | 1 tech x 1 day
|  | Kicker Tech | 8
|  |  | 32 | TOTAL
| Final Design | Fluids Eng'r | 200
| Final Design Review | Fluids Eng'r | 60
| Installation | Fluids Eng'r | 120
| Installation Document Review & As-Builts | Fluids Eng'r | 40
| Inspect & prep penetrations between MI-14 to Q-105 for piping fit | Fluids Eng'r | 8
|  |  | 428 | TOTAL
| Shut down MI LCW system, isolate, drain and prep for long term shutdown | Fluids Tech | 48 |  |  | 3 techs x 2 days
| Disconnect dipoles, quads, remove hoses, flags, move to storage | Fluids Tech | 48 |  |  | 3 techs x 2 days
| Shut down MI-14 Fluorinert system, isolate, drain both LCW and Fuorinert sides of system | Fluids Tech | 48 |  |  | 3 techs x 2 days
| Empty MI-14 Girardi box, and penetrations to Q-105 | Fluids Tech | 16 |  |  | 2 days, cubic yards of poly beads to deal with
| Extract pipes from top of Girardi box thru MI-14, move to storage | Fluids Tech |  | Pipfitter | 80 | all 4 runs are around 50' length, 2 each at about a 40 degree angle thru the penetration, with spiders, and barely fit installation inside of roof by bending pipe what it would sag by weight
| Close & protect all open ends to systems | Fluids Tech | 16 | Pipfitter
| Task Manager for above | Fluids Tech | 120 |  |  | Full length of construction + prep / wrap up
| Reinstall all hoses, brackets, any misc. | Fluids Tech | 32 |  |  | 2 techs x 2 days
| Fill & test system headers | Fluids Tech | 16 |  |  | 2 techs x 1 day - DO NOT FILL UNTIL READY! hydrostatic test not required nor advisable
| Bring system to operational status | Fluids Tech | 16 |  |  | 2 techs x 1 day
| Valve in quad cells | Fluids Tech | 8 |  |  | 2 techs x 0.5 days
| Task Manager for above | Fluids Tech | 240 |  |  | 30 DAYS Full length of construction + prep / wrap up
| Retrieve & stage LCW and Fluorinert piping, brackets, etc from storage and/or delivery | Fluids Tech | 8 | Pipfitter | 8
| Install LCW hoses to header | Fluids Tech | 4
| Fill & test MI-14 skid system | Fluids Tech | 4
| Refill MI-14 Girardi box, and penetrations to Q-105 | Fluids Tech | 8 |  |  | cubic yards of poly beads to deal with
| Reinstall all hoses, brackets, any misc. | Fluids Tech | 8
| Fill & test system headers, Valve in kickers | Fluids Tech | 8 |  |  | NOT UNTIL READY! hydrostatic test not required nor a good idea
| Task Manager for above | Fluids Tech | 120 |  |  | Full length of construction + prep / wrap up
| Install all hoses, brackets, any misc. | Fluids Tech | 8
| Fill & test system line | Fluids Tech | 4 |  |  | NOT UNTIL READY! hydrostatic test not required nor a good idea
| Task Manager for above | Fluids Tech | 24 |  |  | Full length of construction + prep / wrap up
| Retrieve & stage quad bus, brackets, etc from storage and/or delivery | Fluids Tech | 8 | Pipfitter | 8
| On-site fab & braze of 7/8" bus connection x 2 at each quad | Fluids Tech | 32 |  |  | Often lab insisted to be Fermi techs for magnet connections
| Task Manager for above | Fluids Tech | 96 |  |  | Full length of construction + prep / wrap up
| Retrieve dipole bus, flags, brackets, etc from storage and/or delivery | Fluids Tech | 8 |  |  | 2 techs x .5 day
| Reinstall hoses | Fluids Tech | 16
|  | Task Manager | 12
| Task Manager for above | Fluids Tech | 40 |  |  | Full length of construction + prep / wrap up
|  |  | 856 | TOTAL
|  | Machine Eng/Phys | 60
|  |  | 60 | TOTAL
|  | Magnet Eng'r | 24
|  | Magnet Eng'r | 16
|  | Magnet Eng'r | 20
|  | Magnet Eng'r | 4
|  |  | 64 | TOTAL
|  | Rad Tech | 16
|  | Rad Tech | 8
|  |  | 24 | TOTAL
| LABOR TOTALS - FERMILAB | Bead Crew | 56
|  | Drafter/Designer | 608
|  | Elec. Eng'r | 64
|  | Elec. Tech | 32
|  | Fluids Eng'r | 428
|  | Fluids Tech | 856
|  | Machine Eng/Phys | 60
|  | Magnet Eng'r | 64
|  | Rad Tech | 24
| TASK | LABOR |  | LABOR |  | NOTES
|  | FERMI |  | TRADES
|  | Type | Hours | Type | Hours
LBNF EXTRACTION LINE
MI-10 Q-103 thru Q-107 LCW & BUS RETROFIT
LABOR ESTIMATE
FINAL DESIGN
PIPE & BUS REMOVAL
Global LCW Pipe:
| Stage and prep for Q100 tunnel work - LCW & bus removal |  |  | Pipfitter | 16 | 2 pf x 1 days
| Mark & cut LCW pipe, move to storage |  |  | Pipfitter | 80 | 2 pf x 5 days
Quadrupole Bus:
| Mark & cut quad bus, move to storage |  |  | Pipfitter | 120 | min 6 man crew, DS alcove walll @ Q-103 thru D-107-1 & -2, 8 lbs/ft ttl ~ 550', ~ 4600 lbs
| Remove header & bus wall brackets, move to storage |  |  | Pipfitter | 16
Dipole Bus:
| Remove dipole bus & brackets, move to storage |  |  | Pipfitter | 120 | min 6 man crew, Q-103 thru Q-107, 15 lbs/ft, 5 pair in sets @ ~ 600 lbs/set
MI-14 LCW & Fluorinert Pipe:
| Stage and prep for Q-105 & MI-14 work - LCW & Fluorinert removal |  |  | Pipfitter | 16 | 2 pf x 1 day
| Mark & cut pipes @ Q-105 |  |  | Pipfitter | 8 | 2 pf x 0.5 day
| Mark & cut pipes @ MI-14 |  |  | Pipfitter | 8 | 2 pf x 0.5 day
| Clean up, remove equipment, all work shelved |  | 4 | Pipfitter | 16
ENCLOSURE UTILITIES PREP FOR TO REINSTALL
Beneficial occupancy, all survey & layout work complete
| Move, lower, relocate grounding strap on outer enclosure (magnet) wall bottom |  |  | Electrician | 32 | 2 elec x 2 days
| Lower cable trays in center of overhead to enable installation of LCW crossover piping |  |  | Electrician | 64 | 4 elec x 2 days
| Move, lower, relocate lighting and conduits on Aisle side |  |  | Electrician | 80 | 2 elec x 5 days
| Raise & return cable trays in center of overhead to proper elevation |  |  | Electrician | 64 | 4 elec x 2 days
z
PIPE & BUS INSTALLATION
Global LCW Pipe:
| Stage and prep and layout for Q100 tunnel work - LCW & bus installation |  | 24 | Pipfitter |  | 3 pf x 1 day, placement of manifolds and taps, valves, on upper aisle side
| Retrieve header piping, brackets, etc from storage and/or delivery |  | 24 | Pipfitter |  | 3 pf x 1 day
| Remove, modify, and reinstall manifolds w/ crossovers |  | 160 | Pipfitter |  | 2 pf x 10 day
| Install header pipe hangers on aisle side |  | 32 | Pipfitter |  | 2 pf x 2 day
| Install header piping for Q-107 cross-over |  | 80 | Pipfitter |  | 2 pf x 5 day
| Install header piping from Q-103 alcove to Q-107 cross-over |  | 240 | Pipfitter |  | 3 pf x 10 day
MI-14 Fluorinert & LCW Pipe:
| Reinstall LCW and Fluorinert lines through penetrations to MI-14 system |  |  | Pipfitter | 120 | 3 pf x 5 Day
| Install Fluorinert lines to kickers |  |  | Pipfitter | 32 | 2 pf x 2 day
| Installl modified piping runs across ceiling, similar to manifolds |  |  | Pipfitter | 32 | 2 pf x 2 day
| Primary Beamline LCW Fill Line Pipe: |  |  |  |  | New line, no removal necessary
| Install PBE fill line piping at Q-105 cross-over |  |  | Pipfitter | 32
Quadrupole Bus:
| Reinstall quadrupole bus & hangers in new location |  |  | Pipfitter / Electrician | 480 | 6 x 10 day, min 6 man crew, DS alcove walll @ Q-103 thru D-107-1 & -2, 8 lbs/ft , ttl ~ 550', ~ 4600 lbs
| Dipole Bus: |  |  |  |  | min 6 man crew, Q-103 thru Q-107, 15 lbs/ft, 5 pair in sets @ ~ 600 lbs/set; requires sync w/ magnet installation
| Reinstall dipole bus & hangers in existing location at each quad |  |  | Pipfitter / Electrician | 200 | 5 crew x 5 day
REFER TO C. GATTUSO ESTIMATE,
BOE Report 131.NSCFB.03.05.05_Installation Coordination

## Labor Tallies - Trades
LBNF EXTRACTION LINE
MI-10 Q-103 thru Q-107 LCW & BUS RETROFIT
LABOR ESTIMATE - TRADES
| Move, lower, relocate grounding strap on outer enclosure (magnet) wall bottom |  |  | Electrician | 32 | 2 elec x 2 days
| Lower cable trays in center of overhead to enable installation of LCW crossover piping |  |  | Electrician | 64 | 4 elec x 2 days
| Move, lower, relocate lighting and conduits on Aisle side |  |  | Electrician | 80 | 2 elec x 5 days
| Raise & return cable trays in center of overhead to proper elevation |  |  | Electrician | 64 | 4 elec x 2 days
[5 empty] | 240 | TOTAL
| Stage and prep for Q100 tunnel work - LCW & bus removal |  |  | Pipfitter | 16 | 2 pf x 1 days
| Mark & cut LCW pipe, move to storage |  |  | Pipfitter | 80 | 2 pf x 5 days
| Mark & cut quad bus, move to storage |  |  | Pipfitter | 120 | min 6 man crew, DS alcove walll @ Q-103 thru D-107-1 & -2, 8 lbs/ft ttl ~ 550', ~ 4600 lbs
| Remove header & bus wall brackets, move to storage |  |  | Pipfitter | 16
| Remove dipole bus & brackets, move to storage |  |  | Pipfitter | 120 | min 6 man crew, Q-103 thru Q-107, 15 lbs/ft, 5 pair in sets @ ~ 600 lbs/set
| Stage and prep for Q-105 & MI-14 work - LCW & Fluorinert removal |  |  | Pipfitter | 16 | 2 pf x 1 day
| Mark & cut pipes @ Q-105 |  |  | Pipfitter | 8 | 2 pf x 0.5 day
| Mark & cut pipes @ MI-14 |  |  | Pipfitter | 8 | 2 pf x 0.5 day
| Extract pipes from top of Girardi box thru MI-14, move to storage | Fluids Tech |  | Pipfitter | 80 | all 4 runs are around 50' length, 2 each at about a 40 degree angle thru the penetration, with spiders, and barely fit installation inside of roof by bending pipe what it would sag by weight
| Close & protect all open ends to systems | Fluids Tech | 16 | Pipfitter
| Clean up, remove equipment, all work shelved |  | 4 | Pipfitter | 16
| Stage and prep and layout for Q100 tunnel work - LCW & bus installation |  | 24 | Pipfitter |  | 3 pf x 1 day, placement of manifolds and taps, valves, on upper aisle side
| Retrieve header piping, brackets, etc from storage and/or delivery |  | 24 | Pipfitter |  | 3 pf x 1 day
| Remove, modify, and reinstall manifolds w/ crossovers |  | 160 | Pipfitter |  | 2 pf x 10 day
| Install header pipe hangers on aisle side |  | 32 | Pipfitter |  | 2 pf x 2 day
| Install header piping for Q-107 cross-over |  | 80 | Pipfitter |  | 2 pf x 5 day
| Install header piping from Q-103 alcove to Q-107 cross-over |  | 240 | Pipfitter |  | 3 pf x 10 day
| Retrieve & stage LCW and Fluorinert piping, brackets, etc from storage and/or delivery | Fluids Tech | 8 | Pipfitter | 8
| Reinstall LCW and Fluorinert lines through penetrations to MI-14 system |  |  | Pipfitter | 120 | 3 pf x 5 Day
| Install Fluorinert lines to kickers |  |  | Pipfitter | 32 | 2 pf x 2 day
| Installl modified piping runs across ceiling, similar to manifolds |  |  | Pipfitter | 32 | 2 pf x 2 day
| Install PBE fill line piping at Q-105 cross-over |  |  | Pipfitter | 32
| Retrieve & stage quad bus, brackets, etc from storage and/or delivery | Fluids Tech | 8 | Pipfitter | 8
[5 empty] | 232 | TOTAL
| Reinstall quadrupole bus & hangers in new location (2 pf + 4 elec minimum) |  |  | Pipfitter / Electrician | 480 | 6 x 10 day, min 6 man crew, DS alcove walll @ Q-103 thru D-107-1 & -2, 8 lbs/ft , ttl ~ 550', ~ 4600 lbs
| Reinstall dipole bus & hangers in existing location at each quad (2 pf + 4 elec minimum) |  |  | Pipfitter / Electrician | 200 | 5 crew x 5 day
[5 empty] | 680 | TOTAL
| SPLIT TOTAL BETWEEN PF & ELEC |  |  | Pipfitter | 240
|  |  |  | Electrician | 440
| LABOR TOTALS - TRADES |  |  | Pipfitter | 472
|  |  |  | Electrician | 680
| TASK | LABOR |  | LABOR |  | NOTES
|  | FERMI |  | TRADES
|  | Type | Hours | Type | Hours
LBNF EXTRACTION LINE
MI-10 Q-103 thru Q-107 LCW & BUS RETROFIT
LABOR ESTIMATE
FINAL DESIGN
| Final Design | Fluids Eng'r | 200
|  | Magnet Eng'r | 24
|  | Elec. Eng'r | 24
|  | Drafter/Designer | 400
| Final Design Review | Fluids Eng'r | 60
|  | Magnet Eng'r | 16
|  | Elec. Eng'r | 16
|  | Drafter/Designer | 100
|  | Machine Eng/Phys | 60
| Installation | Fluids Eng'r | 120
|  | Magnet Eng'r | 20
|  | Elec. Eng'r | 20
|  | Drafter/Designer | 40
| Installation Document Review & As-Builts | Fluids Eng'r | 40
|  | Magnet Eng'r | 4
|  | Elec. Eng'r | 4
|  | Drafter/Designer | 60
PIPE & BUS REMOVAL
Global LCW Pipe:
| Shut down MI LCW system, isolate, drain and prep for long term shutdown | Fluids Tech | 48 |  |  | 3 techs x 2 days
| Disconnect dipoles, quads, remove hoses, flags, move to storage | Fluids Tech | 48 |  |  | 3 techs x 2 days
Quadrupole Bus:
Dipole Bus:
MI-14 LCW & Fluorinert Pipe:
| Shut down MI-14 Fluorinert system, isolate, drain both LCW and Fuorinert sides of system | Fluids Tech | 48 |  |  | 3 techs x 2 days
|  | Kicker Tech | 8 |  |  | 1 tech x 1 day
| Empty MI-14 Girardi box, and penetrations to Q-105 | Fluids Tech | 16 |  |  | 2 days, cubic yards of poly beads to deal with
|  | Rad Tech | 16
|  | Bead Removal Crew | 32
| Task Manager for above | Fluids Tech | 120 |  |  | Full length of construction + prep / wrap up
ENCLOSURE UTILITIES PREP FOR TO REINSTALL
Beneficial occupancy, all survey & layout work complete
PIPE & BUS INSTALLATION
Global LCW Pipe:
| Reinstall all hoses, brackets, any misc. | Fluids Tech | 32 |  |  | 2 techs x 2 days
| Fill & test system headers | Fluids Tech | 16 |  |  | 2 techs x 1 day - DO NOT FILL UNTIL READY! hydrostatic test not required nor advisable
| Bring system to operational status | Fluids Tech | 16 |  |  | 2 techs x 1 day
| Valve in quad cells | Fluids Tech | 8 |  |  | 2 techs x 0.5 days
| Task Manager for above | Fluids Tech | 240 |  |  | 30 DAYS Full length of construction + prep / wrap up
MI-14 Fluorinert & LCW Pipe:
| Inspect & prep penetrations between MI-14 to Q-105 for piping fit | Fluids Eng'r | 8
|  | Drafter/Designer | 8
|  | Task Manager | 12
| Install LCW hoses to header | Fluids Tech | 4
| Fill & test MI-14 skid system | Fluids Tech | 4
| Refill MI-14 Girardi box, and penetrations to Q-105 | Fluids Tech | 8 |  |  | cubic yards of poly beads to deal with
|  | Rad Tech | 8
|  | Bead Refill Crew | 24
z | Reinstall all hoses, brackets, any misc. | Fluids Tech | 8
| Fill & test system headers, Valve in kickers | Fluids Tech | 8 |  |  | NOT UNTIL READY! hydrostatic test not required nor a good idea
|  | Kicker Tech | 8
| Task Manager for above | Fluids Tech | 120 |  |  | Full length of construction + prep / wrap up
| Primary Beamline LCW Fill Line Pipe: |  |  |  |  | New line, no removal necessary
| Install all hoses, brackets, any misc. | Fluids Tech | 8
| Fill & test system line | Fluids Tech | 4 |  |  | NOT UNTIL READY! hydrostatic test not required nor a good idea
| Task Manager for above | Fluids Tech | 24 |  |  | Full length of construction + prep / wrap up
Quadrupole Bus:
| On-site fab & braze of 7/8" bus connection x 2 at each quad | Fluids Tech | 32 |  |  | Often lab insisted to be Fermi techs for magnet connections
| Task Manager for above | Fluids Tech | 96 |  |  | Full length of construction + prep / wrap up
| Dipole Bus: |  |  |  |  | min 6 man crew, Q-103 thru Q-107, 15 lbs/ft, 5 pair in sets @ ~ 600 lbs/set; requires sync w/ magnet installation
| Retrieve dipole bus, flags, brackets, etc from storage and/or delivery | Fluids Tech | 8 |  |  | 2 techs x .5 day
| Reinstall & certify flags | Elec. Tech | 16 |  |  | 2 techs x 2 days
| Reinstall hoses | Fluids Tech | 16
| Task Manager for above | Fluids Tech | 40 |  |  | Full length of construction + prep / wrap up
REFER TO C. GATTUSO ESTIMATE,
BOE Report 131.NSCFB.03.05.05_Installation Coordination

## Labor Tallies - Durations
LBNF EXTRACTION LINE
MI-10 Q-103 thru Q-107 LCW & BUS RETROFIT
LABOR ESTIMATE - LIST OF TASKS
|  | FERMI |  | TRADES |  | MIN. TASK
|  | LABOR |  | LABOR |  | DURATION | NOTES
|  | Type | Hours | Type | Hours | Days
FINAL DESIGN
Final Design Engineering:
|  | Fluids Eng'r | 200 |  |  | 25
|  | Magnet Eng'r | 24
|  | Elec. Eng'r | 24
|  | Drafter/Designer | 400 |  |  | 50
[6 empty] | 75 | TOTAL
Final Design Review:
|  | Fluids Eng'r | 60 |  |  | 8
|  | Magnet Eng'r | 16
|  | Elec. Eng'r | 16
|  | Drafter/Designer | 100 |  |  | 13
|  | Machine Eng/Phys | 60 |  |  | 21 | TOTAL
Installation:
|  | Fluids Eng'r | 120 |  |  | 15
|  | Magnet Eng'r | 20
|  | Elec. Eng'r | 20
|  | Drafter/Designer | 40 |  |  | 5
[6 empty] | 20 | TOTAL
Installation Document Review & As-Builts:
|  | Fluids Eng'r | 40 |  |  | 5
|  | Magnet Eng'r | 4
|  | Elec. Eng'r | 4
|  | Drafter/Designer | 60 |  |  | 8
[6 empty] | 13 | TOTAL
[6 empty] | 129 | TOTAL - FINAL DESIGN
PIPE & BUS REMOVAL
Global LCW Pipe:
| Shut down MI LCW system, isolate, drain and prep for long term shutdown | Fluids Tech | 48 |  |  | 2 | 3 techs x 2 days
| Disconnect dipoles, quads, remove hoses, flags, move to storage | Fluids Tech | 48 |  |  | 2 | 3 techs x 2 days
| Stage and prep for Q100 tunnel work - LCW & bus removal |  |  | Pipfitter | 16 | 1 | 2 pf x 1 days
| Mark & cut LCW pipe, move to storage |  |  | Pipfitter | 80 | 5 | 2 pf x 5 days
[6 empty] | 10 | TOTAL
Quadrupole Bus:
| Mark & cut quad bus, move to storage |  |  | Pipfitter | 120 | 5 | min 6 man crew, DS alcove walll @ Q-103 thru D-107-1 & -2, 8 lbs/ft ttl ~ 550', ~ 4600 lbs
| Remove header & bus wall brackets, move to storage |  |  | Pipfitter | 16 | 2
[6 empty] | 7 | TOTAL
Dipole Bus:
| Remove dipole bus & brackets, move to storage |  |  | Pipfitter | 120 | 5 | min 6 man crew, Q-103 thru Q-107, 15 lbs/ft, 5 pair in sets @ ~ 600 lbs/set
[6 empty] | 5 | TOTAL
MI-14 LCW & Fluorinert Pipe:
| Shut down MI-14 Fluorinert system, isolate, drain both LCW and Fuorinert sides of system | Fluids Tech | 48 |  |  | 2 | 3 techs x 2 days
|  | Kicker Tech | 8 |  |  |  | 1 tech x 1 day
| Empty MI-14 Girardi box, and penetrations to Q-105 | Fluids Tech | 16 |  |  | 2 | 2 days, cubic yards of poly beads to deal with
|  | Rad Tech | 16
|  | Bead Removal Crew | 32
| Stage and prep for Q-105 & MI-14 work - LCW & Fluorinert removal |  |  | Pipfitter | 16 | 2 | 2 pf x 1 day
| Mark & cut pipes @ Q-105 |  |  | Pipfitter | 8 |  | 2 pf x 0.5 day
| Mark & cut pipes @ MI-14 |  |  | Pipfitter | 8 |  | 2 pf x 0.5 day
| Extract pipes from top of Girardi box thru MI-14, move to storage | Fluids Tech |  | Pipfitter | 80 | 5 | all 4 runs are around 50' length, 2 each at about a 40 degree angle thru the penetration, with spiders, and barely fit installation inside of roof by bending pipe what it would sag by weight
| Close & protect all open ends to systems | Fluids Tech | 16 | Pipfitter |  | 1
| Clean up, remove equipment, all work shelved |  | 4 | Pipfitter | 16 | 2
| Task Manager for above | Fluids Tech | 120 |  |  |  | Full length of construction + prep / wrap up
[6 empty] | 14 | TOTAL
[6 empty] | 36 | TOTAL - PIPE & BUS REMOVAL
ENCLOSURE UTILITIES PREP FOR TO REINSTALL
Beneficial occupancy, all survey & layout work complete
| Move, lower, relocate grounding strap on outer enclosure (magnet) wall bottom |  |  | Electrician | 32 | 2 | 2 elec x 2 days
| Lower cable trays in center of overhead to enable installation of LCW crossover piping |  |  | Electrician | 64 | 2 | 4 elec x 2 days
| Move, lower, relocate lighting and conduits on Aisle side |  |  | Electrician | 80 | 5 | 2 elec x 5 days
| Raise & return cable trays in center of overhead to proper elevation |  |  | Electrician | 64 | 2 | 4 elec x 2 days
[6 empty] | 11 | TOTAL - UTILITIES
PIPE & BUS INSTALLATION
Global LCW Pipe:
| Stage and prep and layout for Q100 tunnel work - LCW & bus installation |  | 24 | Pipfitter |  | 1 | 3 pf x 1 day, placement of manifolds and taps, valves, on upper aisle side
| Retrieve header piping, brackets, etc from storage and/or delivery |  | 24 | Pipfitter |  | 1 | 3 pf x 1 day
| Remove, modify, and reinstall manifolds w/ crossovers |  | 160 | Pipfitter |  | 12 | 2 pf x 10 day
| Install header pipe hangers on aisle side |  | 32 | Pipfitter |  | 2 | 2 pf x 2 day
| Install header piping for Q-107 cross-over |  | 80 | Pipfitter |  | 5 | 2 pf x 5 day
| Install header piping from Q-103 alcove to Q-107 cross-over |  | 240 | Pipfitter |  | 12 | 3 pf x 10 day
| Reinstall all hoses, brackets, any misc. | Fluids Tech | 32 |  |  | 2 | 2 techs x 2 days
| Fill & test system headers | Fluids Tech | 16 |  |  | 1 | 2 techs x 1 day - DO NOT FILL UNTIL READY! hydrostatic test not required nor advisable
| Bring system to operational status | Fluids Tech | 16 |  |  | 1 | 2 techs x 1 day
| Valve in quad cells | Fluids Tech | 8 |  |  | 1 | 2 techs x 0.5 days
| Task Manager for above | Fluids Tech | 240 |  |  |  | 30 DAYS Min. Full length of construction + prep / wrap up
[6 empty] | 38 | TOTAL
MI-14 Fluorinert & LCW Pipe:
| Inspect & prep penetrations between MI-14 to Q-105 for piping fit | Fluids Eng'r | 8 |  |  | 2
|  | Drafter/Designer | 8
|  | Task Manager | 12
| Retrieve & stage LCW and Fluorinert piping, brackets, etc from storage and/or delivery | Fluids Tech | 8 | Pipfitter | 8 | 1
| Reinstall LCW and Fluorinert lines through penetrations to MI-14 system |  |  | Pipfitter | 120 | 7 | 3 pf x 5 Day
| Install Fluorinert lines to kickers |  |  | Pipfitter | 32 | 2 | 2 pf x 2 day
| Installl modified piping runs across ceiling, similar to manifolds |  |  | Pipfitter | 32 | 2 | 2 pf x 2 day
| Install LCW hoses to header | Fluids Tech | 4 |  |  | 1
| Fill & test MI-14 skid system | Fluids Tech | 4 |  |  | 1
| Refill MI-14 Girardi box, and penetrations to Q-105 | Fluids Tech | 8 |  |  | 2 | cubic yards of poly beads to deal with
|  | Rad Tech | 8
|  | Bead Refill Crew | 24
z | Reinstall all hoses, brackets, any misc. | Fluids Tech | 8 |  |  | 1
| Fill & test system headers, Valve in kickers | Fluids Tech | 8 |  |  | 1 | NOT UNTIL READY! hydrostatic test not required nor a good idea
|  | Kicker Tech | 8
| Task Manager for above | Fluids Tech | 120 |  |  |  | Full length of construction + prep / wrap up
[6 empty] | 20 | TOTAL
| Primary Beamline LCW Fill Line Pipe: | [5 empty] | New line, no removal necessary
| Install PBE fill line piping at Q-105 cross-over |  |  | Pipfitter | 32 | 3
| Install all hoses, brackets, any misc. | Fluids Tech | 8
| Fill & test system line | Fluids Tech | 4 |  |  |  | NOT UNTIL READY! hydrostatic test not required nor a good idea
| Task Manager for above | Fluids Tech | 24 |  |  |  | Full length of construction + prep / wrap up
[6 empty] | 3 | TOTAL
Quadrupole Bus:
| Retrieve & stage quad bus, brackets, etc from storage and/or delivery | Fluids Tech | 8 | Pipfitter | 8
| Reinstall quadrupole bus & hangers in new location |  |  | Pipfitter / Electrician | 480 | 12 | 6 x 10 day, min 6 man crew, DS alcove walll @ Q-103 thru D-107-1 & -2, 8 lbs/ft , ttl ~ 550', ~ 4600 lbs
| On-site fab & braze of 7/8" bus connection x 2 at each quad | Fluids Tech | 32 |  |  |  | Often lab insisted to be Fermi techs for magnet connections
| Task Manager for above | Fluids Tech | 96 |  |  |  | Full length of construction + prep / wrap up
[6 empty] | 12 | TOTAL
| Dipole Bus: | [5 empty] | min 6 man crew, Q-103 thru Q-107, 15 lbs/ft, 5 pair in sets @ ~ 600 lbs/set; requires sync w/ magnet installation
| Retrieve dipole bus, flags, brackets, etc from storage and/or delivery | Fluids Tech | 8 |  |  |  | 2 techs x .5 day
| Reinstall dipole bus & hangers in existing location at each quad |  |  | Pipfitter / Electrician | 200 | 6 | 5 crew x 5 day
| Reinstall & certify flags | Elec. Tech | 16 |  |  |  | 2 techs x 2 days
| Reinstall hoses | Fluids Tech | 16
| Task Manager for above | Fluids Tech | 40 |  |  |  | Full length of construction + prep / wrap up
[6 empty] | 6 | TOTAL
[6 empty] | 79 | TOTAL - PIPE & BUS INSTALLATION
LABOR TASK DURATION - TOTALS
| FINAL DESIGN |  |  |  |  | 129
| Final Design Engineering |  |  |  |  | 75
| Final Design Review |  |  |  |  | 21
| Installation |  |  |  |  | 20
| Installation Document Review & As-Builts |  |  |  |  | 13
| PIPE & BUS REMOVAL |  |  |  |  | 36
| Global LCW Pipe |  |  |  |  | 10
| Quadrupole Bus |  |  |  |  | 7
| Dipole Bus |  |  |  |  | 5
| MI-14 LCW & Fluorinert Pipe |  |  |  |  | 14
| ENCLOSURE UTILITIES PREP FOR TO REINSTALL |  |  |  |  | 11
| PIPE & BUS INSTALLATION |  |  |  |  | 79
| Global LCW Pipe |  |  |  |  | 38
| MI-14 Fluorinert & LCW Pipe |  |  |  |  | 20
| Primary Beamline LCW Fill Line Pipe |  |  |  |  | 3
| Quadrupole Bus |  |  |  |  | 12
| Dipole Bus |  |  |  |  | 6
| TOTAL DURATION, Days |  |  |  |  | 255
REFER TO C. GATTUSO ESTIMATE,
BOE Report 131.NSCFB.03.05.05_Installation Coordination