## Slide 1
Dean (Chip) Edstrom
11/18/2022
IOTA Proton Injector Update

## Slide 2: IPI Summary – Source Commissioning
HV ORC Conclusion
  HV Enclosure items remaining:
    ✓ Redo CU Ground bar configuration
    ✓ HV Enclosure Door latches installed
    🕑 HV Enclosure Door interlock wiring and interface needs to be completed.
    🕑 10 kV (Extractor) Supply Output & remote-on kludge touch-up (Jeff Simmons)
    🕑 Extractor Modulator / Spark Protection boxes (Jeff Simmons)
    ✓ 50 kV Bridge Supports in hand… will cut bridge to length upon installation
    ❌ 120 VAC distribution only set up for only 20A??? Meeting with Kermit early next week…
  Next steps
    Button-up / Evaluation by Dave Mertz / Final 50kV Test
Source Characterization ORC Preparation
  Rad Safety Status (Dan)

## Slide 3: IPI Summary – Bigger picture
Beamline Installation
  MEBT Layout (Steve Wesseln, Sasha R.)
  Cable Acquisition in progress
    All non-stock cable reqs in
  No initial cable pull contract estimate
  BPM pre-amp enclosures being fabricated (Brian Fellenz)
RF
  600A Windowed & Kirk Key’d Disconnect
    Rescheduled to ship on 12/12, but schedule continues to slip…
    Modulator controls to follow (EE Support)
  HLRF
    Ding continued evaluation of the buncher SSA
  LLRF
    Met with Euclid… Upgrade quote requested.