## Slide 1: PIP PMG
Project Controls
Elmie Evans-Peoples

## Slide 2: Project Controls – Agenda
FY12 Summary
Schedule Modification Process
FY13 Budget Process
RLS Summary
Tracking Progress
  Schedule Updates
  Budget & Effort Reports
  Planned Budget vs Actuals
Going Forward
Notes: Add FY12 labor and M&S year end, FY12 FTE by category chart (include comment about budget changes thru the year that cause us to redo RLS and the process we have to go thru everytime)

## Slide 3: FY12 Summary – RLS Plan vs Actual
Chart: FY12 FTEs by Division
| AD | APC | PPD | TD | FESS | CS | DIR
RLS Plan | 41.1748 | 2.6886 | 0.96267 | 2.9679 | 0 | 0 | 0
Actual | 30.9359 | 1.635 | 1.2627 | 3.1045 | 0.27404 | 0 | 0
Chart: FY12 FTEs by OHAP Category
| Alignment | Civil Engineer | Contractor | Design | Electrical Engineer | Electrical Technician | Facilities Management | Guest Scientist | Information Technology | Mechanical Engineer | Mechanical Technician | Operations | Other Technical | Postdoctoral Research Associate | Procurement | Project Management | Scientist
RLS Plan | 0.17873 | 0.31376 | 0.28452 | 1.5721 | 10.8218 | 10.8076 | 0.1 | 0 | 0.47574 | 2.66 | 8.1467 | 1.6004 | 0.81118 | 0 | 0.040498 | 0.044796 | 9.9316
Actual | 0.01 | 0.19 | 1.58 | 8.35 | 10.4 | 0.088801 | 0.17036 | 0.08 | 2.78 | 3.99 | 3.08 | 1.89 | 0.14 | 0.24 | 4.25
Notes: For this summary slide, make sure I show all divisions even the ones at zero

## Slide 4: Schedule Modifications
Strategically match new funding profile and refresh cost estimates
Revised sub-projects w/corresponding manager based on work to complete (FY13 and beyond)
Reviewing PIP labor/M&S needs as a whole and prioritizing resources to meet funding profile and FY13 budget upload allocations
Goal is to complete this effort in the next 2-3 weeks.
Funding Profile ($M) |  |  |  |  | 
FY13 | FY14 | FY15 | FY16 | FY17 | FY18
7.017 | 8.7 | 15 | 16 | 16 | 11
Notes: Maybe add a slide that shows the process for figuring this out
Show what the labor and M&S breakdown is right now FY13 and beyond and mention we’re making progress

## Slide 5: Schedule Modification Process
1-2 Weeks
2 Weeks
1 Week
3 Weeks
Strategically delay tasks based on priority due to funding constraints
Verify changes with managers
Upload new estimates & logic
Review cost estimates & logic with managers
Baseline RLS to use for reference in tracking progress
We are currently at this point
Delay M&S purchases w/lowest priority
Check if meets guidance (apply overhead)
Delay effort w/lowest priority
Check if meets guidance (apply overhead)
Notes: Maybe add a slide that shows the process for figuring this out
Show what the labor and M&S breakdown is right now FY13 and beyond and mention we’re making progress

## Slide 6: Current RLS Summary – Schedule Info
WBS | Name | Start | Finish | % Work Complete | M&S Overhead | M&S | FTEs | Labor | Labor Overhead | Total Costs
1 | PIP | Jun-05 | Dec-18 | 16% | $8,286,242 | $40,638,753 | 193.47 | $19,198,318 | $18,430,385 | $86,553,698
1.00 | Program Management | Oct-11 | Dec-18 | 15% | $37,518 | $184,000 | 12.63 | $1,654,217 | $1,588,048 | $3,463,783
1.01 | Linac | Aug-11 | Dec-18 | 7% | $4,461,804 | $21,882,315 | 46.47 | $4,879,677 | $4,684,490 | $35,908,286
1.01.01 | 200MHz RF Power System | Nov-11 | Dec-18 | 3% | $4,263,640 | $20,910,445 | 41.02 | $4,309,984 | $4,137,585 | $33,621,653
1.01.01.01 | High Level RF | Feb-12 | Aug-16 | 10% | $2,978,979 | $14,610,000 | 3.34 | $337,417 | $323,920 | $18,250,316
1.01.01.02 | Linac Modulator | Jan-12 | Dec-18 | 3% | $1,019,774 | $5,001,346 | 37.68 | $3,971,323 | $3,812,470 | $13,804,914
1.01.01.03 | 7835 Procurement | Nov-11 | Aug-14 | 94% | $264,886 | $1,299,099 | 0.01 | $1,243 | $1,193 | $1,566,422
1.01.02 | Accelerator Physics | Aug-11 | May-15 | 24% | $79,470 | $389,750 | 3.81 | $425,919 | $408,882 | $1,304,021
1.01.02.01 | Simulations and Studies | Oct-11 | May-15 | 34% | $0 | $0 | 1.60 | $181,151 | $173,905 | $355,056
1.01.02.03 | Linac Notch Creation | Aug-11 | Dec-14 | 16% | $79,470 | $389,750 | 2.21 | $244,769 | $234,978 | $948,967
1.01.03 | Instrumentation | Aug-11 | May-13 | 67% | $8,156 | $40,000 | 0.56 | $64,734 | $62,145 | $175,035
1.01.05 | Utilities | Nov-11 | Jan-14 | 63% | $110,538 | $542,120 | 1.08 | $79,041 | $75,879 | $807,579
1.02 | Booster | Jun-05 | Sep-18 | 17% | $3,729,522 | $18,290,938 | 130.36 | $12,251,107 | $11,761,063 | $46,032,630
1.02.01 | RF | Oct-11 | Sep-18 | 4% | $3,178,873 | $15,590,355 | 83.73 | $7,244,593 | $6,954,809 | $32,968,631
1.02.01.01 | Anode Supply | Oct-12 | Dec-13 | 0% | $142,730 | $700,000 | 0.60 | $66,613 | $63,948 | $973,291
1.02.01.02 | Bias Supply | Jan-12 | Jul-15 | 4% | $82,172 | $403,000 | 4.62 | $417,943 | $401,225 | $1,304,340
1.02.01.04 | Cavity Test Stand | Jan-12 | Jul-12 | 100% | $0 | $0 | 0.09 | $9,021 | $8,660 | $17,681
1.02.01.05 | Cavity & Tuner Refurbishment | Oct-11 | Apr-15 | 18% | $63,366 | $310,770 | 11.40 | $587,161 | $563,675 | $1,524,972
1.02.01.06 | New Tuners | Oct-11 | Dec-15 | 5% | $443,806 | $2,176,585 | 6.29 | $525,997 | $504,957 | $3,651,345
1.02.01.07 | New Cavities | Oct-11 | Sep-18 | 1% | $2,446,800 | $12,000,000 | 60.40 | $5,613,999 | $5,389,439 | $25,450,238
1.02.01.08 | Cavity 1013 | Dec-11 | Feb-13 | 8% | $0 | $0 | 0.34 | $23,860 | $22,906 | $46,766
1.02.02 | Accelerator Physics | Jun-10 | Sep-16 | 26% | $97,604 | $478,687 | 20.71 | $2,688,898 | $2,581,342 | $5,846,531
1.02.02.01 | Simulations & Studies | Oct-11 | Sep-16 | 19% | $14,273 | $70,000 | 14.83 | $1,903,471 | $1,827,332 | $3,815,076
1.02.02.02 | Alignment & Aperture | Apr-11 | Feb-14 | 48% | $2,039 | $10,000 | 1.10 | $267,474 | $256,775 | $536,288
1.02.02.03 | Booster Notcher | Oct-11 | Nov-14 | 56% | $78,030 | $382,687 | 2.59 | $236,233 | $226,784 | $923,734
1.02.02.04 | Booster Cogging | Aug-11 | Oct-14 | 18% | $1,223 | $6,000 | 1.54 | $211,258 | $202,808 | $421,289
1.02.02.05 | Booster Collimation | Oct-13 | Dec-13 | 0% | $1,020 | $5,000 | 0.31 | $37,482 | $35,983 | $79,484
1.02.02.06 | Radiation Shielding | Jun-10 | Jun-13 | 62% | $1,020 | $5,000 | 0.34 | $32,981 | $31,662 | $70,662
1.02.03 | Instrumentation | Oct-12 | Mar-16 | 0% | $25,895 | $127,000 | 5.38 | $526,729 | $505,660 | $1,185,284
1.02.05 | Utilities | Nov-11 | Dec-14 | 39% | $231,957 | $1,137,600 | 2.82 | $291,658 | $279,992 | $1,941,206
1.02.07 | Solid State Upgrade | Jun-05 | Jul-13 | 71% | $195,193 | $957,296 | 17.71 | $1,499,230 | $1,439,261 | $4,090,979
1.03 | RFQ Injector | Oct-11 | Dec-12 | 82% | $57,398 | $281,500 | 4.01 | $413,317 | $396,784 | $1,148,999
Notes: Try to make this a process chart
Remove decimals for all except for FTEs

## Slide 7: Current RLS Summary – Cost Overview
 | FY13 | FY14 | FY15 | FY16 | FY17 | FY18 | FY19
M&S | $2,782,201 | $5,781,091 | $7,049,507 | $8,720,371 | $10,145,935 | $758,437 | $0
M&S Overhead | $567,291 | $1,178,764 | $1,437,394 | $1,778,084 | $2,068,756 | $154,645 | $0
Total M&S | $3,349,492 | $6,959,855 | $8,486,901 | $10,498,455 | $12,214,691 | $913,082 | $0
Labor SWF | $2,489,561 | $3,347,830 | $3,153,852 | $2,607,813 | $1,669,790 | $2,669,844 | $112,699
Labor Overhead | $2,389,979 | $3,213,917 | $3,027,698 | $2,503,500 | $1,602,998 | $2,563,050 | $108,191
Total Labor | $4,879,540 | $6,561,747 | $6,181,550 | $5,111,313 | $3,272,788 | $5,232,894 | $220,890
Labor FTEs | 26.60 | 34.63 | 31.55 | 22.42 | 16.73 | 27.95 | 1.16
Total Direct Costs | $5,271,762 | $9,128,921 | $10,203,359 | $11,328,184 | $11,815,725 | $3,428,281 | $112,699
Total Overhead Costs | $2,957,269 | $4,392,681 | $4,465,092 | $4,281,584 | $3,671,755 | $2,717,696 | $108,191
Total Costs | $8,229,031 | $13,521,602 | $14,668,451 | $15,609,768 | $15,487,480 | $6,145,977 | $220,890
Funding Guidance | $7,017,000 | $8,700,000 | $15,000,000 | $16,000,000 | $16,000,000 | $11,000,000 | 
Difference | -$1,215,031 | -$4,821,602 | $331,549 | $390,232 | $512,520 | $4,854,023 | -$220,890
Notes: Try to make this a process chart

## Slide 8: FY13 Budget Process
Extract M&S and Labor needs from RLS
Check RLS numbers w/managers
Provide budget sheet to D/S/C
Modify numbers as needed
SWF and M&S w/overhead
FTE % and names
OHAP Role in place of name
D/S/C provide PIP w/labor allocations by FTE%, name and OHAP category/role
Review labor allocations and provide modifications to D/S/C
Provide task codes for allocations to D/S/C
Upload allocations to RLS
Use names and FTE %
Schedule modification process (last steps)
Present FY plan to all stakeholders
Notes: Try to make this a process chart

## Slide 9: FY13 Budget vs RLS Overview
 | RLS Plan | Upload
M&S | $2,782,201 | $1,874,050
M&S Overhead | $567,291 | $853,209
Total M&S | $3,349,492 | $2,727,259
Labor SWF | $2,489,561 | $2,431,324
Labor Overhead | $2,389,979 | $1,858,417
Total Labor | $4,879,540 | $4,016,340
Labor FTEs | 26.60 | 23.28
Total Direct Costs | $5,271,762 | $4,305,374
Total Overhead Costs | $2,957,269 | $2,711,626
Total Costs | $8,229,031 | $7,017,000
Chart: FY13 FTEs by Division
| AD | APC | PPD | TD | Total
D/S/C Allocations | 20.18 | 1.6 | 0.22 | 1.28 | 22.28
RLS Plan | 22.0286 | 1.7441 | 0.21215 | 1.848 | 25.8329
Low due to special overhead for SSU labor.
High due to overhead to complete SSU.
Notes: Try to make this a process chart

## Slide 10: Tracking Progress - Monthly Updating Process
Day 1
Dump Data into Template
Distribute Template to Managers
Day 8
Return Templates to L2 Managers
Day 15
Return Templates to Project Controls
Day 22
Complete Schedule Update
1st Wednesday after Update
Present Updated Schedule at PIP Meeting
Save Current Schedule

## Slide 11: Tracking Progress – Monthly Update Template
Kiyomi Seiya | 10 |  |  | Enter % Complete |  | ENTER REMAINING DURATION I | 12/1/2012 | ENTER ACTUAL START | ENTER NEW START |  | ENTER ACTUAL FINISH | 
Task ID | WBS | Task Name | Previous % Complete | Current % Complete | Duration | Remaining Duration | Start | Actual Start | Est New Start | Finish | Actual Finish | Comments/Concerns
2630 | 1.2.2.2 | Alignment and Aperture | 55% |  | 731 d |  | 4/1/2011 |  |  | 2/20/2014 |  | 
2648 | 0 | FY13 M&S | 0% | #NAME? | 1 d | #NAME? | 10/1/2012 | #NAME? | #NAME? | 10/1/2012 | #NAME? | 
2760 | 1.2.2.4 | Booster Cogging | 32% |  | 681 d |  | 8/1/2011 |  |  | 4/11/2014 |  | 
2761 | 0 | Develop FPGA and DSP code for FPGA board | 40% | #NAME? | 330 d | #NAME? | 10/3/2011 | 10/3/2011 | #NAME? | 3/29/2013 | #NAME? | 
2762 | 0 | Slot 0 card/ ACNET control support as needed | 40% | #NAME? | 420 d | #NAME? | 8/1/2011 | 8/1/2011 | #NAME? | 3/29/2013 | #NAME? | 
2763 | 0 | Beam studies | 10% | #NAME? | 260 d | #NAME? | 10/3/2011 | 10/3/2011 | #NAME? | 10/11/2012 | #NAME? | 
2764 | 0 | Control Unit Board | 54% | #NAME? | 167 d | #NAME? | 4/2/2012 | 4/2/2012 | #NAME? | 11/27/2012 | #NAME? | 
2766 | 0 | Fabricate CAMAC cables and connectors | 50% | #NAME? | 167 d | #NAME? | 4/2/2012 | 4/2/2012 | #NAME? | 11/27/2012 | #NAME? | 
2768 | 0 | Pull cables for control unit boards installation | 50% | #NAME? | 167 d | #NAME? | 4/2/2012 | 4/2/2012 | #NAME? | 11/27/2012 | #NAME? | 
2769 | 0 | Install control unit boards | 0% | #NAME? | 10 d | #NAME? | 11/12/2012 | #NAME? | #NAME? | 11/27/2012 | #NAME? | 
Notes: delete last two columns can add comments

## Slide 12: Tracking Progress – Budget & Effort Reports
Budget Reports
  Issued on a monthly basis from AD Headquarters
  Used to load M&S actuals into RLS at CTC level
  Compare actuals to plan
  Help managers track FY spending (M&S)
Effort Reports
  Issued on a weekly basis from AD Headquarters
  Compare labor effort to plan and verify SWF charges (people reporting appropriately)
  Used to determine FTE % to compare to budget allocations to verify PIP receiving labor agreed to
    Request more labor when FTE% low

## Slide 13: Tracking Progress – Identifying Trends/Issues
Chart: 
| 9/1/2011 | 10/1/2011 | 11/1/2011 | 12/1/2011 | 1/1/2012 | 2/1/2012 | 3/1/2012 | 4/1/2012 | 5/1/2012 | 6/1/2012 | 7/1/2012 | 8/1/2012 | 9/1/2012
AD | 12.3571 | 27.6973 | 30.9116 | 22.0197 | 30.9667 | 27.6973 | 30.9813 | 35.6643 | 27.0731 | 31.0762 | 35.1922 | 31.5259 | 28.9099
APC | 0.30952 | 1.3571 | 2.9755 | 2.6565 | 3.102 | 2.0884 | 2.102 | 1.915 | 0.85034 | 0.92245 | -1.6156 | 1.3694 | 1.6313
FESS | 0.27211 | 0.45578 | 0.21769 | 0.14286 | 0.32313 | 0.34014 | 0.31973 | 0.34014 | 0.36735 | 0.51701
PPD | 0.52721 | 1.2313 | 1.034 | 1.7823 | 1.6156 | 0.59864 | 0.10884 | 1.2109 | 1.3163 | 1.3197 | 1.2381 | 1.0748 | 2.1293
TD | 4.5068 | 4.5544 | 3.4966 | 2.5697 | 2.2296 | 3.0697 | 2.2619 | 6.4728 | 2.102 | 1.619 | 1.3571 | 1.4796 | 1.619
Chart: 
| 9/1/2011 | 10/1/2011 | 11/1/2011 | 12/1/2011 | 1/1/2012 | 2/1/2012 | 3/1/2012 | 4/1/2012 | 5/1/2012 | 6/1/2012 | 7/1/2012 | 8/1/2012 | 9/1/2012
Alignment | 0.098639
Civil Engineer | 0.27211 | 0.45578 | 0.21769 | 0.13605 | 0.15646 | 0.26531 | 0.12925 | 0.19728 | 0.15646 | 0.20408
Design | 0.41497 | 0.80952 | 1.1871 | 1.1293 | 2.6531 | 1.5816 | 1.9864 | 1.8946 | 1.2041 | 1.6837 | 1.869 | 1.1531 | 1.381
Electrical Engineer | 3.8214 | 6.7483 | 7.9643 | 6.4915 | 9.0789 | 7.7687 | 8.3895 | 9.9024 | 7.3588 | 6.7228 | 10.9014 | 8.5561 | 6.6684
Electrical Technician | 5.1361 | 11.4932 | 8.2092 | 5.6463 | 8.2517 | 8.2211 | 10.4167 | 12.7619 | 9.2823 | 11.5578 | 10.585 | 9.7993 | 10.9966
Facilities Management | 0.0068027 | 0.12925 | 0.07483 | 0.19048 | 0.14286 | 0.21088 | 0.31293
Guest Scientist | 0.054422 | 0.21088 | 0.047619 | 0.24218 | 0.4966 | 0.46122 | 0.53605
Information Technology | 0.0017007 | 0.020408 | 0.02381 | 0.010204 | 0.0068027 | 0.027211 | 0.51701 | 0.29932 | 0.013605
Mechanical Engineer | 1.3946 | 2.4252 | 3.7007 | 2.4626 | 3.1973 | 2.8844 | 2.4626 | 3.2075 | 2.7041 | 2.3435 | 2.2891 | 1.7891 | 2.5442
Mechanical Technician | 3.2857 | 7.0646 | 5.619 | 4.5 | 4.8163 | 2.3367 | 1.9286 | 5.0136 | 2.8129 | 2.4014 | 1.9082 | 2.6701 | 3.4524
Operations | 1.381 | 2.3946 | 3.0136 | 2.4252 | 2.1769 | 2.5748 | 2.7755 | 2.5578 | 2.3367 | 4.2398 | 4.085 | 4.4269 | 2.6497
Other Technical | 1.7619 | 1.6395 | 1.7075 | 1.352 | 1.0051 | 2.2398 | 1.9354 | 3.9524 | 1.6395 | 1.5204 | 1.0952 | 1.2415 | 1.5986
FY12 Actual FTEs
FY12 Actual FTEs

## Slide 14: Going Forward
Monthly Status Updates
  Continue to streamline the process
  Provide mechanism for management to analyze data
    Create pivot table with all the data to make it easier to analyze the data through charts and graphs by just selecting one’s particular interest
    Will require updating on a weekly basis (effort reports are weekly)
Budget and Effort Reports
  Cater reports to meet PIP reporting and data analysis needs
  Budget Reports will show overhead financial information starting this FY13
Complete Schedule Modifications
  Ensure RLS labor and M&S inline with FY13 budget upload and funding guidance in the outer years (focus on FY14)

## Slide 15
Chart: FY12 Actual FTEs By Division
| AD | APC | FESS | PPD | TD | DIR | WDRS | BSS | CMS | ESH | FS | CPA | CS
Total | 30.9359 | 1.635 | 0.27404 | 1.2627 | 3.1045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Chart: Actual FY12 FTEs by OHAP Category
| Alignment | Civil Engineer | Design | Electrical Engineer | Electrical Technician | Facilities Management | Guest Scientist | Information Technology | Mechanical Engineer | Mechanical Technician | Operations | Other Technical | Postdoctoral Res Assoc | Project Management | Scientist
Total | 0.0082014 | 0.18213 | 1.5754 | 8.3454 | 10.1734 | 0.088801 | 0.17036 | 0.076499 | 2.7774 | 3.9751 | 3.0795 | 1.8865 | 0.13914 | 0.24038 | 4.2454

## Slide 16: RLS – Baseline Summary
PIP Baseline Schedule Cost/Labor Summary |  |  |  |  | 
WBS | M&S | M&S - OH | FTEs | Labor | Labor - OH
1 PIP | $40,553,583 | $47,853,228 | 182.4 | $29,179,510 | $54,857,478
1.0 Program Management | $0 | $0 | 16.7 | $2,671,819 | $5,023,020
1.1 Linac | $21,564,066 | $25,445,598 | 35.1 | $5,611,315 | $10,549,272
1.1.1 200MHz RF Power System | $20,346,066 | $24,008,358 | 27.6 | $4,419,403 | $8,308,477
1.1.2 Accelerator Physics | $515,000 | $607,700 | 3.8 | $603,206 | $1,134,028
1.1.3 Instrumentation | $40,000 | $47,200 | 2.2 | $356,742 | $670,675
1.1.5 Utilities | $663,000 | $782,340 | 1.4 | $231,964 | $436,092
1.2 Booster | $18,708,017 | $22,075,460 | 126.8 | $20,290,405 | $38,145,962
1.2.1 RF | $16,086,472 | $18,982,037 | 81.6 | $13,060,677 | $24,554,073
1.2.2 Accelerator Physics | $601,790 | $710,112 | 21.1 | $3,379,953 | $6,354,312
1.2.3 Instrumentation | $127,000 | $149,860 | 5.3 | $843,446 | $1,585,679
1.2.5 Utilities | $1,185,820 | $1,399,268 | 2.2 | $347,152 | $652,646
1.2.7 Solid State Upgrade | $706,935 | $834,183 | 16.6 | $2,659,178 | $4,999,255
1.3 RFQ Injector | $281,500 | $332,170 | 3.8 | $605,970 | $1,139,224
PIP Baseline Schedule Major Milestone Summary | 
Milestone | Schedule Date
12 Hz Operation | 
15Hz Operation | 
Double Throughput | 
> 85% Reliability | 

## Slide 17: Tracking Progress – Quarterly Reports
Quarterly Reports
  1st report published in May 2012
  Used to inform PIP stakeholders about the project status; budget and schedule

## Slide 18: FY13 Budget Process
Using partially updated RLS and input from L3/L4 managers PIP Management provided labor and M&S budget requests to D/S/C as other projects due
D/S/C responded with FTE allocations, corresponding names and SWF; PIP responded with modifications or agreement (iterative process)
Currently updating the RLS; along with modifications mentioned above, to reflect actual labor allocations by D/S/C and M&S approved by AD
Goal is to complete this effort in the next two weeks
Notes: Try to make this a process chart

## Slide 19: Current RLS Summary – Gantt Chart
Notes: Try to make this a process chart