## Slide 1
Status Update – Jan 26, 2022

## Slide 2: SSR2 Cavity
Cavity Component Forming
  End Wall copper trial under progress
EBW Trials
  Trials completed; Acceptable parameters achieved for all weld types
  WPS, PQR completed for 3.2 mm Nb-Nb, 4.0 mm, 4.7mm Nb-Nb
  Weld coupon EB weld completed for 4.0 mm Nb-Ti Grade 2; Testing u/p.
  Weld coupon EB weld u/p for 13mm Nb-Ti Grade 5.
Nb Components Machining
  Nb 4.7 mm sheet cutting completed.
  Components which can be made from tubes completed.
Weld Fixture scheme and Drawing completed
  Manufacturing Under Progress

## Slide 3: SSR2 Tuner
Process Sheet Prepared
Manufacturing under progress; 45% Complete