## Assessment
Prevention through Design (PtD) Hazard Risk Assessment
Date: | 2023-04-11 | Assessed By: | Alex Chen, Richard Andrews, Raul Campos, Lucy Nobrega
System: | PIP-II Vacuum Systems
Identifier | Potential Hazard Description | Life Cycle Stage | Who is at risk? | What is at risk? | Pre-Mitigation Severity | Pre-Mitigation Probability | Pre-Mitigation Risk Score | Mitigations | Post-Mitigation Severity | Post-Mitigation Probability | Post-Mitigation Risk Score | Status of Mitigation Implementation | Comments
1 | Bellows fail | Multiple | Personnel | Vacuum systems, beam instrumentation, Cryomodules | Minimal | D - Unlikely | 5 - Negligible | - Define cycle requirements for bellows, develop acceptance criteria, so fatigue is unlikely - Corrosion most likely root cause of any failure - Once leak checking and bellows pass acceptance criteria, bellows are fine. - Most bellows do no cycle during operations - Properly constrain bellows prior to pumpdown | Minimal | E - Rare | 5 - Negligible | Integrated into Design | Per experience, no past injuries to personnel
2 | Vacuum optical viewports fail | Operations | Process | Vacuum Systems | High | D - Unlikely | 3 - Moderate | - Develop viewports specifications and acceptance testing criteria. - Continue to collaborate with Beam Instrumentation sytems to define risk mitigation from laser damage - Add viewports protectors (even just red conflat caps) for protection during shutdowns. - Minimize use of viewports if note needed (including for other subsystems) | Low | E - Rare | 5 - Negligible | Integrated into Design | Mostly damage to equipment, not to personnel
2 | Vacuum windows fail | Operations | Process | Vacuum Systems | Low | D - Unlikely | 4 - Low | Develop vacuum windows specifications and acceptance testing criteria | Low | E - Rare | 5 - Negligible | Integrated into Design
3 | Mechanical pump support structure fails due to excesive vibration | Operations | Personnel | Insulating vacuum systems, Cryomodules | Minimal | D - Unlikely | 5 - Negligible | Design vibration dampening mechanism into strucure | Low | E - Rare | 5 - Negligible | Integrated into Design
4 | Cleanroom stops working or particles present in clean volumes | Fabrication | Process | Vacuum systems | Minimal | D - Unlikely | 5 - Negligible | Develop QC process and document process in Traveler. Follow regular maintenance. Checking cleanroom equipment before use. | Minimal | E - Rare | 5 - Negligible | Specifications and Interfaces Updated | Affects schedule more than personnel
5 | Vacuum assemblies are dropped during assembly or installation | Multiple | Personnel | Vacuum Systems | Minimal | C - Possible | 4 - Low | Develop QC process and document process in Traveler. Train technicians. Technicians follow procedures. | Minimal | D - Unlikely | 5 - Negligible | Specifications and Interfaces Updated
6 | Hydrogen exhast from ion source scroll pump could increase risk of fire if in high concentrations | Multiple | Personnel, Environment | Personnel, Tunnel, Equipment | Low | D - Unlikely | 4 - Low | Exhaust to outside enclosure | Low | E - Rare | 5 - Negligible | Integrated into Design | Total amount of H would be low even if not exhausted to outside
7 | Not having the necessary tools lowers efficiency of personnel during assembly and installation | Multiple | Efficiency of personnel | Vacuum systems | Minimal | C - Possible | 4 - Low | Use the correct equipment. Ensure that all the necessary tools are available. Follow procedure. Train technicians | Minimal | D - Unlikely | 5 - Negligible | Specifications and Interfaces Updated
8 | Difficult to assemble vacuum components inside portable cleanroom due to small working space | Multiple | Efficiency of personnel | Vacuum systems | Minimal | C - Possible | 4 - Low | Ensure that enough spacing is available for threaded studs for assembly in beamline. Use the correct equipment. Ensure that all the necessary tools are available. Follow procedure. Train technicians | Minimal | D - Unlikely | 5 - Negligible | Integrated into Design
11 | Contamination of UHV wetted surfaces | Multiple | Equipment, Efficiency of Personnel | Vacuum Systems | Minimal | C - Possible | 4 - Low | Use of proper UHV cleaning and haldling procedures, and UHV certification | Minimal | D - Unlikely | 5 - Negligible | Specifications and Interfaces Updated | QC plan developed. Travellers to be written
12 | Pinch hazard during assembly | Multiple | Personnel, Efficiency of personnel | Personnel | Low | B - Likely | 3 - Moderate | Use proper assembly procedures | Low | C - Possible | 3 - Moderate | Specifications and Interfaces Updated | QC plan developed. Travellers to be written
13 | Lifting injury during assembly. | Multiple | Personnel, Efficiency of personnel | Personnel | Low | B - Likely | 3 - Moderate | - Use proper assembly procedures and training - Use appropriate lifting equipment and lifting procedures | Low | C - Possible | 3 - Moderate | Specifications and Interfaces Updated | QC plan developed. Travellers to be written

## Hazard Severity Matrix
Fermilab QAM 12030TA Table 1
HAZARD SEVERITY
SEVERITY | PEOPLE | ENVIRONMENT | COMPLIANCE | PROPERTY | PROCESS/PROJECT
CRITICAL | Multiple deaths from injury or illness; multiple cases of injuries involving permanent disability; or chronic irreversible illnesses. | Permanent loss of a public resource (e.g. drinking water, air, stream, or river). | Willful disregard for the rules and regulations. | Loss of multiple facilities or program components; (>$5,000,000 total cost*) | Total breakdown identified resulting in loss/shut down of a process or project.
HIGH | One death from injury or illness; one case of injury involving permanent disability; or chronic irreversible illnesses. | Long-term loss of a public resource (e.g., drinking water, air, stream, or river). | Major noncompliance that exposes the Lab to significant potential fines and penalties. | Loss of a facility or critical program component; (>$5,000,000 total cost*) | Major breakdown identified resulting in the failure to attain the budget, schedule, key performance indicators or customer expectations.
MEDIUM | Injuries or temporary, reversible illnesses resulting in hospitalization of a variable but limited period of disability. | Seriously impair the functioning of a public resource. | Significant noncompliance that requires reporting to DOE or other authorities. | Major property damage or critical program component; ($1,000,000 - $5,000,000 total cost*) | Significant compromise to the attainment of the budget, schedule, key performance indicators or customer expectations which exposes process/project to potential failure if gap cannot be immediately resolved.
LOW | Injuries or temporary, reversible illnesses not resulting in hospitalization with lost time. | Isolated and minor, but measurable, impact(s) on some component(s) of a public resource. | Programmatic noncompliance with the Lab's Work Smart set. | Minor property damage or critical program component; ($50,000 - $1,000,000 total cost*) | Minor breakdown or gap identified which does not result in significant compromise to the attainment of the budget, schedule, key performance indicators or customer expectations; gaps can be resolved.
MINIMAL | Injuries or temporary illnesses requiring only minor supportive treatment and no lost time. | No measurable impact on component(s) of a public resource | Specific instance of a noncompliance with the Lab's Work Smart set. | Standard property damage or critical program component; (<$50,000 total cost*) | Minor gaps identified which do not compromise the attainment of the budget, schedule, key performance indicators or customer expectations; gaps can easily be resolved.
* total cost = total dollar value including parts, labor, contingency plans, etc. that is necessary to repair/replace property or program component.

## Probability
Fermilab QAM 12030TA Table 2
MISHAP PROBABILITY TABLE
PROBABILITY | DESCRIPTION
A - Almost Certain | Could occur annually
B - Likely | Could occur once in two years
C - Possible | Occurring not more than once in ten years
D - Unlikely | Occurring not more than once in thirty years
E - Rare | Occurring not more than once in one hundred years.

## Risk Assessment Actions
Risk Assessment Codes and Actions
1 - Very High | Unacceptable. Operation not permissible. Immediate action necessary.
2 - High | Remedial actions to be given a high priority.
3 - Moderate | Remedial actions to be taken at an appropriate time. Can be considered an acceptable risk.
4 - Low | Remedial action discretionary.
5 - Negligible | No action necessary.

## Look-up Tables
Life Cycle Stage | Severity | Probability |  |  | Risk Matrix |  |  |  | Mitigation Status
|  |  |  | A - Almost Certain | B - Likely | C - Possible | D - Unlikely | E - Rare
Fabrication | Critical | A - Almost Certain | Critical | 1 - Very High | 1 - Very High | 1 - Very High | 2 - High | 3 - Moderate | Integrated into Design
Installation | High | B - Likely | High | 1 - Very High | 1 - Very High | 2 - High | 3 - Moderate | 4 - Low | Specifications and Interfaces Updated
Commissioning | Medium | C - Possible | Medium | 1 - Very High | 2 - High | 3 - Moderate | 3 - Moderate | 4 - Low | Not Implemented
Operations | Low | D - Unlikely | Low | 2 - High | 3 - Moderate | 3 - Moderate | 4 - Low | 5 - Negligible
Equipment Shutdown | Minimal | E - Rare | Minimal | 3 - Moderate | 4 - Low | 4 - Low | 5 - Negligible | 5 - Negligible
Maintenance
Trouble-shooting
Repairs/Replacement
Decommissioning
Disposal or Recycling
Multiple