## Slide 1
PIP-II Vacuum Systems Installation Handoff Documentation
WBS 121.03.06
Lucy Nobrega, Ryan Crawford, Aisha Ibrahim, Kyle Kendziora, Denton Morris
PIP-II Vacuum Systems Integrated System FDR
May 13, 2024

## Slide 2: Outline
Documentation Overview for Complex Handoffs
Handoff Details
  Linac Installation
  BTL Installation
  Beam Instrumentation
  Cables and Connectors
Summary
Charge #1,7

## Slide 3: Documentation Overview for Complex Handoffs
QC Plan PIP-II-docdb-5709 covers
  Acceptance
  Cleaning/handling
  Certification and other travelers
  Nonconformance handling
  Technician Qualification
  New: considering QR code assembly tracking system
Installation Deliverables lists detail handoffs
  PIP-II IDL VAC-LI (ED0011282)
  PIP-II IDL VAC-BTLI (ED00XXXX)
  PIP-II BI IDL (ED0011271)
  PIP-II Cable Database
These include
  Equipment list
  Shipping configuration/location
  Configuration at handoff
  Quantity
  Documentation
  Additional details as required
Acceptance Criteria Document, ED00XXXX, will be attached to IDL’s to describe incoming deliverables.

## Slide 4: Vacuum Hardware Hand-off to Linac Installation- VAC IDL

## Slide 5: Vacuum Hardware Hand-off to Linac Installation- VAC IDL
Includes controllers and special cables only. Interface between VAC and Cntrls is connector on back of controller.

## Slide 6: Quality Assurance- Traveler Tree
Work to be documented in travelers, utilizing FNAL’s Vector system
Hierarchical traveler tree reflects system build-up
Gates (e.g. Operational Readiness Clearance) identified and coordinated with Verification & Validation
Individual Traveler
ORC gate

## Slide 7: BTL Installation Scope

## Slide 8: BTL Installation Phases

## Slide 9: BTL Installation Phases

## Slide 10: BTL Installation Phases

## Slide 11: VAC – Beam Transfer Line Installation (BTLI) Handoffs

## Slide 12: BTL Installation Hand-off
Notes: The System L3s (Vacuum) come to the Installation Readiness Review (IRR) with the following:
Functional and Technical Requirement Specifications
Preliminary and Final Design Reviews
  Recommendations
  Responses to Recommendations
Quality Control Documentation
  Non-conformities
  Corrective actions
Travelers
Installation Deliverables List (IDL)
  Installation drawings
  Special handling procedures
  Hazard Analysis (When needed)
  LOTO procedures (When needed)
Following completion of all IRRs the Vacuum L3 WBS will be closed out and Vacuum efforts will be covered under the Installation WBS (121.05.03 BTL Installation)
BTL Installation will continue with QC., Travelers and installation documentation which will all be presented at the Operational Readiness Clearance prior to running the systems. Upon completion of the ORCs for all systems they will be presented to the Accelerator Readiness Review prior to the start of Commissioning.

## Slide 13: Beam Instrumentation Handoff Paths
  BI Acceptance Documents will be BI’s QC Plan (PIP-II-Doc-5520)
  BI Verification Plans will be listed in the BI’s QC Plan (PIP-II-Doc-5520)
Notes: Green “HO MS”, in slide, ties to BI750440 – BPM Pickup Components Ready for Installation, which drives a vacuum activity chain that drives (orange MS) LI-17100 & LI-17110.
QUESTION:
How many procurement cycles are there for the BPM pickups?
RECOMMEND:
Remove BI7514025 and BI7514035 as predecessor to BI750440
Add HO MS for BPM installation in the BTL; Predecessor to new HO MS will BI7514025 and BI7514035; Successor will be an BTL installation activity

## Slide 14: Quality Control Plan (PIP-II docDB 5520)
Example of how QA documents map against workflow and handoff milestones (HO MS)
PIP-II Beam Instrumentation Quality Control Plan (PIP-II docDB 5520) host tables, in which all acceptance documents, verification procedures, and travelers are enumerated, for each BI system.
Diagrams are available in BI Verification and Validation Plan (pip2-docDB #7517)

## Slide 15: Beam Instrumentation Hand-off to Vacuum (BI-VAC IDL)
BI-VAC handoffs include
  (14) BPM (SCL)
  (7) BI Reference Line Tap
  (56) BPM (BTL)
  (2) Large Aperture BPM (BTL)
  (2) ACCT (SCL)
  (1) End of SCL ACCT
  (1) End of SCL DCCT
  (2) End of SCL TWS subassemblies
  (16) TWS subassemblies (BTL)
  (12) Laserwire subassemblies (SCL)
  (12) Optical Mirror Box

## Slide 16: Cable and Connectors
Cable Documents
  Standard Cable and Connector List - ED0014371
    Needs some updating as we move forward with final designs
    BldgI will procure cables included in this document
  Cable Criteria - ED0014355
    Details requirements for standard (BldgI procured cables) and specialty cables (procured by individual L3s)
Handoffs
  Cable Plan - ED0014352
    QC checks (Tracked via Travelers)
    Hand off documents (Travelers, Cable DB entries, etc.)
    Cable DB requirements (Cable type, Origin, Destination, etc.)

## Slide 17: Cable and Connectors
Cable DB
  Used to track all cable and connector information
  Automatic label generation
  Used successfully since MI era at Fermilab
Cable Type and DB ID
Function
Origin
Destination

## Slide 18: Summary
Installation Deliverables Lists detail handoffs.
  PIP-II IDL VAC-LI (ED0011282)
  PIP-II IDL VAC-BTLI (ED00XXXX)
  PIP-II BI IDL (ED0011271)
  PIP-II Cable Database
Expectations and P6 handoffs are well understood and detailed in above documents
Remaining work – complete the following
  VAC-BTLI IDL
  Unfinished document deliverables (procedures, documents, travelers)
  Acceptance Criteria Document for incoming off-the-shelf purchases and BI deliverables
Meet handoff goals
  WFE assemblies to LI Q2 2025
  BTL assemblies to BTLI Q1 2026
  BAL assemblies to BTLI Q1 2027

## Slide 19
THE FUTURE OF FERMILAB
Follow us:
http://pip2.fnal.gov/
@PIP2accelerator
/showcase/pip-ii/