## Slide 1
Thoughts and Considerations
from the
Daya Bay Experience
S. Kettell
BNL
LBNE International Symposium
October 3, 2012

## Slide 2: Overview
Daya Bay was a joint US-China construction project, with Taiwan, Hong Kong, Russia and Czech Rep.
  Detector: ~50%:50% US/China, ~10% others
  Civil: China
Co-spokespersons: China and US (non-China)
  Collaboration: 50% China, 40% US
Subsystem co-managers
Operations: US-China
  Common Fund by collaboration membership
International Finance Committee
  annual US-China meeting
  Executive Board tried to represent various funding sources
Daya Bay was a green field site

## Slide 3: Outline
International framework
Communication
Imports/Exports
Daya Bay as green field site
Safety
Cultural differences
Project lessons
Collaboration lessons

## Slide 4: International Framework
US-China Treaty
  1979 (Jimmy Carter/Deng Xiaoping) under control of State Department
Implementing Accord on Science and Tech.
  1979 (DOE/Ministry of Science & Technology)
  Points of Contact: DOE-OHEP/Chinese Academy of Science
Daya Bay works under the auspices of US-China treaty – important!
But MOU was signed by BNL, LBNL and IHEP (not DOE or CAS). LOG was important!

## Slide 5: Communications
Meetings (at all levels) need minutes, should be face-to-face, all decisions and actions items should be summarized at the end of each meeting
  design
  Safety and work planning
Cultural differences
  What does “yes” mean?
Different time scales and approval processes
  Hard to focus on issues not yet required by your funding agency
Notes: 5

## Slide 6: Communications
We would expect to push-decision making down as far as reasonable.
  Not used to centralized decision making
  We expect(ed) distributed authority
Make sure that there are appropriate levels of authority to appeal to
Notes: 6

## Slide 7: Export/Imports
US Export Control laws
  Review all equipment purchased by or shipped from the US
  China and India are both sensitive countries
  “Deemed” exports, intellectual property, etc…
Chinese Import Duties
  Needed list in advance (before we finished design)
  Needed US-China Treaty

## Slide 8: Greenfield site
Not a national laboratory
  Expectation of finding common tools and equipment
  Difficult to arrange purchase of pliers, cable ties,…
  Hard to plan all needed common tools and items
  Must provide all manpower (crane operators, welders, etc… not available from another experiment in emergency)
What are rules for use of machine shops, cranes, vehicles, forklifts

## Slide 9: Safety
Safety review processes
Safety standards
  Equipment/design reviews
  Work procedures
  Worker training/PPE (personnel protective equip.)
Safety personnel (especially onsite)
Work planning required constant vigilance.
Liability

## Slide 10: Cultural Difference
How (who) to make decisions (verify concurrance)
Document decisions, action items, results
Contracting practices
Review process
Liability

## Slide 11: Project’ology
Decouple KPP from any milestones out of your control
  Can never have too much schedule contingency?
Good engineers to work with physicists in all mgmt.
Try to understand nonverbal and unwritten rules of communication. Face-to-face contact essential.
Technical translation can be very difficult
Decouple deliverables by institution as much as possible
  Clean WBS
Assure that key installation decision makers are onsite
Maintain minutes, insist on responses to all action items
Formal work plans, ORR, onsite safety personnel

## Slide 12: Collaboration
Bylaws (owned by collaboration) and MOU (owned by Labs and project)
IB represents all institutions
EB supposed to concur on L2 managers, scientific scope, key technical decisions (bigger role in Operations phase)
Tensions between countries
Tensions between collaboration and project

## Slide 13: Summary
Daya Bay: successful example of international collaboration on a large scale (~50%:50%)
Many challenges
Daya Bay experience may not be relevant to LBNE. (DB site owned by China, LBNE site by US)
…