## Slide 1
IJCLAB status/updates on SSR2 activities
Patricia Duchesne, Sandry Wallon, Nicolas Gandolfo, Longuevergne David
On behalf of PIP-II team at IJCLab

## Slide 2: OUTLINE
Progress on SSR2 cavity
Progress on Coupler
Progress on Tuner
Other points

## Slide 3: Recent key technical achievements (cavity and tuner)
3 tests in vertical cryostat:
  1st test of ZA01 + tuner (October 2022)
  ZA01 didn’t reach specs because of strong field emission
  Internal inspection + HPR + baking @ IJCLab
  2nd test of ZA01 + ZA03 + tuners (January 2023)
  ZA01 and ZA03 didn’t reach specs because of field emission
  2 tuners tested and validated
ZA01 shipped to Fermilab
  Test as received in STC
ZA02 (fully prepared at IJCLab)
  Assembled in clean room
  Baking next week
  Vertical test mid of March

## Slide 4
Recent key technical achievements (couplers)
4 couplers under fabrication at PMB
2 vacuum side have been shipped to Fermilab in January directly from company
  1 vacuum side has been damaged during handling
  1 vacuum side is ok and will be power tested at Fermilab
  Overall quality is very good (copper plating, brazing, …)
  Cleanliness not perfect
  RF power test to be performed at Fermilab in coming weeks
Warm ends to be finished in march
  Some difficulties with copper plating (non uniformities around bellows)
  IJCLab will proceed with assembly test of full coupler at PMB in mid-March.

## Slide 5: Other points
Schedule
    Finalized. Milestones validated in PPD part2
PPD
    PPD part2 finalized
    PPD part1 pending
Documentation
    Acceptance plan : to be drafted by Fermilab
    Acceptance criteria list : preliminary list edited.
    All documentation as procedures, reports, travelers are being edited and improved with prototypes parts
    First reports and travelers for ZA01 sent to Fermilab