## Slide 1
FD1 Planning Updates
Eric James
FD1 Technical Board Meeting
March 15, 2023

## Slide 2: Updated FD1 Design Report
Executive Summary was submitted to LBNC last month and expected to be discussed at March 23-24 LBNC meeting
Targeting end of April for submission of full document (editing work will resume following re-submission of FD2 TDR)

## Slide 3: LBNC Meeting
Shortened LBNC meeting on March 23-24
FD1 parallel session on Thursday, March 23 from 1:30-3:30pm Chicago-time
Presentations requested from APA and DAQ consortia

## Slide 4: Design Reviews
Last four FD1 Final Design Reviews
  Cryogenic Instrumentation FDR: January 18, 2023
    Committee report expected shortly
  DAQ FDR: February 22-23, 2023
    Committee report expected shortly.
  Photon Detection FDR: March 14-15, 2023
    In progress this week.
  Installation FDR: April 10-11, 2023
    Consortia participation required

## Slide 5: EDMS Links
One-stop location for review documentation
  https://edms.cern.ch/project/CERN-0000233999
FD1 Technical Board Minutes (up-to-date)
  https://edms.cern.ch/project/CERN-0000219863

## Slide 6: APA Testing at CERN
First two production APAs from Daresbury will be shipped to CERN for testing in NP04 Cold Box (targeted pack/ship dates are April 13-14)
NP04 TCO closure now targeted for mid-June
  At a minimum need to complete testing of first APA and have the second APA installed inside Cold Box prior to beginning this work

## Slide 7: Cold Box Testing Schedule
Draft schedule for cold box tests under construction
  Link
Need to confirm the availability of required personnel for each stage in the process
Note that working at heights and lift training opportunities are available at CERN in late April and Early May
  Working at Heights – April 28
  Lift training (refresher) – May 2
  Lift training (full course) – May 3 and 4