## Slide 1
Jeff Eldred
Monday, March 6, 2023
Huddle + virtual
9am Meeting

## Slide 2: Current Plan for This Week
NuMI / MI
- At 600kW over the weekend – RRXDMP node reset (today?)
- Keep NuMI flux below 800kW until approved (with new optics).
- NuMI Underground backup generator under maintence, temporary replacement in use, still access to Target Hall will be restricted to an as needed basis.
Linac
- KRF2 ~4hr downtime Sat evening, thank you to experts for coming in to look at it and thank you also for those tuning up into the next day.
MTest
- MTest CDC issues in MTW2D1 resolved by experts last night.
Linac/Booster Access Half-Shift Wed 3/8
- Linac has request a half-shift access on Wed 3/8, for vacuum pump on DTL Tank 5.
- Source change A->B.
- Diagnostics applied to KRF5.
- RF to access Booster to tie-off BRF2.

## Slide 3: Outlook
Proton Source Studies Day tentatively 3/22
Opportunistic Downtime Requests
- Linac RF Station 2 PA replacement, 4-6 hours.
- NuMI Experiments, electrical work which would inhibit beam permit, 1 shift. (tentatively during PS studies)
- TSD adjust air flow, <1 shift (tentatively during PS studies)
- BNB water leak, >1 shift.
Linac DTL Tank 5
-- DTL Tank 5 is a significant concern going forward.
-- Looking to schedule a 5-7 day downtime when repair plan is in place.
AP-0 Air System Work
-- Scheduled for April 17 + 6 weeks (~May 29)
-- Procedure identified to avoid Switchyard downtime.