## Slide 1: ICARUS Operation
C. Montanari
FNAL – INFN Pavia
SBN Oversight Board Meeting – June 9, 2023

## Slide 2: Detector status
  The ICARUS detector continues to run in excellent and stable conditions.
  The free electrons lifetime remains stable at about 8 ms in the WEST module (liquid filters regenerated) and about 4 ms in the EAST module.
  Neutrino data are being collected with high efficiency.
    Some trigger synchronization issues, due to changing parameters in the early warning signals following an increase of beam repetition rate, have caused some loss of data.
  Calibration activities take place routinely during beam off periods.
  Summer shutdown activities are being organized.
    Interference with SBND commissioning activities, impacting work on cryogenics and purification, is being dealt with

## Slide 3: Working Groups Activities During the Summer Shutdown
  Beam off on July 9, 2023
  TPC WG
    Readout boards, Chebyshev filter addon
    Power supplies, fuses upgrade
  Trigger WG
    Servers update
    …
  DAQ, Networking, Slow Controls
    Servers upgrades
    Networking checks
  PMT WG
    Production and installation of new signal cables
    Calibrations and synchronization
  CRT WG
    Bottom CRT integration / SiPM replacement on spare modules

## Slide 4: Working Groups Activities During the Summer Shutdown (cont.)
  Beam off on July 9, 2023
  Calibrations WG
    See slides
  Drift HV WG
    Software upgrades + testing
  Cryogenics
    LN2 pump maintenance
    West LAr pump regular maintenance
    East LAr pump upgrade
    East liquid filters regeneration
    New fill filter implementation
    LAr refill
  DAQ
    Upgrade of servers to Linux AL9 conditioned to availability of stable Artdaq on AL9
    Upgrading and testing performed in parallel and in conjunction with hardware activities

## Slide 5: July 2023
Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
25 | 26 | 27 | 28 | 29 | 30 | 1
2 | 3 | 4 | 5 | 6 | 7 | 8
9 Beam OFF | 10 Calibrations | 11 Calibrations | 12 Calibrations LN2 pump maint. | 13 Calibrations LN2 pump maint. | 14 Calibrations LN2 pump maint. | 15 Calibrations
16 Calibrations | 17 Calibrations | 18 Calibrations | 19 Calibrations | 20 TPC PWR supp. LAr pump maint. | 21 TPC PWR supp. LAr pump maint. | 22
23 | 24 Calibrations TPC PWR supp. TPC filter test | 25 Calibrations TPC PWR supp. TPC filter test | 26 Calibrations TPC PWR supp. TPC filter test | 27 Calibrations TPC PWR supp. TPC filter test | 28 Calibrations TPC PWR supp. TPC filter test | 29 Calibrations
30 Calibrations | 31 PMTs Cabling TPC PWR supp. TPC filter test | 1 PMTs cabling TPC PWR supp. TPC filter test | 2 PMTs cabling TPC PWR supp. TPC filter test | 3 PMTs sync. TPC PWR supp. TPC filter test | 4 PMTs sync. TPC PWR supp. TPC filter test | 5 PMTs Calibration

## Slide 6: August 2023
Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
30 Calibrations | 31 PMTs Cabling TPC PWR supp. TPC filter test | 1 PMTs cabling TPC PWR supp. TPC filter test | 2 PMTs cabling TPC PWR supp. TPC filter test | 3 PMTs sync. TPC PWR supp. TPC filter test | 4 PMTs sync. TPC PWR supp. TPC filter test | 5 PMTs calibration
6 | 7 | 8 | 9 | 10 Power cut Drift HV | 11 Drift HV | 12
13 | 14 | 15 | 16 | 17 | 18 | 19
20 | 21 | 22 | 23 | 24 | 25 | 26
27 | 28 Filter regeneration Trigger rack | 29 Filter regeneration Trigger rack | 30 Filter regeneration Trigger rack | 31 Filter regeneration Trigger rack | 1 Filter regeneration Trigger rack | 2

## Slide 7: September 2023
Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
27 | 28 Filter regeneration Trigger rack | 29 Filter regeneration Trigger rack | 30 Filter regeneration Trigger rack | 31 Filter regeneration Trigger rack | 1 Filter regeneration Trigger rack | 2
3 | 4 GW/FS/DS AL9 upg PMTs cb. removal Filter regeneration Pump upgrade | 5 GW/FS/DS AL9 upg PMTs cb. removal Filter regeneration Pump upgrade | 6 GW/FS/DS AL9 upg PMTs cb. removal Filter regeneration Pump upgrade | 7 GW/FS/DS AL9 upg PMTs cb. removal Filter regeneration | 8 GW/FS/DS AL9 upg PMTs cb. removal Filter regeneration | 9
10 | 11 DAQ srv AL9 upg Filter regeneration | 12 DAQ srv AL9 upg Filter regeneration | 13 DAQ srv AL9 upg Filter regeneration | 14 DAQ srv AL9 upg Filter regeneration | 15 DAQ srv AL9 upg Filter regeneration Drift HV | 16
17 | 18 DAQ testing Calibrations | 19 DAQ testing Calibrations | 20 DAQ testing Calibrations | 21 DAQ testing Calibrations | 22 DAQ testing Calibrations | 23
24 | 25 Netw. testing | 26 Netw. testing | 27 | 28 | 29 | 30

## Slide 8: October 2023
Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
1 | 2 | 3 | 4 | 5 | 6 | 7
8 | 9 LAr refill | 10 LAr refill | 11 LAr refill | 12 | 13 | 14
15 | 16 Beam ON | 17 | 18 | 19 | 20 | 21
22 | 23 | 24 | 25 | 26 | 27 | 28
29 | 30 | 31 | 1 | 2 | 3 | 4

## Slide 9: Conclusions
  The ICARUS detector continues to run in excellent and very stable conditions.
  Data are being collected with high efficiency both of BNB and NuMI, though several beam interruptions are limiting the amount of collected data.
  The plan of activities during the summer shutdown has been discussed in several instances and is almost complete.