## Slide 1
Jeff Eldred
Wednesday, April 5, 2023
Huddle + virtual
9am Meeting

## Slide 2: Current Plan for This Week, Next Week
MI / NuMI Power
- Ran 850kW while Switchyard was off.
- KPS4A NuMI kicker about 6 hrs downtime last night.
-- request for another 1-2 hour for conditioning after 9 o’clock.
NuMI Horn Power Supply
- Yesterday, 240kA overcurrent trip (vs 210kA limit) on pulse sent to NuMI horn.
- Fixed yesterday afternoon (replaces relay chasis).
GMPS Trip Fri & Tues
- Replaced T0 card, experts will continue to monitor.
MCenter
- Signoffs yesterday, experiment in 1-2 weeks.
Proton Source Studies
- Prepare list of studies, asking for better documentation of study topics.

## Slide 3: Current Plan for This Week, Next Week
Water Resistivity & CUB Columns
- Insufficient LCW water resistivity (~4.5 MOhm at F1 right now)
- Muon held off until 8pm last night (when not in access).
- Switchyard held off all night.
-- Current limits: Switchyard (>4 MOhm), Muon (>3 MOhm), + MC approval.
Mu2e M4 Line Work
- Hydrostatic testing and HRS pumbing work in M4 line.
- Does not interfere with Delivery Ring BPM studies.
- Started yesterday, expect to complete today.

## Slide 4: Outlook
Linac DTL Tank 5
- Vacuum, temperature seem more stable after the switch to dedicated water skid.
- Full repair option being coordinated, not scheduled yet, will require a week downtime.
AP-0 Air System Work
-- Scheduled for April 17, to go for about 6 weeks (~May 29)
-- Procedure identified to avoid Switchyard downtime.
-- Still resolving whether Delivery Ring studies will be inhibited.
June International Booster Studies
-- Scheduled for week of June 26-30th, also Users Meeting Week.
Shutdown “Beam Off” Date: July 9th