## Slide 1
Cons Gattuso
April 7th, 2023
Summer Shutdown 2023

## Slide 2: Shutdown Parameters (Tentative)
Start Shutdown
  We will determine if the need intensity reduction intensity as the work list evolves.
  Duration
    10-12 Weeks (duration may change depending on the major tasks undertaken )
  Beam Off
    Sunday July 9th @0001 hrs.
    Configuration Control
    Open surveys would take place Monday 10th -Wednesday 12th
    Specialty access would be from Wednesday-Friday
      Lighting Assessment, Phone Assessments, Fire protection testing, WiFi installation … *
    General tunnel access would commence Monday July 17th
  Start of tunnel work
    Monday July 17th
  End of tunnel work
    Week of Monday October 9th
  HEP
    Monday October 16th
Calendar Days: 93
Working Days: 66

## Slide 3
HEP
Plan phase 1:Determine Jobs and Define schedule
Plan Phase 3:Execute Shutdown
Close out
Plan phase 2: Finalize Schedule
Shutdown 2023 Timeline
Crew Marching orders
Define Scope
Plan
Execute
Close out
Shutdown Boot Camp
Work Planning
  HA’s
  Dose Plan
  Permits
  Etc..
Timeline of events
Work List Entries
Expectations
General Task Approval process
Work In HRA
JAN
FEB
MAR
APR
MAY
JUN
JULY
AUG
SEP
OCT
NOV
DEC
Milestone 1
Define Shutdown Coordinators.
Completed
Milestone 2
ID Jobs to the 90% level.
Milestone 3
First pass resource level Schedule.
Milestone 4
Milestone 5
Milestone 6
Milestone 7
Second pass resource level Schedule.
Final resource level Schedule.
Start Shutdown.
Complete shutdown.
Milestone 9
Milestone 8
Complete
Startup.
Return HEP
DEC
Milestone 0
Refine Shutdown Parameters
Completed
Activities planned
AD All Hands
Exterior Divisions All Hands
Commence ISD Job Collections
Milestone 4A
By end March, All Trades work Procurements need to be in Procurements hands…
Planned
Progress Indicator
Achieved
Commence Major Job collection
Completed
Milestone 1A
By May, Final Power Outage schedule
ISD Job imported in the Shutdown (~700 tasks)
Mid April
Completed
Completed

## Slide 4: Planning Stages
Planning Milestones
  Kick off meeting (completed)
  Set Major Jobs (nearly complete settling into final list)
  Get T&M/Fixed price packets out by early March (completed)
  Setup up Prep-work for given areas (Underway)
    Booster West Gallery
  Set Alignment Tasks (Underway)
    Input into their system (end of April)
  Finalizing ISD work in and around Tunnel Enclosures (Underway)
  Finalize Service Building Outages (early May)
  Set Maintenance tasks (mid of May)
    FESS and Machine activities
  Fit tasks with our Manpower (mid May)
  Resource leveled schedule
    Primary (mid April)
    Final (mid/end May)
  Please label jobs in the work list “Summer shutdown 2023:…”

## Slide 5: Alignment Needs
Linac
  Preacc : LEBT and MEBT
Pion Beam line
  Quad Alignment
Booster
  Collimator installation (limited) (1),
    Stand work
BNB
  swic installation
MI-8
  Collimator installation (limited) (1),
  relocate/repair/upgrade 1-3 Multiwire cans in 825 and 827 regions
MI
  Mi quad replacement (IQB) (3)
  RF cavities
  Elevation Run
Recycler
  Sextupoles Installation (2)
Muon campus
  907 collimator
  M4 line RWM
  ESS installation
  M3 line SEM installation (1)
  Possibly replace SQC quads in 30 (only if we do a swop) (3)
F-sector
  Install MWF45 wire plane (1),(2)
Enclosure C
  Replacement of SWIC 202 (1),(2)
  Replacement of SWIC 208 (1),(2)
M02
  Replace MC2Q1 magnet
M03
  Pin hole collimator work MT4TGT
NuMI
  Replace 1 damaged wire plane pair for NuMI. Possibly for the 114, 115, or 121 profile monitor.
Pre-Shutdown
(1)Referencing/Stake out
(2)Replacement
(3)Referencing

## Slide 6: Culvert Replacement
Before
After
Road
Culvert
Culvert Inside
Concrete Box
* Artist rendition not to scale
https://admd.fnal.gov/Culvert%20road%20work/index.html

## Slide 7: Road Work….
We will be standing up a roadway and parking lot reconstruction contract to start work in the early summer, covering Kautz road and the Wilson Hall west parking lot roughly as indicated in the screen shot below.
Traffic patterns are still being worked out
Impacts to AD
  Magnet loads
    We should plan on Moving Magnets to staging area in Accelerator Complex prior to this work starting.

## Slide 8
That’s all for this week…….
In two week
  Post the preliminary schedule
    Accelerator Enclosure Work
    Power Outage

## Slide 10: EE Support
BNB
  Horn PS @ MI-12 -- replace HV divider G10 covers with Lexan covers
Muon:
  AP-30 secondary braid and hardware replacement
MI:
  VCB maintenance
  Secondary cable replacement at another building (MI50?)
Meson
  Replacing 4 old power supplies w/ new switcher power supplies at MS1
  Fixing water leak in MC6Q2 PS at MS4

## Slide 11: Next meeting
Focus on Controls

## Slide 12: Electrical Agenda
Electrical work
  Booster
    Est are needed for the following
      The time it takes to characterize the Booster RF
      The time it will take to remove cabinets for the work area
      The time it will take to complete Physical work
      The impact of not having AC in the gallery for the duration of the work
      Time and access to yard Switch's and anode supply
    Collimator work cable pulls
  MI/RR
    Status of conversion to VDF Drives
      MI52/50
    MI-50 Power Supply DLO replacement
    8- Gev Collimator work
  LINAC Compressors
  Fixed target vacuum pump upgrades
  WIFI installation in the F sector and beyond
  Interlocks F-2, F-3 Manhole
Review Major work going on during the Shutdown
Review changes that may be coming for long-term key issues and re-coring

## Slide 13: Linac (electrical)
LINAC Compressors
  Do we have everything in place to do this task….?
    PO
    Material

## Slide 14: Booster Clean Power (electrical)
Booster West Gallery
  General Task
    Existing duct work in Booster Gallery West will be removed by HVAC subcontractor and stored outside the gallery footprint to be reinstalled later.
    Existing abandoned water pipes (6” and smaller) to be removed by yet be determined subcontractor and disposed of in dumpsters
    New raceways and trough to be installed by Leyden Electric
    All wire to be pulled wherever raceways will be covered by reinstallation of ductwork and inspected/verified by TM/CC and Leyden Electric representative
  Prep Work
    Does the area need to be cleaned out
      Do we need to remove of cabinets in the gallery??
      If so…
        Where are we placing them?
        How long does this take?
        Please work with Paul Neville and Scott Crowell
    We would like the RF characterization to be completed in the first week

## Slide 15: MI/RR (electrical)
Status of conversion to VDF Drives
  MI52/50
MI-50 Power Supply DLO replacement
  Material
8- Gev Collimator work
  Cable pulls
    Do we have pull list and material
  Plan if Steel Material does not arrive in time…
    Complete Stack out
    Complete Vacuum work
      End Flanges
      Ion pumps
    Complete Cable pulls
      Motion Control and TC gauges
Current schedule driver
Est 12-14 weeks

## Slide 16: External Beam Lines (electrical)
Switch yard
  WIFI installation in the F sector and beyond
  Interlocks F-2, F-3 Manhole
    Scope of work to be done
Meson
  MT3 Pinhole MC PM
  MT4TGT Motion PM
  M03 Light Replacement
  MS1-3 Vacuum PLC Install

## Slide 17: Major Jobs
Linac
  LRF5
    Internal Water Leak
Booster
  Clean RF power West Gallery
    Removal of BWG Dual Temp Line, AC Duct removal, re-install
  L8 Collimator Prep work
    Cable pulls
    Prep work in area

## Slide 18: MI/RR Major Jobs
MI12
  Repair TAC air velocity/pressure sensors .
  Seal wall/ceiling cracks in MI12-A & MI12-B.
  Sort out water level transducer sensor plan for MI12 sump and well sumps.
MI-8
  Collimator install
MI/RR
  VFD Upgrade (MI50/52)
  MI20 Sump Repair
  MI white hose replacement (MI50/MI60)
  MI quad Replacement (new IQB in the 20 sector?)
  MI20 Sump repair
NuMI Beam line
  Rebuild manifolds on Q118 (pre-target), Q115 (lower hobbit), possibly think about Q105 (MI).
  Like to replace 1 damaged wire plane for NuMI. Possibly for the 114, 115, or 121 profile monitor. Currently negotiating with Rich Prokop.

## Slide 19: ISD (maintenance projects in/around AD areas ) Preliminary
1. A0 chiller replacement (temporary chiller will be placed until permanent chiller arrives) [WO840860] – started
2. CMTF LED lighting retrofit [WO874612]
    Looking to start end of this month
3. Linac – Sub-levels LED lighting retrofit [WO??]
4. BTW 2nd flr LED retrofit [WO871278]
    Waiting Control Quote summer shutdown time frame
5. Minos roof tuckpointing [WO875790]
6. Minos LED retrofit [WO895697]
7. WH Parking lot & Kautz Rd rework
8. WH SW plaza entrance replacement
9. MI Pond transfer structure sinkhole investigation
10. MI20 sump discharge reroute
11. A0 Clean Room HVAC project (ISD-Engrg)
    Walk through was completed this last week.
12. AP0 HVAC (2 units) replacements (ISD-Engrg)[WO751725] –start on the 17th
    We are concerned about communications
    Impact operations: AD/ ESH/ISD side
13. Replacement of HVAC units on MI service buildings (ISD-Engrg
14. MS3 Oil switch replacement
Tunnel work

## Slide 20: Road Work….
We will be standing up a roadway and parking lot reconstruction contract to start work in the early summer, covering Kautz road and the Wilson Hall west parking lot roughly as indicated in the screen shot below.

## Slide 21: Road Survey
Road boring
  56 area across
  Characterization for Roadbed
    Load rating

## Slide 22: Next Meeting
Alignment Needs
  Linac tank 5
  MI 8 Collimator
  MI Quad change out
  NuMI
    Target hall
RCT Needs
  Coverage of jobs
  Dealing with Rad Waste

## Slide 24: Trades Work (As of 2/14/23)

## Slide 25
Booster RF Upgrade (2 man crew minimum, 3+ at times for wire pull)
  Existing duct work in Booster Gallery West will be removed by HVAC subcontractor and stored outside the gallery footprint to be reinstalled later.
  Existing abandoned water pipes (6” and smaller) to be removed by yet be determined subcontractor and disposed of in dumpsters
  New raceways and trough to be installed by Leyden Electric
  All wire to be pulled wherever raceways will be covered by reinstallation of ductwork and inspected/verified by TM/CC and Leyden Electric representive
  May include transferring source to new distributed circuits at this time if time permits.
  Ductwork to be reinstalled in original location after clearance is given by Leyden Electric
  Remaining Electrical installation to continue after ductwork if needed.
MI-50 Power Supply DLO replacement (2 man crew minimum)
    This is the same as what John did at the beginning of last years shutdown. I’d like to put one crew together to just work on that, two guys, potentially rewiring all three at MI-50
MI-50 VFD Upgrade (2 man crew minimum 4 at times for wire pull)
Main Injector and Booster Collimators (3-man crew minimum)
  Two new collimators being installed somewhere in the accelerator.
  36 cables being pulled for the Booster Collimator (12) 3C20AWG, (12) 5C18AWG & (12) 2 pair 22AWG, lengths are being determined
  -8 cables being pulled for Mian Injector Collimator (16) 3C20AWG, (16) 5C18AWG & (16) 2 pair 22 AWG, lengths are being determined
  All I know is the cables are pulled from a relay rack upstairs, to the collimators downstairs, terminations will be done by machine technicians

## Slide 26
LINAC Compressors (2-man crew)
  There are two compressors in the lower level of LINAC that need to be separated from the common circuit powering them now
  The compressors are labeled as having separate circuits however when both run, the circuit breaker trips and both die. Compressors are labeled with PP-L3-3 #7,9,11 and PP-L3-3 #13,15,17
  We will have to open and inspect existing as is installation to verify how much is incorrectly installed, including the PP-L3-3
  Current config control under MCR control, coordination with MCR needed for inspection/diagnosis.
MESON Power Supply upgrade (unknown)
  This has a small likelihood of being done this summer
  not much information available at this time
Fixed target vacuum pump upgrades (2 man crew, ODH required)
  Three locations for new 30amp 208v three phase Hubbell integrated twist lock/disconnects installed
  One location requires a 7.5 kva xfmr
  Roll over from last year, G2 service building, F-1 manhole job
WIFI installation in F sector and beyond
  not much information at this time but I believe it be relatively simple, similar to the cable pull John did in MS-3 last summer but in 5(?) locations
Interlocks F-2, F-3 Manhole (2-man crew, confined space required)
  Replace the Rotting Boxes and interconnecting Conduit
Need to add muon campus work

## Slide 27: Instrumentation

## Slide 28: SY
  Lighting upgrade (assigned to FESS during the 2022 shutdown and wasn't done).
    Transfer Hall
    Meson M03
      Working with FESS on this task.
      No plan has been put forth yet
  Switchyard service building clean up (no manpower for this job in 2022)
    Working on Getting additional Vet Techs

## Slide 29: RF
BOOSTER RF Days
  RF Characterization 10
  RF Maintenance (estimated) 15
  Booster West Gallery 480V Upgrade 40
MAIN INJECTOR RF
  RF Characterization 10
  RF Maintenance (estimated) 15
  RF Cavity LCW Cooling Path Upgrade 35
  Dual PA RF Station Upgrade 15

## Slide 30: MSD

## Slide 31: Planning Transition states
Into Shutdown
  Configuration Control
  Opening Surveys
  Re-coring
  Fire system testing
Out of Shutdown
  Restart Forms
  Re-coring
  Safety System testing
    Enclosure securing
    Interlock testing
  Configuration Control
  Safety System testing
    Rad permits
Sequencing has been completed
Milestone have been setup to final completion dates