## Slide 1: Muon Campus Operation Report
Dean Still
Friday 09:00 Operation Meeting
Week of April 17, 2023

## Slide 2: Performance for the Past Week
Protons On Target
Avg Protons on Target
Particles to Entrance of G-2 Ring
Decay Positrons in G-2 Ring
G-2 Trolley Run
8Gev Delivery Ring beam
<-------Weekend ------
<------------Week Days -------------------
 AP0 AC Install
 DR D:KPS5A PFL replaced
 300 Mev Study for g-2
 g-2 repairs & 300Mev Study
 RR KPS4A PFL bad cable
 BPM Studies

## Slide 3: Activities for the Past Week
G-2 Status:
  Delivered beam to g-2
Work completed:
  Replace Delivery Ring D:KPS5A abort kicker PFL.
  Replace Recycler Ring R:KPS4A abort kicker PFL.
  ESS2 power supply is back in service.
  Target Blower Maintenance
  AP0 AC installation started on Monday and only impacted operation 1 day. Sub-contractors are working on badging and should be ready next week.
  Delivery Ring BPM system working on solving communication issues with new boards.
Studies: (1 day)
  Mu2e BPM commissioning.
  300 Mev EDM Study . (Morgan)

## Slide 4: G-2 Performance – Integrated for Run 6
G-2 Experiment POT Run Goal
~4.2E20 POT
Run 6 period is Nov 2022 – June 2023
Run 6: Goal of ~x 6 BNL
Total Run: goal of x 21 BNL
Currently running 6.6 Hz
Run 6 # POT Delivered ~ 7.6E20
Plots as of 4/14/2023
Run 6 Integrated ~ x 2.59 BNL
0.08 for the week
Start of
Summer
Shutdown
2023
Total Integrated ~ x 21.54 BNL

## Slide 5: Plan for Next Week
g-2 operation:
  Deliver Beam to g-2
Muon Campus Plans :
AP0 AC installation work.
  AC work during day shift & delivery beam to g-2 & studies in the Evening & Owls.
  To work in AP0 water cage area requires 1.5 hour cool down.
  Friday – Deliver beam to g-2
  Saturday – Deliver beam to g-2
  Sunday – Deliver beam to g-2
  Monday - 0800 -1600 -- M4 beamline studies
  Tuesday - 0530-1600 - AP0 AC work - No Beam to g-2
  Wednesday - Booster Study Day – No beam to muon campus –
        Access DR, Extraction, M4, Pre-Vault, Pre target, Fsector
  Thursday – TBD
  Friday – TBD
Future Planning :
Mu2e M4
line
G-2 ,ine