## Slide 1
Cons Gattuso
May 5th, 2023
Summer Shutdown 2023

## Slide 2: Shutdown Parameters (Tentative)
Start Shutdown
  We will determine if the need intensity reduction intensity as the work list evolves.
  Duration
    10-12 Weeks (duration may change depending on the major tasks undertaken )
  Beam Off
    Sunday July 9th @0001 hrs.
    Configuration Control
    Open surveys would take place Monday 10th -Wednesday 12th
      Go over order this next week
    Specialty access would be from Wednesday-Friday
      Lighting Assessment, Phone Assessments, Fire protection testing, WiFi installation … *
      Go over order this next week
    General tunnel access would commence Monday July 17th
  Start of tunnel work
    Monday July 17th
  End of tunnel work
    Week of Monday October 9th
  HEP
    Monday October 16th
Calendar Days: 67
Working Days: 48

## Slide 3
HEP
Plan phase 1:Determine Jobs and Define schedule
Plan Phase 3:Execute Shutdown
Close out
Plan phase 2: Finalize Schedule
Shutdown 2023 Timeline
Crew Marching orders
Define Scope
Plan
Execute
Close out
Shutdown Boot Camp
Work Planning
  HA’s
  Dose Plan
  Permits
  Etc..
Class Zero
Expectations
General Task Approval process
Work In HRA
JAN
FEB
MAR
APR
MAY
JUN
JULY
AUG
SEP
OCT
NOV
DEC
Milestone 1
Define Shutdown Coordinators.
Completed
Milestone 2
ID Jobs to the 90% level.
Milestone 3
First pass resource level Schedule.
Milestone 4
Milestone 5
Milestone 6
Milestone 7
Second pass resource level Schedule.
Final resource level Schedule.
Start Shutdown.
Complete shutdown.
Milestone 9
Milestone 8
Complete
Startup.
Return HEP
DEC
Milestone 0
Refine Shutdown Parameters
Completed
Activities planned
AD All Hands
Commence ISD Job Collections
Milestone 4A
Planned
Progress Indicator
Achieved
Commence Major Job collection
Completed
Milestone 1A
Completed
Completed
Completed
Underway

## Slide 4: Planning Stages
Planning Milestones
  Kick off meeting (completed)
  Set Major Jobs (completed)
  Get T&M/Fixed price packets out by early March (completed)
  Setup up Prep-work for given areas (Underway)
    Booster West Gallery
  Set Alignment Tasks ~90% complete
    Input into their system (end of April)
  Finalizing ISD work in and around Tunnel Enclosures 85% Complete
  Finalize Service Building Outages (early May) (completed)
  Set Maintenance tasks (mid of May)75% Complete
    FESS and Machine activities
  Fit tasks with our Manpower (mid May) 80% Complete
  Resource leveled schedule 65%Complete
    Primary (mid April)
    Final (mid/end May)
  Please label jobs in the work list “Summer shutdown 2023:…”

## Slide 5: Culvert Replacement
Before
After
Road
Culvert
Culvert Inside
Concrete Box
* Artist rendition not to scale
https://admd.fnal.gov/Culvert%20road%20work/index.html
Underway
On Schedule
Done

## Slide 6: Road and New Gate Work….
Roadway and Parking lot work
  To start work in the fall/Late Fall, covering Kautz road and the Wilson Hall west parking lot roughly as indicated in the screen shot below.
  Traffic patterns are still being worked out
Gate installation
  To start ASAP
    Impact to AD
    New Traffic patterns
Impacts to AD
  Magnet loads
    We should plan on Moving Magnets to staging area in Accelerator Complex prior to this work starting.

## Slide 7: New Gate
Removal Fencing
New Guard House/gate
Staging are for Booster RF work
Shipping Container
Power distribution modification
Tie into Electrical Panel

## Slide 8: ISD Activities
Power Outage
  This week
    Wednesday May 3rd
      NL LABS A-C-D-CDX
    Thursday May 4th
      PAB, TPL, Site 50 & 52
    Saturday May 6th
      Village PM
        07:30-16:00 hrs
        Entire Village, All village labs and residences.
  Next week
    Wednesday May 10th
      PS4, PC4, PS2, PW2,3,4
      All day
Tevatron A-E (all week)
  P&M on Tunnel Sumps and Dehumidifies
Completed
Completed
Scheduled

## Slide 9: Schedule
Releases
  Electrical should start coming in in the next week
Schedule
  ~ 800 jobs have been posted to the Shutdown worklist
  Next Phase of our planning
    Meeting with each Machine Coordinator/system Coordinator
      Review the current schedule
        Task order and when in the shutdown they occur
        Review general scope
        Review critical activities than may need to be detail out further
        Review schedule Pivot Points
      Revise Schedule
      Resource level schedule
      Post schedule

## Slide 10
That’s all for this week…….
Next Week
  Switching over to Weekly Shutdown planning meetings
    Tuesday at 11:00 in the huddle and Via Zoom