## Slide 1
LCLS-II-HE Cavity and Cryomodule Test Progress
James Maniscalco | SRF Engineer | SLAC National Accelerator Laboratory
5 December 2023

## Slide 2: LCLS-II-HE project scope
Slide adapted from G. Hays / F. Garcia
Add 23 additional cryomodules (L4 linac) to increase the LCLS-II accelerator energy to 8 GeV.
Install new cryogenic distribution box and transfer line between the cryoplant and the new L4 linac.
Upgrade soft X-ray undulator for 8 GeV operation.
Upgrade the LCLS Hard X-ray endstations for MHz beam and data rates.
Develop conceptual design of a Low Emittance Injector including a tunnel design; also fund construction of a prototype high-gradient SRF gun for the LEI.

## Slide 3: LCLS-II-HE SRF plan overview
Building on the success of LCLS-II cavity production to meet higher performance requirements
  Eacc ≥ 23 MV/m
  Quality factor: Q0(21 MV/m) ≥ 2.5×1010 (in vertical test)
  No field emission accepted in vertical test
Improvements to LCLS-II cavity production strategy
  Updated nitrogen doping recipe following R&D program
  Expanded process reporting requirements (QA/QC)
  Frequent in-person visits to cavity supplier
Cavity acceptance testing at Fermilab and Jefferson Lab
  Cavities tested as-is from vendor (static vacuum)
  HPR as needed to recover from field emission

## Slide 4: Vertical test performance so far – as of Dec. 1, 2023
167 cavities tested, of which:
132 qualify (79%)
  109 as received
  12 after 1 rerinse
  11 after 2+ rerinses
8 placed “on hold” (marginal Eacc) (4.8%)
  7 with marginal Eacc
  1 with marginal Q0
9 disqualified (5.8%)
  4 with low Eacc
  1 with low Q0
  3 with persistent FE
  1 with HOM scratch
11 undergoing other rework (6.6%)
  7 bellows damage
  4 surface rework at labs
6 awaiting re-test after high-pressure rinse to mitigate field emission (3.6%)
13 of the above recently sent back to the supplier for repair/rework
All cavities with no FE

## Slide 5: Vertical test performance so far – Eacc and Q0
Average quench gradient: 27.0±3.5 MV/m
Average Q0:
3.24±0.38×1010
Accelerating gradient
Quality factor @ 21 MV/m

## Slide 6: Cavity production challenges – field emission radiation
Early and continuing issue
  40% of initial cavities had FE in first vertical test
  Has been a recurring issue, similar long-term average rate to LCLS-II (20%)
    Higher Eacc for LCLS-II-HE means we are likely cleaner now than in earlier project
  High pressure rinsing (HPR) has removed FE in some cavities (29 of 38 so far)
  Some FE may be due to issues at labs
Site visits
  Initial visit to evaluate clean room practices & recommend changes
  Periodic follow-on site visits
Rework at cavity supplier
  2 FE cavities included in rework plan
Clean room site visit

## Slide 7: Cavity production challenges – bellows damage
Damage at supplier and laboratory to ~8% of cavities
  Delicate external bellows is a weak point in the LCLS-II/LCLS-II-HE cavity design
  Problem early in production despite using incumbent vendor (“rusty” technicians; loss of expertise/training)
  Damage also caused due to mishandling at the laboratories
Schedule and cost impact
  Several months total delay to shore up deficient procedures at supplier and lab
  Cost to repair cavities damaged after receipt
Mitigations effective but imperfect
  External covers and retraining only go so far
Typical bellows unit – covers normally installed during handling and transport
Damage encountered early in production

## Slide 8: Cavity production challenges – further bellows issues
Incumbent bellows supplier not willing to continue supply
  Cavity supplier could not reach an agreement with incumbent supplier
Quality issues with new supplier
  Many months of prototyping and QA/QC to produce acceptable parts
  Titanium supply chain issues caused further delays
  Parallel effort to identify another supplier took very long, quality issues resolved first.
Good quality achieved after 5-6 months
  Additional QC in place at cavity supplier
Poor weld quality
Surface defects

## Slide 9: Cavity production challenges – weak vacuum
Cavities found in a state of “weak vacuum” at time of string assembly
  Vacuum well below atmosphere but above acceptance level (1e-3 – 1e-1 torr)
  9 cavities encountered so far (7 FNAL, 2 JLab)
  All > 3.5 months with static vacuum
  7 had last vacuum pulled at supplier; 2 at labs
Root cause study in progress
  Strongly suspected: VAT right angle valves
    Not rated for cryogenic use; known to develop intermittent leaks
    Does anyone know of a different valve type that is rated for particle-free UHV and cryo use?
  Also suspected: other re-used cavity accessories (burst disks, etc.)
  Leak checking has been inconclusive
  Ongoing “sleeper” issue – likely that this will be encountered again as work continues

## Slide 10: Cryomodule assembly and testing in progress

## Slide 11: Cryomodule assembly and testing in progress
F1.3-21 built using recovered LCLS-II cavities

## Slide 12: Cavity performance in cryomodules

## Slide 13: Cavity performance in cryomodules
Accelerating gradient
Quality factor @ 21 MV/m
ΔEacc = 2.7±2.8 MV/m
ΔQ0 = 2.1±3.8×109
Excluding field emission and administrative limits

## Slide 14: Cryomodule issues
Field emission encountered in approximately 13% of cavities
  2 worst cases caused by off-normal work to repair damaged beamline bellows
  No root cause determined for other cases
  No captured dark current detected so far, only X-rays
Partial rebuilds to correct other issues
  Another case of damaged beamline bellows
    Lessons learned from first case → revised disassembly scheme & requalification of cavities
  Beamline leak
    Leak localized to field probe feedthrough; full rebuild required
    Leak only appeared after > 6 thermal cycles! Will be investigated after disassembly.
  Chipped FPC ceramics
    Rebuild required
  We are taking a conservative approach, prioritizing quality over schedule.

## Slide 15: Outlook
13 of 192 production cavities remaining to be delivered
  Final delivery coming in May 2024
13 rework cavities to be delivered Dec 2023 – Feb 2024
Vertical test qualification to continue through June/July 2024
Cryomodule assembly and test to continue through mid 2025
Installation scheduled to start Summer 2025

## Slide 17: Backup slides

## Slide 18: LCLS-II-HE cavity and cryomodule requirements
Objective: increase beam energy from 4.0 to 8.0 GeV
  23 new cryomodules added to existing 35
Quantity | LCLS-II Cavities | LCLS-II Cavities in HE | HE Cavities in HE | Unit
Number of 1.3 GHz cavities | 280 | 280 | 193† | 
Minimum average cavity Q0 at nominal Eacc | 2.7 | 2.7 | 2.7 | 1010
Vertical test qualifying gradient | 19 |  | 23 | MV/m
Assumed fraction of failed cavities | 6 | 3 | 6 | %
Nominal average operating gradient | 15.7 in L2-3 | 16.9 in L2-3 | 20.8 | MV/m
Vertical test field emission onset min. | 17.5 |  | No FE allowed | MV/m
Maximum CM captured dark current | 10 | 10 | 30 | nA
† includes injector CM (8) and BCC (1)
Bare 1.3 GHz LCLS-II/LCLS-II-HE cavity

## Slide 19: High-Q/High-Gradient R&D
R&D program following LCLS-II project to improve nitrogen doping recipe and surface processing (2018-2020):
  Research collaboration between SLAC, Fermilab, Jefferson Lab, Cornell University
  Increase cavity gradient without degrading Q0
  Improve uniformity of performance with tighter QA
    Challenge: long lag between vendor activities and cavity tests (2-3 month minimum)
New “2N0” recipe chosen
  Update to LCLS-II “2N6” recipe
  R&D results:
    4 of 5 cavities exceeded 30 MV/m
    Average Q0(21 MV/m) ≈ 3.5×1010
2N0 R&D results (9-cell cavities)
Plot from D. Gonnella

## Slide 20: LCLS-II-HE recipe
Additional changes:
  Require continuous RGA spectrum during furnace runs
  Require continuous monitoring of temperatures during electropolishing runs
  Sort cavity half-cell material by required heat treatment temperature
LCLS-II | LCLS-II-HE
Bulk EP High Temperature Furnace Treatment & Doping (2N6) Fine EP | Bulk EP 1 High Temperature Furnace Treatment Bulk EP 2 (last portion cold) Doping (2N0) Fine EP (all cold)

## Slide 21: LCLS-II-HE cavity scope
10 qualification + 168 main production + 24 additional cryomodule cavities ordered from an industrial vendor in Europe, following competitive bid process
  Qualification cavities went into “verification cryomodule” (vCM)
Cavity qualification testing overseen by Cavity Technical Board (CTB)
Manufacture @ vendor
Analysis by cavity technical board
reporting
oversight
Vertical qual.
@ partner labs
Cryomodule
assembly
PASS
Analysis by cavity technical board
FAIL /
MARGINAL
minor issue: light rework at labs
major
issue
CTB: SRF experts from SLAC, JLab, and FNAL
Set aside for possible rework

## Slide 22: Cavity hold point data (some examples)
Mechanical measurements
  CMM reports
  Eccentricity
Frequency & field measurements
  Passband modes
  9x9 field flatness measurements
Process data
  Furnace temps and RGA
  EP temps, voltage, current
  Assembly particle counts
Other inspections
  Final visual inspection
  Weld reports
~16 MB per cavity + photos
Example hold point data form
Database & GUI for data review
Example final inspection photo

## Slide 23: LCLS-II-HE cavity timeframes
Mechanical fabrication begins: t=0
Bare 9-cell cavity complete: 6 months
  Hold Point 1 data submitted and reviewed
Steps through doping: +1 month
  Hold Point 2 data submitted and reviewed
Steps through final assembly: +1.5-2 months
  Hold Point 3 data submitted and reviewed
Shipping: +2 weeks
First vertical test: +1 week – 3 months
  Prioritization scheme in place to ensure new and old cavities tested
High pressure rinse and retest: +1-2 months
Timely review of process/hold point data is crucial for identifying production issues

## Slide 24: Vertical qualification testing – requirements
Gradient: Eacc ≥ 23 MV/m
Quality factor: Q0(21 MV/m) ≥ 2.5×1010
  VT stainless steel flange R = 0.8 nΩ
HOM coupling: Qext > 2.7e11
HOM power: PHOM(21 MV/m) < 1.7 W
Field emission: no detectable FE up to quench
Frequency: f = 1300.25±0.10 MHz
Field probe coupling: 2.5×1011 < Qext < 7.0×1011
Multipacting: fully processed before final Q vs. E
7π/9 mode: avoid mode buildup → quick measurements

## Slide 25: High pressure rinse to mitigate field emission
FE example: CAVR017
HPR