## Slide 2: Strategy and installation experience for ESS SRF linac
On behalf of SRF, Cryo and Vacuum team at ESS
Installation activities are supported by IFJ-PAN and WUST ESS IK partners
PRESENTED BY Paolo PIERINI

## Slide 3: Outline
1 The ESS linac
2 Handling of main CM NCRs after reception and testing
3 Pilot installation and cooldown
4 CM Series installation
5 Linac Warm Units
6 Conclusions

## Slide 4
The ESS SRF LINAC
1

## Slide 5: ESS SOUP: 2 MW (capability)
Full ESS scope: 5 MW beam, in phases (43 CMs: 13+9+21)
2 MW for End Of Construction and Start Of User Ops 2027
All infrastructure prepared for 3 MW capability
  Requires +6 CM (+procure 24 RF Systems)
  Cryomodules delivered by IK partners up to the full 5 MW scope, but 5 MW operation not in current project plan
  Not all infrastructure in place (RF cells in gallery)
82 Individual cavities (and associated RF systems), 27 CMs
ISrc
LEBT
RFQ
MEBT
HEBT
SOUP/EOC
MBL
SPK
DTL
HBL
870 MeV
571 MeV
26 SPK
36 MB
20 HB
Cavities
TS2 operation until 2026/06
Test Stand 2 operation
We still have 15 HB CM to test
Vertical integration test stand before operation
Coupler/Cavity conditioning
Calibration
Site Acceptance Test for SRF and Cryo performances
1
3
4/5
352 MHz
704 MHz
13
9
5
See C. Maiano for ELL tests
See M.Zhvoner for SPK tests

## Slide 6: ACC Timeline to BOT
October 2023 Update
Today
Q3
Q4
Q1 2024
Q2
Q3
Q4
Q1 2025
Q2
Q3
Q4
20 May '25 - 19 Jun '25
Beam Commissioning to Target
19 Jun '24 - 12 Jul '24
CM Warm Conditioning
15 Aug '24 - 11 Sep '24
CDS and CM Cooldown/Testing
12 Sep '24 - 23 Oct '24
CM Cold Conditioning
24 Oct '24 - 13 Jan '25
Beam Commissioning to Dump
14 Jan '25 - 27 Jan '25
ACC SAR5
1 Nov '23 - 8 May '24
CM/CDS/DTL5/RF/BI/LWU/Infra/ICS Installation and Testing
26 Mar '25 - 8 Apr '25
Facility SRR5
10 Oct '24 - 23 Oct '24
SRR4
23 Jun '25 - 25 Sep '25
Beam Commissioning to Target
25 Sep '24 - 8 Oct '24
SAR4
13 May '24 - 18 Jun '24
PSS FIT
2024 Summer Holiday
CM Warm Conditioning
12 Mar '25 - 25 Mar '25
Facility SAR5
ACC RBOT
27 Jan '25
Facility RBOT
19 May '25
BOT
19 Jun '25
SAR4
8 Oct '24
SRR4
23 Oct '24
Where are we now?
13 SPK installed
5 MB in tunnel
Beamline connection in progress
Target wheel installed in monolith Solid W target
Partial Beam Dump
Limited power
Licensing process (neutron)
Licensing process (Beam)

## Slide 7: Large In Kind model (Greenfield org)
All accelerator components come from collaboration partners
ISrc
LEBT
RFQ
MEBT
HEBT
Dump
Target
75 keV
3.6 MeV
90 MeV
216 MeV
571 MeV
ISrc
LEBT
RFQ
MEBT
HEBT
ISrc
LEBT
RFQ
MEBT
HEBT
ISrc
LEBT
RFQ
MEBT
HEBT
ISrc
LEBT
RFQ
MEBT
HEBT
TS2/FREIA
DTL-W
RFI
@ESS
@IK
Tunnel
8
7
6
5
5
4
3
2
1
4
3
2
1
13
12
11
10
9
8
7
6
5
4
3
2
1
9
8
7
6
5
4
3
2
1
13
12
11
10
9
21
20
19
18
17
16
15
14
MBL
SPK
DTL
HBL
MBL
SPK
DTL
HBL
MBL
SPK
DTL
HBL
MBL
SPK
DTL
HBL
MBL
SPK
DTL
HBL
Assembly Exceptions @ CEA
Preparation to test
Under test
Ready 4 Install Cold leak 1 CM
SPK 0.5
SPK-010
SPK-020
SPK-030
SPK-040
SPK-050
SPK-050
SPK-070
SPK-080
SPK-090
SPK-100
SPK-110
SPK-120
SPK-130
MBL-010
MBL-020
MBL-030
MBL-040
MBL-050
MBL-060
MBL-070
MBL-080
MBL-090
HBL-010
HBL-020
HBL-030
HBL-040
HBL-050
HBL-060
HBL-070
HBL-080
HBL-090
HBL-100
HBL-110
HBL-120
HBL-130
HBL-140
HBL-150
HBL-160
HBL-170
HBL-180
HBL-190
HBL-200
HBL-210
ELL 0.67
ELL 0.86

## Slide 8
2
Handling of main CM NCRs after reception and testing

## Slide 9: The SPK CTS issue
Main root cause: gearbox coating, enhanced by mechanical “squeeze”
Failures during Uppsala tests lead to perform accelerated lifetime tests
Even after removing the thermalization from the motor body motors in the test bench fail after 20-40 full tuning cycles of the cavities
Concern for the operational reliability
Unfortunately motor access ports were descoped at early project stage before performing EOL testing

## Slide 10: Mitigation strategy
Actions on the tuner motors, at ESS: short and long term
We opened 11/13 SPK cryomodules in lab area to perform actions on the cold tuner systems
  To mitigate chances of early failures in the tunnel
  Developed an in-situ repair tooling for performing action in tunnel (for long term solution)
    Still, an invasive procedure requiring long downtimes if needed

## Slide 11: ELL repairs
CM03 Gauge and CM02-1 in-situ coupler exchange
November 2021
February 2023
Leak after DK assembly: cracked ceramic
Very successful operations, at the max of ESS current repair capabilities: Under discussion the need of a facility for decryostating the cold mass
See C. Madec contribution

## Slide 12
2
Pilot Installation and cooldown

## Slide 13: Pilot installation
Setting of installation procedures
Usual findings
  Collision resolution
  Improve tools/procedure
  Identify correct sequence of assembly operations
From March to June one SPK and one ELL CM were fully installed in the tunnel
  Alignment
  Welding of the CM to VB
  Installation of all support infrastructure
    Connection to RFDS
    Auxiliary He piping (vent lines from burst disk into collector, coupler cooling, He guards
    Water cooling manifolds
    Compressed air
    Cabling
Credits: H. Przybilski

## Slide 14: 2nd cooldown
It took 26 hours to cool down ACCP-CDS and 2 Cryomodules together
Temperature trends of 2nd cooldown
VLP return temperature for CDS
26 hours
TS return temperature for CDS
TS supply temperature for CDS
4K supply temperature for CDS
MBL020 LHe level
ACCP, CDS and two Cryomodules
Configuration at the 2nd cooldown
Credits: J.Frydrich/P. Arnold
Nominal HL achieved, TAO observed in 1st CD suppressed
Endbox LHe level

## Slide 15: Vertical integration across systems
Main scope for pilot installation (without license for HP RF)
Building on the experience of TS2 operation
  Achieved 2 K He level control in both SPK and MBL
  Flawless readout of all internal sensors, operation of heater
  Implemented fault tolerance on level sensors
Credits: N. Elias
SPK-110Crm
MBL-020Crm
QL=7.02 105
FWHM=1 kHz
Cold cavity transmission from klystron gallery

## Slide 16
3
CM Series Installation

## Slide 17: CDS Preparation
Area prepared/cleared, loops opened, module in nominal position
Credits: H. Przybilski

## Slide 18: Weld of CM to CDS
Additional work to compensate for the CDS misalignment
Credits: H. Przybilski
Individual “tailoring” of each process line
Additional work to compensate for a misalignment of the CDS

## Slide 19: Ancillary completion
To water, compressed air, vacuum manifolds, He collector line, rf
Water manifold
Vacuum-Isovac angle valve
Cryo connections from RD
Doorknob assembly
Coupler bias feed/rf choke
Pilot installation was extremely important
Pilot: 2 months
12 CM: 5 months
Full scope in Jan 2024
Credits: H. Przybilski

## Slide 20: Non conformities during assembly
Usual amount, requiring corrective actions due to lack of QA handover
Credits: H. Przybilski
Dirty Valves
Wrong material grade(rust)
Scratches
Workshop machining on components that were integrated for the first time at ESS, e.g. DK to allow stress-free installation
Cleaning and refurbishing of all 2K environment protection valves (leaky)
Damage to He Guard piping due to collision with scissor lift by contractor

## Slide 21
4
Linac Warm Units

## Slide 22: Particle free systems
In spoke and elliptical, the LWU beam pipes follow particle free workflow
Cleaning and assembly in ISO 4 clean room!
Cleaning and assembly in ISO 5 clean room!
Credits: A. Gevorgyan
Linac Warm Units
Doublet, steerer, BPM and Beam Diagnostics
(And some include wire scanners and insertable beam stops)

## Slide 23: Procedures for all metal gate valves
From testing and handling
ISO 2 cleanroom equivalent
ISO 5 cleanroom equivalent
Inspect valves before
integration
Photos by Pierre Bosland,
CEA, Saclay.
Test
Early issue!
Coupling nuts were removed during cryo module assembly They are unique for each valve, although they look the same
Block of the rod during long-term transportation
@ESS
Credits: A. Gevorgyan

## Slide 24: Use of NEG pumps in LWU (ZAO alloy)
CM volume is pumped through LWU
Cleaned and assembled in ISO 4
Images by D. Hardion and T. Cornes. ESS
Credits: A. Gevorgyan
ISO 6 equivalent. After 1st Activation
ISO 6 equivalent. As received before activation
ISO 3 equivalent. After 4th Activation
2nd and 3rd activation show ISO 6 compatibility

## Slide 25: NEG ZAO Transport test
Uncontrolled transport (no damping, no shock monitoring)
Before transport test, cleaned for ISO 4
After transport test ISO 4 is preserved
In-vacuum transport is better than N2. Van der Waals forces help. Even though the NEG pump generates particles, in vacuum, they will fall down (gravity) and do not move …orientation and location of pump is important. Note: severe vibration is still a problem.
Only laminar gas flow during venting or pumping vacuum systems. Maximum flow 3l/m. Delta P=1mbar.
Credits: A. Gevorgyan

## Slide 26: Qualification of assembly conditions
Tunnel setup, with concurrent operations during major piping assembly
High numbers of particles are due to the
counter installation (multiple entering/exiting the room).
Particles settling slowly …yes, a day or two is needed!
Major impact, due to welding, grinding, cutting activities.
Source is 5-8 meter far from the clean room.
Barrier off the zone at least a day before…
Running cleanroom is important… to maintain the cleanliness
Cover with plastic dirty parts.
Credits: A. Gevorgyan

## Slide 27: Installation ongoing
9 LWU in SPK area, 4 connected and pumping currently CM
NEG ZAO
NEG ZAO
Credits: A. Gevorgyan
Wire scanner unit
Achieved 1E-8 mbar vacuum conditions in a couple of days from static conditions of CMs at 1E-2 mbar

## Slide 28: Summary
Delivering 2 MW beam capability (870 MeV, 62.5 mA) in 2024
The installation of the SRF linac is ongoing at a fast pace
Presently: 13 SPK,5 MB CM and 9 LWU are being integrated in the tunnel
Installation of all 13 SPK, 9 MB and 5 HB, and all LWU between them, to achieve a 2 MW capability, will be complete by May 2024
Cooldown of the entire linac is scheduled for August 2024
Beam commissioning on the beam dump (BOD) is foreseen in October 24 after
  Conditioning and technical commissioning of all SRF equipment
  Fullfilling all administrative steps to obtain beam licence from authorities
Beam commissioning to the target (BOT) is foreseen in Mid 2025, after obtaining the licence for Intentional Neutron Production from authorities