## Slide 1: Hi Lumi LHC Crab Cavity Cryomodules
Niklas Templeton
STFC Daresbury Laboratory
UK Crab Cavity Cryomodules WP Lead

## Slide 2: Crab Cavity Cryomodules for Hi Lumi LHC
UK 4-Rod Cavity Prototype 2012
DQW SPS Cryomodule 2018
RFD SPS Cryomodule 2023
Hi Lumi LHC Crab Cavities
Crabs Collaboration
Design Features & Innovations
RFD SPS Prototype Cryomodule Build
UK Lessons Learnt (so far)

## Slide 3: Hi Lumi LHC Crab Cavities
To maximise discovery potential of LHC by increasing rate of collisions
400 MHz crab cavities to mimic head on collision
4 cavities installed either side of Interaction Points
Double Quarter Wave (DQW) – vert. crabbing at CMS
RF design by BNL & CERN
Supplied by CERN & R.I.
Radio Frequency Dipole (RFD) – horiz. crabbing at ATLAS
RF design by ODU
Supplied by US-AUP & Zanon
DQW & RFD Crab Cavities

## Slide 4: HL-LHC Crab Cavity Collaboration
5 DQW cryomodules | 5 RFD cryomodules | 20 RF Systems
Cavities + processing + helium vessels by Research Instruments (DE) & CERN Cold magnetic shields by UK HOM couplers + antennas by CERN 4 CM by UK (STFC) & 1 CM at CERN with some components from CERN All cavities & CM cold validation tests at CERN (and a back up at Uppsala-Sweden) | Bare cavities by Zanon (IT) under US-AUP Processing + cold magnetic shield + helium vessel + HOM couplers + antennas + cold tests by US-AUP 5 CM by TRIUMF-Canada with some components by CERN CM cold validation tests at CERN | High power amplifiers (IOT) CERN-KEKB High power RF lines, circulators, loads by CERN-KEKB TCA platform for LLRF by CERN
5 DQW cryomodules | 5 RFD cryomodules | 20 RF Systems
Cavities + processing + helium vessels by Research Instruments (DE) & CERN Cold magnetic shields by UK HOM couplers + antennas by CERN 4 CM by UK (STFC) & 1 CM at CERN with some components from CERN All cavities & CM cold validation tests at CERN (and a back up at Uppsala-Sweden) | Bare cavities by Zanon (IT) under US-AUP Processing + cold magnetic shield + helium vessel + HOM couplers + antennas + cold tests by US-AUP 5 CM by TRIUMF-Canada with some components by CERN CM cold validation tests at CERN | 
Thanks to Rama Calaga

## Slide 5: Dressed Cavity Equipped
Bolted Ti He Tank
Secondary Line
HOM Coupler
Fundamental Power Coupler
Tuner
RF Pick-Up
Inner Mag Shield
Tuner Frame
Survey Targets

## Slide 6: Cavity Support System
FSI Position Monitoring
Flexure Blades
FPC Fixed Point
~200kg Offset Mass
5-Point Kinematic Adjustment
TOP PLATE
FSI Head
Target
Common Support Plate

## Slide 7: Thermal Screen
Ti Compensation Washers
Al6061 Panels (t=2mm)
Cu Braids - Direct to Pipes
Al Pipe-Panel Clamps
Al Stiffeners & Nut Plates
Low Cost
Minimal Brazing/Welding
Ease of Assembly
Thermal Performance Validated
Series Pipe-Panel Clamps
St. Steel Cryo Circuit

## Slide 8: Build Overview
Thanks to Teddy Capelli
Guide Rods
Pushers
Crane Lift
2 Bays
Fine
Adjustment
Cryostating Infrastructure

## Slide 9: Detailed Build Procedures
Poster logic + tooling & infrastructure
Part of Traveller (QA)
Troubleshoots & de-risk build
Captures critical requirements, torques & sign-off
‘BOM kits’ pre-prepared by sub-step
Over 900p produced!

## Slide 10: RFD Highlights (1/2)
Cavity string pre-cleanroom
Cleanroom assembly
First Welds
Upper cryo install
Top plate integration
Load Transfer Complete

## Slide 11: RFD Highlights (2/2)
Thermal Screen
50K MLI
Instrumentation
Lower Cryomodule Integration
Shipping

## Slide 12: 4 Lessons Learnt
…with memorable titles
RFD Lowlights…
“Learn from the mistakes of others. You can't live long enough to make them all yourself.” – Eleanor Roosevelt

## Slide 13: Protect Ya Bellows
Issue: hydroform bellows dent pre-cleanroom
Impact: minor (thankfully)
Root cause: assembly procedure execution error
Mitigations:
Better comms between engineers & technicians
  Procedure roll-out & sign-off
  More technical oversight
  Many phone calls
Additional bellows protection installed

## Slide 14: Take On M.E.
Issue: Re-design of test rig & re-qualification of Bi Phase line
Impact: Many months delay to manage QA & resolve NCs
Root Cause: Poor supplier QA
Mitigations: developed & brought in-house:
Welding & weld engineering
Steel procurement
Design of weld-test-transport jigs
(Multi-complex Engineering)

## Slide 15: Respect Yo QMS
Issue: removal & replacement of NC bellows sub-assembly after delivery
Impact: Many weeks to fabricate, re-work & re-qualify
Root Cause: QA processes not followed
Mitigations:
Improved quality training & refreshers
More QA oversight
Local instructions to remove QMS barriers
(Quality Management System)

## Slide 16: Mo Checks – Less Problems
Issue: damage to power couplers discovered at CERN
Root cause analysis & resolution: on-going
Hypothesis: complex load transfer issue
Mitigations:
Tooling design improvements
More intermediate test & checks
  ISO4 glovebox for beamline tests
  Fundamental power coupler checks
BUILD CHECK & TEST (HOLD) POINTS |  |  |  |  | 
Step # | Activity | Alignment | RF | Leak Test | Other
0 | Cavity string pre-assembly | Y |  |  | 
1 | ISO4 string assembly |  | Y | Beamline | 
2 | FPC assembly |  | Y | Beamline | 
3 | Bi Phase welding |  |  | Welds | 
4 | Tuner & thermal links |  |  |  | 
5 | Top plate integration | Y | Y | Welds | 
6 | Top plate load transfer | Y | Y |  | 
7 | Lower cryolines & instr'n |  |  | Welds | Instr'n
8 | 2K MLI |  |  |  | 
9 | Thermal Screen & 50K MLI |  |  | Welds | 
10 | Cryomodule load transfer | Y | Y |  | 
11 | Vacuum equipment |  |  | 2ndline | 
12 | Cryomodule doors |  |  |  | 
13 | Outgoing acceptance | Y | Y | Insu-vac, Beamlines | Pressure, LN2, Instr'n
14 | Transport tooling & frame |  |  |  | Shockloggers

## Slide 17: Hi Lumi Crab Cavity Cryomodules
RFD SPS Cryomodule delivered Oct ’23 with many challenges & obstacles overcome!
Next: series LHC Cryomodules:
DQW: 1x CERN + 4x STFC
RFD: 5x TRIUMF
>10k components (5k unique)
>900 procedure pages
56 CM welds (24 types)

## Slide 18: Thanks! Questions?
Thanks to all Hi Lumi Crabs collaborators for their contributions

## Slide 19
Poster by Teddy Capelli

## Slide 20: RFD Thermal Budget
Thermal budget report for RFD
See EDMS 2310389 - Thermal budget RFD cryomodule
Courtesy J.Swieszek – L.Giordanino
Static + Dynamic 4.1 MV (40 kW FPC) |  |  | 
Source | 2 K | 10 K | 80 K
Radiation | 3.4 | - | 30.0
CWT | 6.0 | 1.0 | 50.6
Supports Cav1 | 0.4 | 2.1 | 8.0
Supports Cav2 | 0.5 | 0.9 | 5.0
FPC | 4.8 | 4.6 | 46.4
VHOM lines | 1.4 | 2.6 | 13.0
VHOM antennas | 0.2 | - | -
HHOM lines | 1.4 | 2.6 | 13.0
HHOM antennas | 0.5 | - | -
Pickup lines | 2.0 | - | 10.6
Pickup antennas | 0.0 | - | -
Tuner | 0.8 | - | 10.2
Instrumentation | 2.3 | - | 10.0
He level sensor | 0.4 | - | 0.8
Cryo safety device | 0.7 | - | 4.8
Beam screen | 1.4 | - | -
Beam impedance | - | - | -
Cavity | 20.0 | - | -
 | 46.2 | 13.8 | 202.4

## Slide 21: Transport Frame Design & Test
38mm drop test performed with a dummy CM
~80% shock isolation

## Slide 22: Welding Developments at Daresbury
Weld Procedure Specifications
Sample qualification: dye & macroscopic

## Slide 23: Upper (Bi Phase) Cryoline
Support for bellows dP