## Slide 1
Cost and Schedule
D. Sherese Humphrey
PIP-II Beam Instrumentation Laser Wire Final Design Review
May 2, 2024

## Slide 2: Contents
Schedule
Cost
Labor
Procurement
Summary

## Slide 3: Summary Schedule
We have sufficient total float to accomplish milestones associated with the laser wire scope.

## Slide 4: Cost
Materials
Labor

## Slide 5: Resources
Laser Wire effort of order 5.5 FTE
Technical demand rises to build production units
Resource demand drop with handoff to installation and commissioning with beam
  Still have BI personnel working under installation and commissioning
Resources needs identified in P6
  Actively recruiting new hires
    Engineering physicist hired in 2023
    Two electrical engineers hired in 2023
        Two electrical engineers lost in the past year
    Part-time technicians coming from College Of DuPage
    DOE funding agreement
Coordinating with directorate for additional personnel
Total PIP-II Beam Instrumentation Staffing Plan

## Slide 6: Laser Wire Procurement Planning
Laser Wire Beamline Hardware
  1st Units for Vacuum, Optical Components, and Stand
  Remaining production ordering will occur post-first units assembly and evaluation
  Orders from a single vendor exceeding $250K will require Procurement Readiness Review (PRR)
Bundled Procurements (primarily <$250K)
  Optical Transport Line
  Laser System
  DAQ and Controls Hardware
Assembly and Testing will be performed in-house

## Slide 7: Summary
Overall scheme, scope of work is $4M
Labor and M&S budget identified, working against this plan
  Labor estimates will be reassessed to ensure staffing plans remain adequate
Bulk of cost is M&S
Work expected to be completed well before needed