## Slide 1
Dean (Chip) Edstrom
07/21/2023
IOTA Proton Injector Update

## Slide 2: IPI Project Schedule
Action Items:
  Source HV Testing (ORC-2176)
    Began HV testing… Continuing
    Hydrogen Distribution Checkout
    HV Enclosure Control Checkout to follow
  Mechanical Engineering
    Engineering Notes: Steve Wesseln finalizing MEBT stand configuration
    15-Deg Bend Chamber Req 346933 – No movement in purchasing…
  Cable Pull / 600A Disconnect
    Any Update?
    24-Conductor cable backorder extended to Late August at earliest (!!)
      Abandoning this and adjusting the cable pull to include more 10-Conductor runs.

## Slide 3: Source HV Test – ORC 2176
Initial attempt (7/19) ran into the Paschen curve
  Arcing at 2 kV through the evacuated Hydrogen Distribution stand-off
  Closed the bypass, let the distribution up to Atm, and ran to 5 kV
Next attempt (7/20) – 41kV max
  Arcing from extraction anode corona suppressor contact to the source stand
  Adjusted positioning from 8:00 to 10:00 position to maximize the gap
Latest attempt (7/20) – 47kV max
  Persistent arcing found in the contactor section
  Suggests failed cable insulation… Re-termination is the likely fix.