## Slide 1
Dean (Chip) Edstrom
08/10/2023
IOTA Proton Injector Update

## Slide 2: IPI Project Schedule
Action Items:
  Source HV Testing (ORC-2176)
    Began HV testing… Continuing
    Hydrogen Distribution Checkout
    HV Enclosure Control Checkout to follow
  Mechanical Engineering
    Engineering Notes: Steve Wesseln finalizing MEBT stand configuration… Getting help with #3
    Variable Coupler Stand Ordered.
    15-Deg Bend Chamber Req 346933 – RFP due 08/25 (bidding ends COB)…
  Cable Pull / 600A Disconnect
    Any Update?
    Cancelled 24-Conductor cable due to extreme backorder
      Adjusted the cable pull to include more 10-Conductor runs and ordered from Stock room… 2/5 reels in.

## Slide 3: Source HV Test – ORC 2176
Initial attempt (7/19) ran into the Paschen curve (2kV)
Next attempts:
  7/20, 41kV max
  7/20, 47kV max
Cleaned Ross Relay Contactor and began Configuration Adjustments
  8/02, 49.12kV max
  8/04, 49.80kV max
  Consistent external sparking in contactor & Ext to Gnd
Now focusing on Voltage Divider
  MDB Setup Included voltage divider
    50 MΩ between HV Common & Extractor
    250 MΩ between Extractor & Ground
    Extractor power supply running DC in parallel with 50 MΩ resistor in -1:5 ratio with HVPS (e.g. -10 kV for 50 kV common)
    Current Pulsed Extractor Needs to be addressed

## Slide 4: Other Progress
HLRF Modulator Controls Installation (RR280 / RR281)
  Nick Gurley leading the effort
  Will require 600A Disconnect installation to conclude
Allison Scanner Controls (RR298)
  Andrea Saewert leading the effort
  Needed for Source Characterization
LLRF Upgrade (EPICS Interface)
  Euclid Techlabs Performing Upgrade Work
  Expected complete late August