## Slide 1
Main Injector Shutdown Status
D. Morris
9 o’clock Meeting
August 18th, 2023

## Slide 2
General
8/18/2023
MI Department Meeting | D. Morris
2
New tunnel surveys are out = new tunnel briefings.
Preparing for HVAC installation impact
Will maintain networking, CAMAC, Vacuum systems
Will power down correction elements, BPM, BLM systems, and more…
MI-10 and MI-20 start Aug. 21st.

## Slide 3
Tunnel Work
8/18/2023
MI Department Meeting | D. Morris
3
Crews are doing vacuum rework in MI-8. Includes replacing LCW header
supports and moving a compressed air line.
Performing final leak check from 810 to 824.
Temporarily removed MW825 guts. Welding finishing up.
Scheduled power outage Tuesday afternoon.
Q333 (IQB-067) LCW leak. Moved the octupole and adjusted the sextupole
to make more space for welding. Ready for repair.
White hose replacement (MI-50 through MI-60) started Tuesday

## Slide 4
Tunnel Work
8/18/2023
MI Department Meeting | D. Morris
4
MIRF#11 cavity removed for water path rework. RF maintenance continues.

## Slide 5
Tunnel Work
8/18/2023
MI Department Meeting | D. Morris
5
Defocusing quad bus ground fault as been isolated to the Q319 (IQC009) quad.
Rebuilt IQCB241-0 has been delivered to MI-60.

## Slide 6
Conventional Power Outages
8/18/2023
MI Department Meeting | D. Morris
6
There are no scheduled conventional power outages in MI/RR until next
week.
Please report any MI outages to the MCR.

## Slide 7
MI-20 Sump Line Repairs
8/18/2023
MI Department Meeting | D. Morris
7
Work is progressing well.
Exterior work is mostly done except for survey/berm final grading.
Stairwell work continues with check valves and “Y” pipe installation.

## Slide 8
MI-20 Sump Line Repairs
8/18/2023
MI Department Meeting | D. Morris
8