## Slide 1
Main Injector Shutdown Status
D. Morris
9 o’clock Meeting
August 25th, 2023

## Slide 2
General
8/25/2023
MI Department Meeting | D. Morris
2
HVAC installation underway at MI-10 and MI-20.
Will maintain networking, CAMAC, Vacuum systems
Will power down correction elements, BPM, BLM systems, and more…
Follow worksite access rules (HA, PPE etc.).
MI-30 HVAC work starts 8/31 (Monday) MI-40 HVAC work starts 9/1 (Friday)

## Slide 3
Tunnel Work
8/25/2023
MI Department Meeting | D. Morris
3
Crews are doing vacuum rework in MI-8. Includes replacing LCW header
supports and moving a compressed air line.
Leak tight 810 to 824. High humidity has moved them to other jobs until next week.
Q333 (IQB-067) LCW leak.
Repair made.
Hydo testing permit in approval process
Q319 faulted quad replacement planning in progress
As-Found scheduled for Wednesday
White hose replacement (MI-50 through MI-60) started last week.
MI50 and MI-60 sectors. Already completed most of 50 sector.

## Slide 4
Tunnel Work
8/25/2023
MI Department Meeting | D. Morris
4
MIRF#11 cavity removed for water path rework. RF maintenance continues.
Replaced 600 L/s ion pump at 606.

## Slide 5
Tunnel Work
8/25/2023
MI Department Meeting | D. Morris
5
Defocusing quad bus ground fault as been isolated to the Q319 (IQC009) quad.
Rebuilt IQCB241-0 has been delivered to MI-60.
Need to verify IQCB241 and confirm IQC009.

## Slide 6
Conventional Power Outages
8/25/2023
MI Department Meeting | D. Morris
6
There are no scheduled conventional power outages in MI/RR until next
week.
Please report any MI outages to the MCR.

## Slide 7
MI-20 Sump Line Repairs
8/25/2023
MI Department Meeting | D. Morris
7
Work is progressing well.
Exterior work is mostly done. Waiting on results from berm topo.
Work in the stairwell is complete. Waiting on check valves for final
“Y” pipe installation.